## 11 12 CONTRACTS Final
WEBSITE REPORT: WDM CONTRACT ENTERED INTO DURING THE FINANCIAL YEAR 2011/12 FROM 1 JULY 2011 TO 30 JUNE 2012
No. | Tender Number | IDP Project # | Project Description | Date Awarded | Service provider |  | Amount Awarded (VAT Excl) | Amount Awarded (VAT Inc) | Date Signed SLA | On -site start Date | SLA Completion Date | Actual Completion Date | SLA Extension | DEPT
1 | LIMITED BIDDING | DIN27 | IFMS - WDM | 2011-09-07 | Munsoft (Pty) Ltd |  | 1995062 | 2274370.68 | 2011-09-07 | 2011-11-01 | 2031-09-07 | 2011-11-30 | None | BTO
2 | LIMITED BIDDING | DIN27 | IFMS - Belabela Local Municipality | 2012-01-26 | Munsoft (Pty) Ltd |  | 2066911 | 2356278.54 | 2011-11-01 | 2011-11-30 | 2012-06-30 | 2012-02-28 | None | BTO
3 | LIMITED BIDDING | DIN27 | IFMS - Thabazimbi Local Municipality | 2012-01-26 | Munsoft (Pty) Ltd |  | 1945479 | 2217846.06 | 2011-11-01 | 2012-01-31 | 2012-06-30 | 2012-03-30 | Addendum SLA effective from 1 July 2012. | BTO
4 | LIMITED BIDDING | DIN27 | IFMS - Modimolle Local Municipality | 2012-06-01 | Munsoft (Pty) Ltd |  | 272405 | 310541.7 | 2012-05-01 | 2012-08-20 | 2012-06-30 | 2012-06-30 | None | BTO
5 | LIMITED BIDDING | DIN17 | Mayoral vehicle | 2011-07-29 | McCarthy Mercedes Benz fountain Ltd (public co) |  | 649348 | 740256.72 | 2011-09-11 | 2011-09-01 | 160 000KM | 2011-09-01 | None | CSSS
6 | WDM/2011/12-01 | 0315150 | Provision of Legal Services (3 years contract) | 2011-11-22 | Verveen Attorneys | Fees are charged depending on the service rendered | 900000 | 1026000 | 2011-11-25 | 2011-11-25 | 2014-11-25 | 2014-11-25 | None | CSSS
7 | WDM/2011/12-02 | 03-15151, etc | Provision of Travelling Agency (3 years contract) | 2011-11-01 | Badiredi Travel | Fees are charged depending on the service rendered | 7500000 | 8550000 | 2011-11-07 | 2011-11-07 | 2014-11-07 | 2014-11-07 | None | CSSS
8 | S32 WDM 2011/12-01 | IN043 | Procurement and Installation of CCTV Cameras | 2012-01-16 | Siyenza Holdings (PTY) LTD |  | 436891.2193 | 498055.99 | 2012-02-21 | 2012-02-21 | 2012-03-21 | 2012-03-21 | None | CSSS
9 | WDM/2011/12-29 | DIN017 | Supply and installation of office furniture. | 2012-03-19 | Ungani Interiors |  | 175169.2982 | 199693 | 2012-03-26 | 2012-03-26 | 2012-05-26 | 2012-05-08 | None | CSSS
10 | WDM/2011/12-19 | DIN021 | Supply and delivery of Disaster Recovery Solution | 2012-03-19 | Business Connexion |  | 269690.4474 | 307447.11 | 2012-04-12 | 2012-04-12 | 2012-06-12 | 2012-06-12 | None | CSSS
11 | S32 WDM 2011/12-02 | IN043 | Supply and Installation of Municipal Chamber's Recording System | 2012-03-23 | MT Sound & Tours CC |  | 427001.11 | 427001.11 | 2012-04-29 | 2012-04-29 | 2012-05-29 | 2012-05-29 | None | CSSS
12 | WDM/2011/12-30 | 015170/015203/ 017870 | Provision of security services | 2012-05-08 | Triotic Protection Services |  | 1651812.48 | 1883066.2272 | 2012-07-01 | 2012-07-01 | 2015-06-30 | 2015-06-30 | None | CSSS
13 | LIMITED BIDDING | 002 015154 | Provision of institutional study | 2012-05-31 | Endurance Business Consulting |  | 256842.11 | 292800.0054 | 2012-05-31 | 2012-06-01 | 2012-06-30 | 2012-06-30 | None | CSSS
14 | LIMITED BIDDING | 015170/015203/ 017870 | Extension of provision of security Services | 2012-02-23 | Fawcett Security Services |  | 310834.386 | 354351.2 | 2012-02-23 | 2012-03-01 | 2012-04-23 | 2012-06-30 | None | CSSS
15 | WDM/2011/12-04 | DM011 | Mogalakwena Fire Fighting Equipment | 2011-11-21 | IBL Fire Fighting Equipment CC | 761594.1 | 668065 | 761594.1 | 2012-02-08 | 2012-02-13 | 2012-07-08 | In-progress | None | Disaster
16 | WDM/2011/12-07 | DM016 | Refurbishment Toyota Land Cruiser and new mounted Equipment - Mookgopong | 2011-11-22 | Marce Marketing CC | 347845.72 | 305127.8246 | 347845.72 | 2012-02-06 | 2012-02-07 | 2012-05-06 | 2012-05-31 | None | Disaster
17 | WDM/2011/12-08 | DM032 | Refurbishment of Mogalakwena Standby Diesel Generator | 2011-11-22 | Joint Venture Golden Dividend 187 (Pty) Ltd and Sunset Bay Skin and Body Clinic | 108300 | 95000 | 108300 | 2012-02-03 | 2012-02-06 | 2012-05-03 | In-progress | None | Disaster
18 | WDM/2011/12-09 | DM033 | Refurbishment of Toyota Dyna - Mogalakwena | 2011-11-22 | Marce Marketing CC | 93840.19 | 82315.9561 | 93840.19 | 2012-02-06 | 2012-02-07 | 2012-05-06 | 2012-05-31 | None | Disaster
19 | WDM/2011/12-10 | DM034 | Refurbishment of Unimog Fire Engine - Mogalakwena | 2011-11-22 | Marce Marketing CC | 403663.5 | 354090.7895 | 403663.5 | 2012-02-06 | 2012-02-07 | 2012-05-06 | 2012-05-06 | None | Disaster
20 | WDM/2011/12-11 | DM017 | 4X4 Double Cab Medium Pumper and Mounted Fire Fighting Equipment - Belabela | 2011-11-22 | Fire Raiders (Pty) Ltd | 1926154.03 | 1689608.7982 | 1926154.03 | 2012-02-08 | 2012-02-13 | 2012-09-08 | In-progress | None | Disaster
21 | WDM/2011/12-13 | DM036 | Water Tanker (10 000 Litres) | 2011-11-22 | Fire and Emergency Vehicle (Pty) Ltd | 1248984 | 1095600 | 1248984 | 2012-02-06 | 2012-02-07 | 2012-09-06 | In-progress | None | Disaster
22 | WDM/2011/12-14 | DM038 | Modimolle - Medium Double Cab Rapid Intervention Vehicle (RIV) | 2011-12-13 | Fire Raiders (Pty) Ltd | 1295632.97 | 1136520.1491 | 1295632.97 | 2012-02-08 | 2012-02-13 | 2012-09-08 | In-progress | None | Disaster
23 | WDM/2011/12-15 | DM031 | Lephalale Hazardous Material (Hazmat) Trailer | 2011-11-22 | Marce Marketing CC | 440860.8 | 386720 | 440860.8 | 2012-02-06 | 2012-02-07 | 2012-05-06 | 2012-05-31 | None | Disaster
24 | WDM/2011/12-16 | DM035 | Thabazimbi Hazardous Material (Hazmat) Trailer | 2011-11-22 | Marce Marketing CC | 440860.8 | 386720 | 440860.8 | 2012-02-06 | 2012-02-07 | 2012-05-06 | 2012-05-31 | None | Disaster
25 | WDM/2011/12-18 | CO009 | Production of WDM Newsletter | 2011-11-22 | 7th Question Marketing and Communications | 492074.16 | 431644 | 431644 | 2012-02-08 | 2012-02-08 | 2013-01-08 | 2013-01-08 | None | EMO
26 | LIMITED BIDDING |  | Provision of Athletics Management Services | 2012-05-03 | Limpopo Athletics (LIMA) |  | 150000 | 150000 | 2012-05-03 | 2012-05-03 | 2012-06-03 | 2012-06-09 | None | EMO
27 | WDM/2010/11-10 | RS21 | Consultants fees for the completion of Modimolle Ring Road Phagameng | 2011-10-24 | Phakama Knight Piesold (PTY)LTD |  | 522392.52 | 595527.4728 | 2011-11-15 | 2012-05-22 | 2012-06-30 | 2012-09-30 | None | ID
28 | WDM/2010/11-08 | RS040 | Consultants fees for the completion of paving of Bela-bela Street | 2011-10-24 | Tlou Integrated Tech CC |  | 356134.72 | 405993.5808 | 2011-11-18 | 2012-05-23 | 2012-06-30 | 2012-09-30 | None | ID
29 | WDM/2010/11-09 | RS041 | Professional fees for tarring of street in Mahwelereng | 2012-02-08 | Ntsu Engineering Consultants CC |  | 321624.9474 | 366652.44 | 2012-02-28 | Contractor not yet appointed | 2012-07-28 | N/A | None | ID
30 | WDM/2011/12-26 | RS21 | Completion of Modimolle Ring Road-Phagameng | 2012-05-08 | Mafafo Building Construction CC |  | 1726309.73 | 1967993.0922 | 2012-05-22 | 2012-05-22 | 2012-09-22 | 2012-09-22 | None | ID
31 | WDM/2011/12-25 | RS40 | Completion of Bela-Bela Street Paving- Radium ( Masakhane | 2012-05-08 | Mmamokgoshi Construction |  | 1596610.4 | 1820135.856 | 2012-05-23 | 2012-05-23 | 2012-09-23 | 2012-09-23 | None | ID
32 | LIMITED BIDDING | IN24 | Performance Management System | 2012-02-24 | Institute for Performance Management |  | 1661208 | 1893777.12 | 2011-05-19 | 2011-11-30 | 2012-06-30 | 2012-06-30 | 2012-09-30 | OMM
33 | WDM/2011/12-28 | DN039 | Audit Information Technology | 2012-05-08 | Sema Integrated Risk Solution |  | 393145 | 448185.3 | 2012-05-31 | 2012-04-06 | 2012-08-30 | 2012-04-09 | None | OMM
34 | ORGAN OF STATE | IN035 | Lephalale Recycling Club Project | 2012-04-04 | Lephalale Local Municipality |  | 420000 | 420000 | 2012-04-13 | 2011-06-30 | 2012-08-13 | In-progress | 2012-11-30 | OMM
35 | LIMITED BIDDING | DUE40 | Cofounding of Waterberg Meander Reserve 2011/12 | 2011-08-22 | Waterberg Biosphere Reserve |  | 100000 | 100000 | 2011-10-10 | 2012-07-01 | 2012-10-09 | 2012-06-30 | None | PED
36 | WDM/2011/12-22 | LA012 | Mookgopong CBD Development Plan | 2011-12-20 | Joint Venture MOK Development Consultants CC and Plan Associates | 473100 | 415000 | 473100 | 2012-02-16 | 2012-02-16 | 2012-09-16 | 2012-08-16 | None | PED
37 | WDM/2011/12-23 | LA012 | Thabazimbi CBD Development Plan | 2011-12-20 | Joint Venture MOK Development Consultants CC and Plan Associates | 460000 | 403508.7719 | 460000 | 2012-02-16 | 2012-02-16 | 2012-09-16 | 2012-08-16 | None | PED
38 | WDM/2011/12-24 | SE017 | Development of Landfill Site in Modimolle | 2012-11-22 | Keletshepile Trading Enterprise | 1525105 | 1674555 | 1674555 | 2011-12-07 | 2012-12-07 | 2012-06-07 | 2012-01-18 | 2012-02-15 | SDCS
39 | LIMITED BIDDING | 009 015125 | Office Rental Mokopane - EHPs | 2012-05-02 | Reality Dynamix 46 Pty LTD | 333000 | 333000 | 333000 | 2012-05-02 | 2012-05-01 | 2013-04-30 | 2013-04-30 | None | SDCS
40 | LIMITED BIDDING | 009 015125 | Office Rental Thabazimbi - EHPs | 2012-05-03 | Bertie Joubert Properties CC | 60000 | 60000 | 60000 | 2012-05-03 | 2012-05-01 | 2013-04-30 | 2013-04-30 | None | SDCS
41 | LIMITED BIDDING | DIN041 | Implementation of Virtual Private Network | 2012-06-28 | SITA | 4640666.9474 | 4640666.9474 | 5290360.32 | 2012-06-28 | 2012-07-01 | 2015-06-30 | 2015-06-30 | None | CSSS
Note on H8: Laubscher: Based on past payment history, average of R 300,00 per year, as the minimum
Note on H9: nlaubscher: 11/12 Budget * 3 year - to be prudent, no increases added. Included all S&T votes.