## D4=Contract report 12 13
ANNEXURE D 4 :- WDM CONTRACTS ENTERED INTO DURING 12/13 AS AT 31 DECEMBER 2012
NO | Tender Number | IDP Project # | Project Description | Date Awarded | Service Provider/ Contractor | Amount Awarded (Vat excl) | SLA signed | On-site start date | SLA completion date | Actual completion Date | SLA Extension | Dpt | Manager`s comment | Challenges
1 | S32/2012-13/01 | IN 043 | Procurement and Installation of CCTV Cameras | 2012-08-13 | Siyenza Holdings | 1002257 | 2012-09-03 | 2012-09-03 | 2012-12-03 | 2012-12-31 | None | CSSS | Project completed | None
2 | WDM/2012/13-01 | DM039 | 4X2 Medium Mobile Command unit (fully equipped) | 2012-12-12 | IBL Fire Fighting Equipment CC | 1605995 | 2013-01-22 | 2013-01-22 | 2013-09-22 | In progress | None | Disaster | None | None
3 | WDM/2012/13-02 | DM041 | Lephalale 4X 4 Major Urban Rescue Pumper and Equipment | 2012-12-12 | Fire and Emergency Vehicle (Pty) Ltd | 2917144 | 2013-01-22 | 2013-01-22 | 2013-09-22 | In progress | None | Disaster | None | None
4 | WDM/2012/13-03 | DM042 | Bela- Bela 4X 2 Double Cab RIV (fully equipped) | 2012-12-12 | Fire Raiders (Pty) Ltd | 1139548.03 | 2013-01-22 | 2013-01-22 | 2013-08-22 | In progress | None | Disaster | None | None
5 | WDM/2012/13-04 | DM043 | Mookgophong medium bush pumper and equipment | 2012-12-12 | Marce Fire Fighting Technology cc | 1290039.35 | Not yet | Not yet | Not yet | Not yet | None | Disaster | None | None
6 | WDM/2012/13-05 | DM015 AND DM044 | Thabazimbi and Modimolle: 4X4 LDVs with Skid units and equipment | 2012-12-14 | Fire and Emergency Vehicle (Pty) Ltd | 869092 | 2013-01-22 | 2013-01-22 | 2010-05-22 | In progress | None | Disaster | None | None
7 | WDM/2012/13-06 | DM046 | Refurbishment of Iveco Truck | 2012-11-28 | Marce Fire Fighting Technology cc | 98240.15 | Not yet | Not yet | Not yet | Not yet | None | Disaster | None | None
8 | WDM/2012/13-07 | DM045 | Modimolle Heavy duty foam canon trailor | 2012-11-29 | Wake up Investments T/A Rural Fire Rescue | 154616.14 | Not yet | Not yet | Not yet | Not yet | None | Disaster | None | None
9 | WDM/2012/13-08 | DM040 | Supply and delivery of Thabazimbi and Mogalakwena army tents and bales of relief blankets | 2012-11-28 | Fastpulse Trading 42 (Pty) Ltd T/A Trans Continental Tarps | 374561.4 | 2012-01-22 | 2012-01-22 | 2012-04-22 | In progress | None | Disaster | None | None
10 | WDM/2012/13-09 | DM029,DM014 & DM041 | Lephalale, Thabazimbi & Modimolle equipment (Compressor and SCBA sets) | 2012-12-14 | Wake up Investments T/A Rural Fire Rescue | 307806.45 | Not yet | Not yet | Not yet | Not yet | None | Disaster | None | None
11 | WDM/2012/13-13 | 03/15168 | WDM Short Term Insurance Cover | 2012-12-12 | Aon South Africa (Pty) Ltd | 371903 | Not yet | Not yet | Not yet | Not yet | None | CSSS | None | None
12 | WDM/2012/13-14 | RS042 | Upgrading of Streets in Marapong - consultant | 2012-12-12 | Fhisol Engineers | 343249.84 | 2013-01-14 | 2013-01-14 | 2014-06-30 | In progress | None | ID | None | None
13 | WDM/2012/13-15 | RS043 | Upgrading of Streets in Regorogile - consultant | 2012-11-28 | GMH Tswelelo Consulting Engineers cc | 158606.58 | 2013-01-14 | 2013-01-14 | 2014-06-30 | In progress | None | ID | None | None
14 | WDM/2012/13-17 | LA012 | Review of spatial development framework | 2012-11-28 | Metplan Pretoria Incorporated | 394736.84 | Not yet | Not yet | Not yet | Not yet | None | PED | None | None
15 | WDM/2012/13-18 | LA007 | Lephalale CBD development plan | 2012-11-28 | Plan Associates Business Trust and Mok Development Consultants JV | 429824.56 | Not yet | Not yet | Not yet | Not yet | None | PED | None | None
16 | WDM/2011/12-31 | SA032 | Mookgophong Township sewer connection - consultant | 2012-12-12 | Kipp Consulting Engineering cc | 1519205.94 | 2013-01-14 | 2013-01-14 | 2014-06-30 | Not yet | None | ID | None | None
17 | WDM/2011/12-32 | IN042 | Supply, Installation & commissioning of standby diesel generators | 2012-12-12 | Diesel Innovations (Pty) Ltd | 456280 | 2013-01-16 | 2013-01-16 | 2013-04-16 | Not yet | None | ID | None | None
18 | WDM/2011/12-33 | RS041 | Tarring of streets in Mahwelereng - contractor | 2012-11-28 | La Fancy Kay | 1197634.9 | Not yet | Not yet | Not yet | Not yet | None | ID | None | None
19 | WDM/2011/12-34 | UE047 | Bela -Bela Flea Market Feasibility Study | 2012-12-12 | Morothwa Trading Enterprise cc | 210000 | Not yet | Not yet | Not yet | Not yet | None | PED | None | None
20 | WDM/2011/12-03- Limited bidding | DM006 | Supply and delivery of Modimolle Fire Fighting Equipments | 2012-12-12 | IBL Fire Fighting Equipment CC | 236554.29 | 2013-01-22 | 2013-01-22 | 2010-04-22 | In progress | None | Disaster | None | None
21 | WDM/2011/12-05- Limited bidding | DM014 | Supply and delivery of Thabazimbi Fire Fighting Equipments | 2012-12-12 | IBL Fire Fighting Equipment CC | 608774.39 | 2013-01-22 | 2013-01-22 | 2012-05-22 | In progress | None | Disaster | None | None
22 | WDM/2011/12-06- Limited bidding | DM029 | Supply and delivery of Lephalale Fire Fighting Equipments | 2012-12-12 | Machauke Multi Service Provider 01 | 75000 | 2013-01-22 | 2013-01-22 | 2013-04-23 | In progress | None | Disaster | None | None
23 | Organ of State | EL008 | Co-funding of the implementation of Electicity supply in Lephalale | 2012-10-17 | Lephalale Local Municipality | 650000 | 2012-09-28 | 2012-09-28 | 2013-06-30 | In progress | None | ID | None | None
24 | Organ of State | EL009 | Co-funding of the implementation of Electicity supply in Bela Bela | 2012-10-11 | Bela- Bela Local Municipality | 850000 | 2012-09-10 | 2012-09-10 | 2013-06-30 | In progress | None | ID | None | None
25 | Limited Bidding | UE043 | Extension - supply & installation of security surveillance cameras for Waterberg | 2012-11-15 | Waterberg Chamber of Commerce | 100000 | 2012-11-28 | 2012-11-28 | 2013-06-30 | In progress | None | PED | None | None
26 | WDM/2011/12-26 | RS021 | Extension of completion of Modimolle ring Road -Phagameng - consultant | 2012-10-26 | Phakama Knight Piesold Consulting | 157870.56 | 2012-11-07 | 2012-11-07 | 2013-02-05 | In progress | None | ID | None | None
27 | Limited Bidding | CO022 | Golf and Life Skill Development for the Waterberg District Municipality | 2012-11-06 | Stainless Steel Design | 193700 | 2012-09-21 | 2012-09-21 | 2012-11-30 | 2012-11-30 | None | EMO | Project completed | None
28 | WDM/2011/12-26 | RS021 | Extension of completion of Modimolle ring Road -Phagameng - contractor | 2012-10-26 | Mafafo Building Construction | 631482.25 | 2012-11-07 | 2012-11-07 | 2013-02-05 | In progress | None | ID | None | None
29 | Limited Bidding | SC013 | Hosting of 2012 annual Mayoral Golf Day at Elements Private Golf Reserve | 2012-12-20 | Elements Private Golf Reserve | 200000 | 2012-12-19 | 2012-12-19 | 2013-03-31 | In progress | None | EMO | None | None
30 | Organ of State | IN035 | Funding of implementation of Lephalale mobile offices | 2012-09-25 | Lephalale Local Municipality | 369911 | 2012-09-26 | 2012-09-26 | 2012-12-26 | Not yet | None |  | None | None
|  |  | Total |  |  | 18914033.67