## 11 12 CONTRACTS
WDM CONTRACT ENTERED INTO DURING THE FINANCIAL YEAR 2011/12 FROM 1 JULY 2011 TO 30 JUNE 2012
No. | Tender Number | IDP Project # | Project Description | Date Awarded | Service provider | Amount Awarded (VAT Excl) | Amount Awarded (VAT Inc) | Date Signed SLA | On -site start Date | Scope | SLA Completion Date | Actual Completion Date | SLA Extension | DEPT | Manager's Comments | Challenges | Date Signed SLA | Duration | SLA End Date
1 | LIMITED BIDDING | DIN27 | IFMS - WDM | 2011-09-07 | Munsoft (Pty) Ltd | 1995062 | 2274370.68 | 2011-09-07 | 2011-11-01 | Integrated Financial Management System for Waterberg District Municipality | 2031-09-07 | 2011-11-30 | None | BTO | Project successfully completed | Customisation | 2011-09-07 | 20 Years | 2031-09-07
2 | LIMITED BIDDING | DIN27 | IFMS - Belabela Local Municipality | 2012-01-26 | Munsoft (Pty) Ltd | 2066911 | 2356278.54 | 2011-11-01 | 2011-11-30 | Integrated Financial Management System for Bela Bela Local Municipality | 2012-06-30 | 2012-02-28 | None | BTO | Project successfully completed | Not all info could be transferred during conversion from SEBATA (info lost)- still not resolved. SP appointed to recover the info. SEBATA paid to reload the info again. Balancing couldn't to date be done. | 2011-11-01 | 8 Months | 2012-06-30
3 | LIMITED BIDDING | DIN27 | IFMS - Thabazimbi Local Municipality | 2012-01-26 | Munsoft (Pty) Ltd | 1945479 | 2217846.06 | 2011-11-01 | 31/01/2012 | Integrated Financial Management System for Thabazimbi Local Municipality | 2012-06-30 | 2012-03-30 | Addendum SLA effective from 1 July 2012. | BTO | Project successfully completed | Customisation of reports but overall, the system is very functional and effective | 2011-11-01 | 8 Months | 2012-06-30
4 | LIMITED BIDDING | DIN27 | IFMS - Modimolle Local Municipality | 2012-06-01 | Munsoft (Pty) Ltd | 272405 | 310541.7 | 2012-05-01 | 20/08/2012 | SCM, MMS & Meter reading modules for Modimolle | 2012-06-30 | 2012-06-30 | None | BTO | Still ongoing | None | 2012-05-01 | 2 Months | 2012-06-30
5 | LIMITED BIDDING | DIN17 | Mayoral vehicle | 2011-07-29 | McCarthy Mercedes Benz fountain Ltd (public co) | 649348 | 740256.72 | 2011-09-11 | 2011-09-01 | Supply of new Mercedes-Benz E350 | 160 000KM | 2011-09-01 | None | CSSS | Project implemented per TOR though the turnaround on the installation of some extras was not that good { sing rings to the Mayoral Vehicle}. | None | 2011-09-11 | 160 000KM | 160 000KM
6 | WDM/2011/12-01 | 0315150 | Provision of Legal Services (3 years contract) | 2011-11-22 | Verveen Attorneys | 900000 | 1026000 | 2011-11-25 | 2011-11-25 | Provision of legal services | 2014-11-25 | 2014-11-25 | None | CSSS | Project implemented per TOR though there has been a delay on the Abattoir debt collection | None | 2011-11-25 | 36 Months | 2014-11-25
7 | WDM/2011/12-02 | 03-15151, etc | Provision of Travelling Agency (3 years contract) | 2011-11-01 | Badiredi Travel | 7500000 | 8550000 | 2011-11-07 | 2011-11-07 | Provision of Travel Agency Services | 2014-11-07 | 2014-11-07 | None | CSSS | Project implemented per TOR though certain things have been done yet as the SLA { Database of preferred and best accommodation within the province} | None | 2011-11-07 | 36 Months | 2014-11-07
8 | S32 WDM 2011/12-01 | IN043 | Procurement and Installation of CCTV Cameras | 2012-01-16 | Siyenza Holdings (PTY) LTD | 436891.2193 | 498055.99 | 2012-02-21 | 2012-02-21 | Provision and Installation of the CCTV Cameras for WDM Head Office | 2012-03-21 | 2012-03-21 | None | CSSS | Project implemented per TOR and the Cameras working good | None | 2012-02-21 | 1 Month | 2012-03-21
9 | WDM/2011/12-29 | DIN017 | Supply and installation of office furniture. | 2012-03-19 | Ungani Interiors | 175169.2982 | 199693 | 2012-03-26 | 2012-03-26 | Supply, delivery and installation of office furniture for the Executive Mayor, Full-time councillors and WDM officials | 2012-05-26 | 2012-05-08 | None | CSSS | Project implemented per TOR though the delivery was delayed. | None | 2012-03-26 | 2 Months | 2012-05-26
10 | WDM/2011/12-19 | DIN021 | Supply and delivery of Disaster Recovery Solution | 2012-03-19 | Business Connexion | 269690.4474 | 307447.11 | 2012-04-12 | 2012-04-12 | Supply and delivery of Disaster Recovery Solution | 2012-06-12 | 2012-06-12 | None | CSSS | All equipment delivered. | None | 2012-04-12 | 8 Weeks | 2012-06-12
11 | S32 WDM 2011/12-02 | IN043 | Supply and Installation of Municipal Chamber's Recording System | 2012-03-23 | MT Sound & Tours CC | 427001.11 | 427001.11 | 2012-04-29 | 2012-04-29 | Supply and Installation of Municipal Chamber's Recording System | 2012-05-29 | 2012-05-29 | None | CSSS | Project implemented per TOR and the System working good | None | 2012-04-29 | 1 Month | 2012-05-29
12 | WDM/2011/12-30 | 015170/015203/ 017870 | Provision of security services | 2012-05-08 | Triotic Protection Services | 1651812.48 | 1883066.2272 | 2012-07-01 | 2012-07-01 | Protection of Municipal Staff assets including money, Cheques, negotiable documents and other valuables. Access control duties of all entrances, including the checking and reporting of the movements of persons entering and leaving the building. Security reporting and monitoring. Incident recording and reporting. Monitoring of CCTV cameras installed in all four (04) WDM Premises | 2015-06-30 | 2015-06-30 | None | CSSS | The Service Provider is less than a month on site, but up to so far, he has managed to meet the WDM’S expectations. | None | 2012-07-01 | 36 Months | 2015-06-30
13 | LIMITED BIDDING | 002 015154 | Provision of institutional study | 2012-05-31 | Endurance Business Consulting | 256842.11 | 292800.0054 | 2012-05-31 | 2012-06-01 | The provision of the Institutional study for Mookgophong local municipality Thabazimbi Local Municipality and Waterberg District Municipality in accordance with the Project process plan. | 2012-06-30 | 2012-06-30 | None | CSSS | Project implemented per TOR and also on time. | None | 2012-05-31 | 1 Month | 2012-06-30
14 | LIMITED BIDDING | 015170/015203/ 017870 | Extension of provision of security Services | 2012-02-23 | Fawcett Security Services | 310834.386 | 354351.2 | 2012-02-23 | 2012-03-01 | Protection of Municipal Staff assets including money, Cheques, negotiable documents and other valuables. Access control duties of all entrances, including the checking and reporting of the movements of persons entering and leaving the building. Security reporting and monitoring. Incident recording and reporting. Monitoring of CCTV cameras installed in all four (04) WDM Premises | 2012-04-23 | 2012-06-30 | None | CSSS | Project implemented per TOR though there were some theft that happened in the presence of Security Company. Again the payment of the Company ‘s was sometimes delayed. | None | 2012-02-23 | 2 Months | 2012-04-23
15 | WDM/2011/12-04 | DM011 | Mogalakwena Fire Fighting Equipment | 2011-11-21 | IBL Fire Fighting Equipment CC | 668065 | 761594.1 | 2012-02-08 | 2012-02-13 | Supply and delivery of Fire Fighting equipments for Mogalakwena | 2012-07-08 | In-progress | None | Disaster | Under quoted with 2 items, which caused a delay. | None | 2012-02-08 | 5 Months | 2012-07-08
16 | WDM/2011/12-07 | DM016 | Refurbishment Toyota Land Cruiser and new mounted Equipment - Mookgopong | 2011-11-22 | Marce Marketing CC | 305127.8246 | 347845.72 | 2012-02-06 | 2012-02-07 | Refurbishment of Toyota land cruiser for Mookgopong | 2012-05-06 | 2012-05-31 | None | Disaster | Discovery of defects that were initially not quoted for. | None | 2012-02-06 | 3 Months | 2012-05-06
17 | WDM/2011/12-08 | DM032 | Refurbishment of Mogalakwena Standby Diesel Generator | 2011-11-22 | Joint Venture Golden Dividend 187 (Pty) Ltd and Sunset Bay Skin and Body Clinic | 95000 | 108300 | 2012-02-03 | 2012-02-06 | Refurbishment of standby generator for Mogalakwena | 2012-05-03 | In-progress | None | Disaster | The standby unit is too old, parts are no longer manufactured in the country except in Germany. | None | 2012-02-03 | 3 Months | 2012-05-03
18 | WDM/2011/12-09 | DM033 | Refurbishment of Toyota Dyna - Mogalakwena | 2011-11-22 | Marce Marketing CC | 82315.9561 | 93840.19 | 2012-02-06 | 2012-02-07 | Refurbishment of Toyota dyna for Mogalakwena | 2012-05-06 | 2012-05-31 | None | Disaster | Discovery of defects that were initially not quoted for | None | 2012-02-06 | 3 Months | 2012-05-06
19 | WDM/2011/12-10 | DM034 | Refurbishment of Unimog Fire Engine - Mogalakwena | 2011-11-22 | Marce Marketing CC | 354090.7895 | 403663.5 | 2012-02-06 | 2012-02-07 | Refurbishment of Unimog for Mogalakwena | 2012-05-06 | 2012-05-06 | None | Disaster | Discovery of defects that were initially not quoted for | None | 2012-02-06 | 3 Months | 2012-05-06
20 | WDM/2011/12-11 | DM017 | 4X4 Double Cab Medium Pumper and Mounted Fire Fighting Equipment - Belabela | 2011-11-22 | Fire Raiders (Pty) Ltd | 1689608.7982 | 1926154.03 | 2012-02-08 | 2012-02-13 | Manufacture and Supply of Fully equipped Medium Pumper for Bela-Bela | 2012-09-08 | In-progress | None | Disaster | The project's time frame is still valid | None | 2012-02-08 | 7 Months | 2012-09-08
21 | WDM/2011/12-13 | DM036 | Water Tanker (10 000 Litres) | 2011-11-22 | Fire and Emergency Vehicle (Pty) Ltd | 1095600 | 1248984 | 2012-02-06 | 2012-02-07 | Manufacture and Supply of 6 000litres Water Tanker for Thabazimbi | 2012-09-06 | In-progress | None | Disaster | The project's time frame is still valid | None | 2012-02-06 | 7 Months | 2012-09-06
22 | WDM/2011/12-14 | DM038 | Modimolle - Medium Double Cab Rapid Intervention Vehicle (RIV) | 2011-12-13 | Fire Raiders (Pty) Ltd | 1136520.1491 | 1295632.97 | 2012-02-08 | 2012-02-13 | Manufacture and supply of Medium Double cab Rapid Intervention Vehicle for Modimolle | 2012-09-08 | In-progress | None | Disaster | The project's time frame is still valid | None | 2012-02-08 | 7 Months | 2012-09-08
23 | WDM/2011/12-15 | DM031 | Lephalale Hazardous Material (Hazmat) Trailer | 2011-11-22 | Marce Marketing CC | 386720 | 440860.8 | 2012-02-06 | 2012-02-07 | Manufacture and supply of Hazmat Trailer for Lephalale | 2012-05-06 | 2012-05-31 | None | Disaster | None | None | 2012-02-06 | 3 Months | 2012-05-06
24 | WDM/2011/12-16 | DM035 | Thabazimbi Hazardous Material (Hazmat) Trailer | 2011-11-22 | Marce Marketing CC | 386720 | 440860.8 | 2012-02-06 | 2012-02-07 | Manufacture and supply of Hazmat Trailer for Thabazimbi | 2012-05-06 | 2012-05-31 | None | Disaster | None | None | 2012-02-06 | 3 Months | 2012-05-06
25 | WDM/2011/12-18 | CO009 | Production of WDM Newsletter | 2011-11-22 | 7th Question Marketing and Communications | 431644 | 431644 | 2012-02-08 | 2012-02-08 | compilation, design, layout and printing of newsletter | 2013-01-08 | 2013-01-08 | None | EMO | Breached of SLA by service provider | End product not in line with specifications | 2012-02-08 | 12 Months | 2013-01-08
26 | LIMITED BIDDING |  | Provision of Athletics Management Services | 2012-05-03 | Limpopo Athletics (LIMA) | 150000 | 150000 | 2012-05-03 | 2012-05-03 | organising of the Mayoral Road race | 2012-06-03 | 2012-06-09 | None | EMO | Excellent work by Service Provider | None | 2012-05-03 | 1 Month | 2012-06-03
27 | WDM/2010/11-10 | RS21 | Consultants fees for the completion of Modimolle Ring Road Phagameng | 2011-10-24 | Phakama Knight Piesold (PTY)LTD | 522392.52 | 595527.4728 | 2011-11-15 | 2012-05-22 | Preliminary and Detailed design Reports, Development of tender documents and Site supervision | 2012-06-30 | 2012-09-30 | None | ID | The project is progressing well | None | 2011-11-15 | 7 Months | 2012-06-30
28 | WDM/2010/11-08 | RS040 | Consultants fees for the completion of paving of Bela-bela Street | 2011-10-24 | Tlou Integrated Tech CC | 356134.72 | 405993.5808 | 2011-11-18 | 2012-05-23 | Preliminary and Detailed design Reports, Development of tender documents and Site supervision | 2012-06-30 | 2012-09-30 | None | ID | The project is progressing well | None | 2011-11-18 | 7 Months | 2012-06-30
29 | WDM/2010/11-09 | RS041 | Professional fees for tarring of street in Mahwelereng | 2012-02-08 | Ntsu Engineering Consultants CC | 321624.9474 | 366652.44 | 2012-02-28 | Contractor not yet appointed | Preliminary and Detailed design Reports, Development of tender documents and Site supervision | 2012-07-28 | N/A | None | ID | Project is at BEC stage | There is a delay in appointing the Contractor | 2012-02-28 | 5 Months | 2012-07-28
30 | WDM/2011/12-26 | RS21 | Completion of Modimolle Ring Road-Phagameng | 2012-05-08 | Mafafo Building Construction CC | 1726309.73 | 1967993.0922 | 2012-05-22 | 2012-05-22 | Earthworks, Pavement layers & Stabilization, Concrete paving blocks and kerbs, Road signs and Road markings | 2012-09-22 | 2012-09-22 | None | ID | The project is progressing well | None | 2012-05-22 | 4 Months | 2012-09-22
31 | WDM/2011/12-25 | RS40 | Completion of Bela-Bela Street Paving- Radium ( Masakhane | 2012-05-08 | Mmamokgoshi Construction | 1596610.4 | 1820135.856 | 2012-05-23 | 2012-05-23 | Earthworks, Pavement layers, Concrete paving blocks and kerbs, Road signs and Road markings | 2012-09-23 | 2012-09-23 | None | ID | The project is progressing well | None | 2012-05-23 | 4 Months | 2012-09-23
32 | LIMITED BIDDING | IN24 | Performance Management System | 2012-02-24 | Institute for Performance Management | 1661208 | 1893777.12 | 2011-05-19 | 2011-11-30 | Reporting & Training & electronic syste, | 2012-06-30 | 2012-06-30 | 2012-09-30 | OMM |  | None | 2011-05-19 | 1 Year | 2012-06-30
33 | WDM/2011/12-28 | DN039 | Audit Information Technology | 2012-05-08 | Sema Integrated Risk Solution | 393145 | 448185.3 | 2012-05-31 | 2012-04-06 | A delivery of a comprehensive Information Audit Technology Report | 2012-08-30 | 2012-04-09 | None | OMM | None | None | 2012-05-31 | 3 Months | 2012-08-30
34 | ORGAN OF STATE | IN035 | Lephalale Recycling Club Project | 2012-04-04 | Lephalale Local Municipality | 420000 | 420000 | 2012-04-13 | 2011-06-30 | Fundiing recyling clubs | 2012-08-13 | In-progress | 2012-11-30 | OMM |  | Delays in implementing project | 2012-04-13 | 4 Months | 2012-08-13
35 | LIMITED BIDDING | DUE40 | Cofounding of Waterberg Meander Reserve 2011/12 | 2011-08-22 | Waterberg Biosphere Reserve | 100000 | 100000 | 2011-10-10 | 2012-07-01 | To manage the Biosphere Reserve and the Waterberg Meander: give support to the community owned tourism products on the Meander, tourism marketing, skills development programmes, environmental and biosphere education & awareness, to enhance the development and management of the reserve to support land use planning & management, communications and community liaison, | 2012-10-09 | 2012-06-30 | None | PED | None | None | 2011-10-10 | 12 Months | 2012-10-09
36 | WDM/2011/12-22 | LA012 | Mookgopong CBD Development Plan | 2011-12-20 | Joint Venture MOK Development Consultants CC and Plan Associates | 415000 | 473100 | 2012-02-16 | 2012-02-16 | Develop a CBD Plan for the Mookgopong Local Municipality | 2012-09-16 | 2012-08-16 | None | PED | None | Poor corparation from Local Municipality | 2012-02-16 | 7 Months | 2012-09-16
37 | WDM/2011/12-23 | LA012 | Thabazimbi CBD Development Plan | 2011-12-20 | Joint Venture MOK Development Consultants CC and Plan Associates | 403508.7719 | 460000 | 2012-02-16 | 2012-02-16 | Develop a CBD Plan for the Thabazimbi Local Municipality | 2012-09-16 | 2012-08-16 | None | PED | None | Poor corparation from Local Municipality | 2012-02-16 | 7 Months | 2012-09-16
38 | WDM/2011/12-24 | SE017 | Development of Landfill Site in Modimolle | 2011-11-22 | Keletshepile Trading Enterprise | 1674555 | 1674555 | 2011-12-07 | 2012-12-07 | Development of landfill site mabatlane(construction of palisade ,guard room toilet and shower ,septic tank ,digging of trenches and burrying of existing waste) | 2012-06-07 | 2012-01-18 | 2012-02-15 | SDCS | Project completed well in advanced | None | 2011-12-07 | 6 Months | 2012-06-07
39 | LIMITED BIDDING | 009 015125 | Office Rental Mokopane - EHPs | 2012-05-02 | Reality Dynamix 46 Pty LTD | 333000 | 333000 | 2012-05-02 | 2012-05-01 |  | 2013-04-30 | 2013-04-30 | None | SDCS | None | None |  | 1 Year
40 | LIMITED BIDDING | 009 015125 | Office Rental Thabazimbi - EHPs | 2012-05-03 | Bertie Joubert Properties CC | 60000 | 60000 | 2012-05-03 | 2012-05-01 |  | 2013-04-30 | 2013-04-30 | None | SDCS | None | None |  | 1 Year
41 | LIMITED BIDDING | DIN041 | Implementation of Virtual Private Network | 2012-06-28 | SITA | 4640666.9474 | 5290360.32 | 2012-06-28 | 2012-07-01 |  | 2015-06-30 | 2015-06-30 | None | CSSS | None | None |  | 3 Year
Note on G8: Laubscher: Based on past payment history, average of R 300,00 per year, as the minimum
Note on G9: nlaubscher: 11/12 Budget * 3 year - to be prudent, no increases added. Included all S&T votes.