## Rollover
Annexure A
Total 10/11 Roll Over IDP projects
2011-07-01
Adjusted Budget 10/11
PROJ NO | PROJECT NAME | PROJ YEAR | Operating | Capital | BUDGET AMOUNT | PAID P/YEARS | UNSPENT AT 30 JUNE 2011 | SPENT 11/12 YEAR | REMAINING | Savings March 2011 | Savings Feb 2011 | Adj Budget | Savings Jan 2011 | Savings Dec 2010 | Total | Operating | Capital | Final savings June 2011 | LAST PMT | RESP MAN | COMMENTS BY MANAGER | Re-budget in 11/12 | Forecast Roll Over 30 June 2011 | Forecast Spending 30 June 2011
1 | Municipal Environmental Health & Environmental Management
SE-05 | Waste Management - development of landfill sites - initiation of partnerships / PPP | 2011 |  |  | 926359 | 390674.72 | 535684.28 | 0 | 535684.28 | [10 empty] | SDCS Health
SE-13 | Air Quality Emissions Inventory | 2011 | 320735 |  | 320735 | 288984.92 | 31750.08 | 0 | 31750.08 | [10 empty] | SDCS
[5 empty] | 1247094 | 679659.64 | 567434.36 | 0 | 567434.36 | [5 empty] | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF!
2 | DISASTER MANAGEMENT
DM-02 | CONSTRUCTION OF LEPHALALE DISASTER MANAGEMENT CENTRE | 2010 |  | 36555 | 2567202 | 2530647 | 36555 | 0 | 36555 | -17059 |  |  |  |  | 36555 |  | 36555 |  | 2010-12-22 | ID | Awaiting for the Records of Decisions | 0 | 0 | 36555
DM-08 | Mogalakwena - new Rescue Pumper | 2011 |  | 3497733 | 3497733 | 3539.71 | 3494193.29 | 0 | 3494193.29 | [10 empty] | MMO
DM-17 | Bela Bela Skid Units & Equipment for main fire station, Masakhane, Pienaarsrivier & Rapotokwane | 2011 |  | 1285759 | 1285759 | 665078.59 | 620680.41 | 0 | 620680.41 | [10 empty] | MMO
DM-22 | Incident Management System | 2011 |  | 307218 | 307218 | 207217.6 | 100000.4 | 0 | 100000.4 | [10 empty] | MMO
DM-23 | Disaster Risk Awareness Program | 2011 | 119780 |  | 119780 | 107279.27 | 12500.73 | 0 | 12500.73 | [10 empty] | MMO
DM-24 | Early Warning System of Flood lines | 2011 |  | 614218 | 614218 | 403649.17 | 210568.83 | 0 | 210568.83 | [10 empty] | MMO
DM-25 | Disaster Risk Management Toll Free Number & promotional signage | 2011 | 500000 |  | 500000 | 2217.6 | 497782.4 | 0 | 497782.4 | [10 empty] | MMO
DM-26 | Information management, communication & dissemination system | 2011 |  | 900000 | 900000 | 355332.26 | 544667.74 | 0 | 544667.74 | [10 empty] | MMO
DM-27 | Risk reduction measures for drought | 2011 | 624987 |  | 624987 | 5757.31 | 619229.69 | 0 | 619229.69 | [10 empty] | MMO
DM-29 | Groblersbrug Port of Entry / Tom Burke Satellite Fire Station - Water Trailer & Equipm & Steenbokpan & Bulgerivier Satellite Fire Station - Water Trailer & Equipment & Villages / Witpoort Fire Station - Equipment | 2011 |  | 242600 | 242600 | 62679.72 | 179920.28 | 0 | 179920.28 | [10 empty] | MMO
[5 empty] | 10659497 | 4343398.23 | 6316098.77 | 0 | 6316098.77 | [5 empty] | 36555 | 0 | 36555 |  |  |  |  | 0 | 0 | 36555
3 | Fire Fighting
IN-22 | Upgrading of existing trained volunteers to minimum requirements for full time fire fighters (phase 2) | 2011 | 100000 |  | 100000 | 0 | 100000 | 0 | 100000 | [10 empty] | CSSS
[5 empty] | 100000 | 0 | 100000 | 0 | 100000
4 | ECONOMIC DEVELOPMENT
UE-34 | Feasibility Study of the Wildlife Centre | 2008 | 399255.63 |  | 3000000 | 2600744.37 | 399255.63 | 0 | 399255.63 | [5 empty] | 399255.63 | 399255.63 |  |  |  | PED | Cordination of the project in collaboration with Modimolle is going on | 0 | 399255.63 | 0
UE-42 | Signage | 2009 & 2010 | 79867.08 |  | 803350 | 723482.92 | 79867.08 | 0 | 79867.08 | [5 empty] | 79867.08 | 79867.08 |  |  | 2011-03-09 | PED | The project has been completed. The outstanding funds will be utilized for the billboards | 0 | 0 | 79867.08
UE-43 | Modimolle & Bela Bela Security Cameras | 2010 | 520000 |  | 800000 | 280000 | 520000 | 0 | 520000 | [5 empty] | 520000 | 520000 |  |  | 2011-03-25 | PED | work is going on. Should be able to secure the new equipment the the next two weeks. Tender for Bela-Bela is closing on Friday the 25 of March | 0 | 0 | 520000
[5 empty] | 4603350 | 3604227.29 | 999122.71 | 0 | 999122.71 | [5 empty] | 999122.71 | 999122.71 | 0 |  |  |  |  | 0 | 399255.63 | 599867.08
5 | ROADS & STORM WATER
RS-21 | Completion of Modimolle Ring Road in Phagameng - 1,603km | 2010 & 2011 | 2395734.35 |  | 2690081 | 294346.65 | 2395734.35 | 0 | 2395734.35 |  |  | 377956 |  |  | 2773690.35 | 2773690.35 |  | 247795 | 2011-03-23 | ID | Consultant Final designs completed in Feb 2011. Construction advertised in March 2011. | 0 | 1100000 | 1295734.35
RS-40 | Bela Bela Paving - Radium - 1.3km | 2011 | 2740093 |  | 2740093 | 920455.9 | 1819637.1 | 0 | 1819637.1 | [10 empty] | ID
RS041 | Mogalakwena Streets tarring | 2010 & 2011 |  |  | 3147912 | 448277.62 | 2699634.38 | 0 | 2699634.38 | [10 empty] | ID
[5 empty] | 8578086 | 1663080.17 | 6915005.83 | 0 | 6915005.83 | [5 empty] | 2773690.35 | 2773690.35 | 0 |  |  |  |  | 0 | 1100000 | 1295734.35
6 | INSTITUTIONAL DEVELOPMENT
IN-17 | Procurement of Movable Assets | 2011 |  | 574090 | 574090 | 545819.53 | 28270.47 | 0 | 28270.47 | [10 empty] | CSSS
IN-24 | Performance Management System (PMS) | 2011 | 938385 |  | 938385 | 861679.7 | 76705.3 | 0 | 76705.3 | [10 empty] | MMO
IN-27 | Integrated Financial Management System | 2010 & 2011 |  | 6273639.4 | 6286945 | 13305.6 | 6273639.4 | 0 | 6273639.4 | [5 empty] | 6273639.4 |  | 6273639.4 |  | 2010-08-04 | CSSS | The tender closed on 23 August 2010. Due to errors by SITA on the tender document the project was officially cancelled by SITA in December 2010. WDM to restart the process on its own, no longer utilising the assistance of SITA. Awaiting formal letter from SITA. | 0 | 186694.4 | 6086945
IN-34 | Geographic Information System (GIS) | 2011 |  | 649806 | 649806 | 589266.1 | 60539.9 | 0 | 60539.9 | [10 empty] | CSSS
IN-36 | Financial Strategy | 2011 | 500000 |  | 500000 | 0 | 500000 | 0 | 500000 | [10 empty] | BTO
[5 empty] | 8949226 | 2010070.93 | 6939155.07 | 0 | 6939155.07 | [5 empty] | 6273639.4 | 0 | 6273639.4 |  |  |  |  | 0 | 186694.4 | 6086945
7 | ABATTOIR
UE-29 | Upgrading of the abattoir (phase 2) | 2011 |  | 2931934 | 2931934 | 1685161.19 | 1246772.81 | 0 | 1246772.81 | [10 empty] | ID
[5 empty] | 2931934 | 1685161.19 | 1246772.81 | 0 | 1246772.81
8 | COMMUNITY PARTICIPATION AND COMMUNICATION
CO-20 | Anti-fraud Hotline | 2010 & 2011 | 186507.73 |  | 300000 | 113492.27 | 186507.73 | 0 | 186507.73 |  |  | 0 |  |  | 186507.73 | 186507.73 |  |  | 2011-01-21 | MMO | The project is running, The monthly retainer invoices for December and january have been received and are under processing. | 0 | 0 | 186507.73
CO-24 | Service Delivery Summit | 08&09 | 351340 |  | 351340 | 0 | 351340 | 0 | 351340 |  |  | 0 |  |  | 351340 | 351340 |  |  |  | EMO | Preparations of the summit underway - earmarked for end April 2011 | 0 | 0 | 351340
[5 empty] | 651340 | 113492.27 | 537847.73 | 0 | 537847.73 | [5 empty] | 537847.73 | 537847.73 | 0 |  |  |  |  | 0 | 0 | 537847.73
9 | LAND
LA-12 | CBD Development Plan & Implementation (Bela Bela, Modimolle & Mogalakwena) | 2011 | 1339649 |  | 1339649 | 1233113.42 | 106535.58 | 0 | 106535.58 | [10 empty] | PED
[5 empty] | 1339649 | 1233113.42 | 106535.58 | 0 | 106535.58 | [5 empty] | #REF! | #REF! | #REF!
12 | SPORTS,ARTS AND CULTURE
SC-07 | Co-ordination of Sports, Arts and Culture | 2010 | 238716.35 |  | 1244551 | 1005834.65 | 238716.35 | 0 | 238716.35 |  |  | 456834 |  |  | 695550.35 | 695550.35 |  | 12283 | 2011-03-30 | EMO | OR Tambo Games scheduled for the last week of May 2011. Adj budget R 456,834 to be used for Endurance Challenge in April 2011. | 0 | 0 | 238716.35
[5 empty] | 1244551 | 1005834.65 | 238716.35 | 0 | 238716.35 | [5 empty] | 695550.35 | 695550.35 | 0 |  |  |  |  | 0 | 0 | 238716.35
|  |  | 11355050.14 | 17313552.4 | 40304727 | 16338037.79 | 23966689.21 | 0 | 23966689.21 | -17059 | 0 | 834790 | 0 | 0 | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF!
|  |  | 28668602.54 | [19 empty] | #REF! | #REF!
| TOTAL ROLLOVER |  |  |  | 23966689.21
| TOTAL SPENT UP TO 30 June 2011 |  |  |  | 0 | [18 empty] | #REF!
| ACTUAL % SPENT |  |  |  | 0% | [6 empty] | #REF! | [10 empty] | Savings | #REF!
#REF!
24364448.34
397759.13
299020
98739.13

## Current
PROJECT STATUS REPORT - 11/12 YEAR PROJECTS
2011-07-01
PROJ NO | PROJECT NAME | PROJ YEAR | Operating | Capital | BUDGET AMOUNT | PAID 10/11 YEAR | REMAINING | Savings Mar 2011 | Savings Feb 2011 | Adj Budget | Savings Jan 2011 | Savings Dec 2010 | Final savings June 2011 | LAST PMT | RESP MAN | COMMENTS BY MANAGER | Re-budget in 11/12 | Forecast Roll Over 30 June 2011 | Forecast Spending 30 June 2011
1 | Municipal Environmental Health & Environmental Management
[6 empty] | 0 |  |  |  | 0 |  |  | 73641 | 2011-03-04 | SDCS | BEC meeting held on the 25th of March 2011,the appointment would be done probably by month end(March 2011).it is a three months project | 0 | 0 | 0
[6 empty] | 0 |  | -151114 |  | 0 |  |  |  | 2011-03-31 | SDCS | consolidation of gaps identified during visits to local municipalities and a workshop is to be held on the 30/03/2011 | 0 | 0 | 0
[6 empty] | 0 |  |  |  | 0 |  |  | -1000 |  | SDCS | CSSS department is processing the enrolment of the identified three EHP's which should be concluded by 31/03/2011 | 0 | 0 | 0
[6 empty] | 0 |  |  | -4000 | 0 |  |  |  | 2010-10-14 | SDCS | Project complete | 0 | 0 | 0
[6 empty] | 0 |  | -179265 |  | 0 |  |  |  | 2011-03-31 | SDCS | service provider appointed and inception meeting held last month and a workshop to be held on the 30/03/2011 | 0 | 0 | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 4977 | 2011-03-31 | SDCS | the programme started and ensaged to be through by end of April 2011 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0
2 | Disaster Management
[6 empty] | 0 | [8 empty] | MMO | These fire equipment not yet delivered by the appointed Service Provider, Moipone Group of Companies. The time frame for their delivery have elapsed and the Project Manager is conducting consecutive follow-ups on a weekly basis. | 0 | 0 | 0
[6 empty] | 0 |  | 0 |  |  | -145000 | -9630 | 447637 | 2010-12-13 | MMO | The Unit is ordered by Marce Fire Fighting Technology at E-One in the USA and the work will commence as soon as the Chassis is received by E-One. The work is on schedule as per the 10 months appointment duration. | 0 | 1970915 | -1970915
[6 empty] | 0 | [8 empty] | MMO | Project cancelled, transferred to Purchase of Unimog - Modimolle. | 0 | 0 | 0
[6 empty] | 0 |  | 0 |  |  |  |  | 48894 | 2011-02-24 | MMO | The 1st site inspection meeting held on Thursday, 17th February 2011 in Boksburg where the TATA chassis was inspected and as a result the 50% payment was recommended by the Project Manager. The work is on schedule as per the 10 months appointment duration. | 0 | 398230 | -398230
[6 empty] | 0 | [6 empty] | 88665 |  | MMO | It's a 2 months project awarded to Moipone Group of Companies ( Pty) Ltd in order to run from 02 December 2010 to 02 February 2011. No updated comment. | 0 | 0 | 0
[6 empty] | 0 | [5 empty] | 9630 | -244929 |  | MMO | The Bid was re-advertised due to Moipone Group of Companies have withdrawn the tender. Limited bidding was approved by the Municipal Manager and the SCMU will do the necessary arrangements for calling the selected Service Providers for the compulsory briefing session. | 0 | 0 | 0
[6 empty] | 0 | [6 empty] | 72782 | 2010-12-03 | MMO | Appointment letter issued on 14 March at hand over meeting. | 0 | 0 | 0
[6 empty] | 0 |  | 76000 |  |  |  |  | 31220 |  | MMO | Appointment letter issued on 14 March at hand over meeting. | 0 | 0 | 0
[6 empty] | 0 |  | -145782 | [5 empty] | 2010-12-03 | MMO | Appointment letter issued on 14 March at hand over meeting. | 0 | 0 | 0
[6 empty] | 0 | [7 empty] | 2010-12-03 | MMO | Limited bidding was approved by the Municipal Manager and the SCMU will do the necessary arrangements for calling the selected Service Providers for the compulsory briefing session. | 0 | 0 | 0
[6 empty] | 0 | [6 empty] | 100000 | 2010-12-03 | MMO | Appointment letter issued on 14 March at hand over meeting. | 0 | 0 | 0
[6 empty] | 0 | [6 empty] | -184987 | 2010-12-13 | MMO | Limited bidding was approved by the Municipal Manager and the SCMU will do the necessary arrangements for calling the selected Service Providers for the compulsory briefing session. | 0 | 0 | 0
[6 empty] | 0 | [6 empty] | 225353 | 2011-03-04 | MMO | These equipment for Lephalale were delivered in good order by the appointed Service Provider, Marce Fire Fighting Technology on Tuesday, 01 March 2011. This project is officially closed. | 0 | 0 | 0
[6 empty] | 0 | [7 empty] | 2011-02-22 | MMO | These quipment for Lephalale were delivered in good order by the appointed Service Provider, Marce Fire Fighting Technology on Tuesday, 01 February 2011. This project is officially closed. | 0 | 0 | 0
[6 empty] | 0 |  |  |  |  | 145000 |  |  |  | MMO | All parts to upgrade the Unit is in stock (Marce Fire Fighting Technology) and the work will commence very soon. The 3 months delivery time frame is on schedule. | 0 | 572500 | -572500
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 2941645 | -2941645
3 | Fire Fighting
[6 empty] | 0 | [8 empty] | CSSS | The received quotes are far above the budget. Still sourcing quotations that will be within the budget | 0 | 100000 | -100000
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 100000 | -100000
4 | Local Economic Development & Tourism
[6 empty] | 0 | [7 empty] | 2011-01-25 | PED | Project complete | 0 | 0 | 0
[6 empty] | 0 |  |  |  | 50000 |  |  | -32471 | 2011-03-23 | PED | Preparations for Indaba are underway | 0 | 0 | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 20000 |  | PED | Work has been completed, awaiting the final invoice | 0 | 200000 | -200000
[6 empty] | 0 |  |  | -1200000 | 0 |  |  |  |  | PED | PED to report on behalf of WEDA board. Bank account has not yet been opened for WEDA, thus no access to new R 1.5 million in 10/11 IDP. | 0 | 0 | 0
[6 empty] | 0 | [6 empty] | 12471 |  | PED | Working on billboard assignment. |  | 0 | 0
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 200000 | -200000
5 | Municipal Roads & Storm Water
[6 empty] | 0 |  |  |  | 311022 |  |  | 51102 |  | ID | Consultant Final designs completed in Feb 2011. Construction advertised in March 2011. | 0 | 200000 | -200000
[6 empty] | 0 |  |  |  | 688978 |  |  | 323885 | 2011-03-23 | ID | Consultant Final designs completed in Feb 2011. Construction advertised in March 2011. | 0 | 1200000 | -1200000
[6 empty] | 0 | [6 empty] | -600117 | 2011-03-23 | ID | Consultant Final designs completed in Feb 2011. Construction advertised in March 2011. | 0 | 1200000 | -1200000
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 2600000 | -2600000
6 | Municipal Support & Institutional Development
[6 empty] | 0 |  |  | 100000 | 0 |  |  | 25910 | 2011-03-22 | CSSS | Procured only Airconditioners and the Furniture for Lephalale Disaster Centre. Departments have submitted their request for furniture and TOR for these furnitures not yet completed. No updated comment. | 0 | 0 | 0
[6 empty] | 0 | [6 empty] | 61615 |  | MMO | Irregular expenditure of 30 June 2010 has been ratified. Item for extension of service of IPM approved by MM. No updated comment. | 0 | 0 | 0
[6 empty] | 0 | [8 empty] | CSSS | The tender closed on 23 August 2010. Due to errors by SITA on the tender document the project was officially cancelled by SITA in December 2010. WDM to restart the process on its own, no longer utilising the assistance of SITA. Awaiting formal letter from SITA. | 0 | 6086945 | -6086945
[6 empty] | 0 |  |  | 80000 | 0 |  |  | 3236 |  | CSSS | Awating for BEC Committee to Sit. | 0 | 0 | 0
[6 empty] | 0 |  | -350194 |  | 0 |  |  |  | 2011-03-28 | CSSS | Second phase has been completed and submitted to WDM. | 0 | 300000 | -300000
[6 empty] | 0 | [6 empty] | 25918 |  | MMO | Approved a Skills Development Strategy project of Lephalale to the amount of R 400,000. Currently considering 'n movable asset procurement request to the amount of R 600,000. No updated comment. | 0 | 0 | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  |  | BTO | Feedback was obtained from various stakeholders and industry experts on what is required from a Finance Strategy. Currently preparing specifications. To be done concurrent with 12/13 IDP process | 0 | 250000 | -250000
[6 empty] | 0 |  |  | -300000 |  |  |  | 200000 |  | CSSS | The Draft By-Laws has been submiited to DPLG for promulgation. DPLG still working on them and the Invoice will be sent to us oncne the By-laws has been promulgated. To obtain written quotation from DPLG for approximate R 120,000 and issue order. | 0 | 0 | 0
[6 empty] | 0 |  | -753694 | -180000 | 0 |  |  | 14676 | 2011-03-31 | CSSS | Third Phase has been completed and Submitted to WDM | 0 | 300000 | -300000
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 6936945 | -6936945
7 | ABATTOIR
[6 empty] | 0 |  | -2114 | [5 empty] | 2011-03-22 | ID | Contractor appointed in December 2010 for Phase 2. Construction ongoing. | 0 | 350000 | -350000
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 350000 | -350000
8 | COMMUNITY PARTICIPATION & GOOD GOVERNANCE
[6 empty] | 0 | [6 empty] | 311196 | 2011-02-09 | EMO | Development of the Communications & Community participation Startegy, advert to be placed on Notice Board by end March | 0 | 280000 | -280000
[6 empty] | 0 | [6 empty] | 201149 | 2011-03-09 | EMO | Farm workers campaign to be conducted on the 10th and 17th April 2011 | 0 | 0 | 0
[6 empty] | 0 | [7 empty] | 2011-03-16 | MMO | IDP Rep Forum held in March 2011 | 0 | 0 | 0
[6 empty] | 0 |  | -3600 | [5 empty] | 2011-03-14 | EMO | Diaries to be delivered on the 8 March 2011 - Completed | 0 | 0 | 0
[6 empty] | 0 |  |  | -100000 |  |  |  | -39246 | 2010-09-20 | EMO | Visit to Kgatleng District - 6-8 April 2011 | 0 | 0 | 0
[6 empty] | 0 |  | -79834 | 0 |  | 0 |  |  | 2011-03-23 | EMO | Elderly Event scheduled for the 16 March 2011 - remainder of the budget to be declared a saving | 0 | 0 | 0
[6 empty] | 0 |  |  | -100000 |  |  |  | 30000 |  | EMO | Still awaiting date of the District AIDS Council launch | 0 | 0 | 0
[6 empty] | 0 | [6 empty] | 15533 | 2011-01-25 | EMO | Capacity building workshop for the leadership of sport federations for people with disabilities scheduled for 13th May 2011 | 0 | 0 | 0
[6 empty] | 0 | [6 empty] | 166161 | 2010-11-10 | EMO | Youth Summit by end April - preparations ongoing | 0 | 0 | 0
[6 empty] | 0 |  |  |  | 0 |  |  |  |  | MMO | The project is running, The monthly retainer invoices for December and january have been received and are under processing. | 0 | 130000 | -130000
[6 empty] | 0 | [7 empty] | 2010-11-09 | EMO | Project completed. | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 410000 | -410000
9 | Land
[6 empty] | 0 |  |  | -1000000 |  | 0 |  |  |  | CSSS | DPLH has project on Land Audit for the entire Limpopo which will also cover Waterberg. Again the TOR of this have also been covered by the Conveyancing Project. Project removed. | 0 | 1000000 | -1000000
[6 empty] | 0 |  | -110351 |  | -50000 |  |  |  | 2011-03-31 | PED | The status quo and the analysis for all the three projects has been completed. Should be able to complete by May the end. | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 1000000 | -1000000
10 | Transport
[6 empty] | 0 |  | -19298 | [6 empty] | PED | Presentation of the analysis and the status quo has been presented | 0 | 150000 | -150000
[6 empty] | 0 | [6 empty] | 68745 | 2010-12-23 | PED | Arrive alive campaign has been planned for Easter Holiday period | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 150000 | -150000
11 | Safety & Security
[6 empty] | 0 | [6 empty] | 5990 |  | EMO | Orientation workshop for new members of Safety & Security Forum by end May 2011 | 0 | 0 | 0
[6 empty] | 0 | [6 empty] | 400000 |  | PED | work is going on. Should be able to secure the new equipment the the next two weeks. Tender for Bela-Bela is closing on Friday the 25 of March | 0 | 400000 | -400000
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 400000 | -400000
12 | Sports, Arts & Culture
[6 empty] | 0 | [8 empty] | EMO | Renamed OR Tambo Games as per proposal to council - scheduled for end May 2011 | 0 | 0 | 0
[6 empty] | 0 |  | -8568 | [5 empty] | 2011-01-20 | EMO | Project Completed | 0 | 0 | 0
[6 empty] | 0 |  | 0 |  |  |  |  | 21075 | 2011-01-20 | EMO | Project Completed | 0 | 0 | 0
[6 empty] | 0 | [6 empty] | 31183 |  | EMO | Moral Regeneration Conference - end April 2011 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0
13 | Electricity
[6 empty] | 0 | [7 empty] | 2011-01-31 | ID | Project completed. | 0 | 0 | 0
[6 empty] | 0 |  |  |  | -1000000 |  |  |  |  | ID | Funds removed during Adj Budget. Project included in 11/12 tabled IDP to assist Mogalakwena. | 0 | 1000000 | -1000000
[5 empty] | 0 | 0 | 0 | [9 empty] | 0 | 1000000 | -1000000
|  |  | 0 | 0 | 0 | 0 | 0 | 1727814 | 2704000 | 0 | 0 | 0 |  | #DIV/0! |  |  | 0 | 16088590 | -16088590
0
| TOTAL APPROVED BUDGET |  |  |  | 0 |  |  | #REF! | [9 empty] | #DIV/0! | #DIV/0!
| TOTAL SPENT UP TO 30 June 2011 |  |  |  | 0 |  |  | 0
| ACTUAL % SPENT |  |  |  | #DIV/0! |  |  | #REF! | [10 empty] | 0
0

## SDBIP
CAPITAL EXPENDITURE AGAINST SDBIP TARGETS |  | 2011-06-01 |  |  | Resp Mng | Due to: | Savings
|  | Proj IDP | Act Capex | % SPENT
Vote Nr |  | R | R | R
Expenditure and Revenue by Vote
001 | Budget & Treasury Office | 500000 | 0 | 0% | CFO
002 | Office of the Municipal Manager | 1665000 | 0 | 0% | MM
003 | Corporate Support & Shared Services | 1989806 | 0 | 0% | CSSS |  | 1300000
004 | Planning and Economic Development | 2737851 | 0 | 0% | MPED |  | 1200000
005 | Infrastructure Development | 4526000 | 0 | 0% | MID
006 | Office of the Executive Mayor | 2345998 | 0 | 0% | MEMO |  | 200000
007 | Social Development & Community Services | 763121 | 0 | 0% | MSDCS |  | 4000
008 | Disaster | 4014048 | 0 | 0% | MM
009 | Health | 300000 | 0 | 0% | MSDCS
020 | Abattoir | 2787345.6 | 0 | 0% | MID
| Total By Vote (Balanced to Cash Flow) | 21629169.6 | 0 | 0% |  |  | 2704000
CAPITAL EXPENDITURE AGAINST SDBIP TARGETS |  | 2011-06-01 |  |  | Resp Mng | Due to: | Savings
|  | Proj Roll Over | Act Roll Over | % SPENT
Vote Nr |  | R | R | R
Expenditure and Revenue by Vote
001 | Budget & Treasury Office | 0 | 0 | - | CFO
002 | Office of the Municipal Manager | 469742 | #REF! | #REF! | MM | Savings
003 | Corporate Support & Shared Services | 1160955 | #REF! | #REF! | CSSS | Conveyancing | 509297
004 | Planning and Economic Development | 4311414 | #REF! | #REF! | MPED | Wildlife Centre, Skills Strategy (new), Biosphere Strategy (new) | 474376
005 | Infrastructure Development | 1002527 | #REF! | #REF! | MID | Savings | 17059
006 | Office of the Executive Mayor | 1379151 | #REF! | #REF! | MEMO | Communication & Summits | 6400
007 | Social Development & Community Services | 0 | 0 | - | MSDCS
008 | Disaster | 1304268 | #REF! | #REF! | MM |  | 36264
009 | Health | 117770 | #REF! | #REF! | MSDCS |  | 18530
020 | Abattoir | 124121 | #REF! | #REF! | MID
| Total By Vote (Balanced to Cash Flow) | 9869948 | #REF! | #REF! |  |  | 1061926
#REF!
Total Spent per Department
| Budget & Treasury Office |  | 0
| Office of the Municipal Manager |  | #REF!
| Corporate Support & Shared Services |  | #REF!
| Planning and Economic Development |  | #REF!
| Infrastructure Development |  | #REF!
| Office of the Executive Mayor |  | #REF!
| Social Development & Community Services |  | 0
| Disaster |  | #REF!
| Health |  | #REF!
| Abattoir |  | #REF!
#REF!
| Dpt 5 |  | #REF!
| Dpt 7 |  | #REF!