## SA37
Annexure B
DC36 Waterberg - Supporting Table SA37 Projects delayed from previous financial year/s
Municipal Vote/Capital project | Project name | Project number | Asset Class 3. | Asset Sub-Class 3. | Previous target year to complete | Current Year 2010/2011 |  | 2010/11 Medium Term Revenue & Expenditure Framework
|  | Audited Actual |  |  |  | Original Budget | Full Year Forecast | Budget Year 2011/12 | Budget Year +2 2012/13 | Budget Year +3 2013/14
R thousand |  | R'000 |  |  | Year
Parent municipality:
List all capital projects grouped by Municipal Vote |  |  | Examples | Examples
Health & Environment | Development of landfill sites | SE05 | None | None | 2011 | 926359 | 390675 | 535684 | 0 | 0
| Air Quality Emissions Inventory | SE13 | None | None | 2011 | 320735 | 288985 | 31750 | 0 | 0
Disaster Management | EIA of Lephalale Disaster Centre | DM02 | None | None | 2010 | 2567202 | 2530647 | 36555 | 0 | 0
| Mogalakwena Rescue Pumper | DM08 | Other Assets | Specialized Vehicles | 2011 | 3497733 | 3540 | 3494193 | 0 | 0
| Bela Bela Skid Units & Equipment | DM17 | Other Assets | Machinery & Equipment | 2011 | 1285759 | 665079 | 620680 | 0 | 0
| Incident Management System | DM22 | None | None | 2011 | 307218 | 207218 | 100000 | 0 | 0
| Disaster Risk Awareness Program | DM23 | None | None | 2011 | 119780 | 107279 | 12501 | 0 | 0
| Early Warning System of Flood Lines | DM24 | None | None | 2011 | 614218 | 403649 | 210569 | 0 | 0
| Disaster Risk Management Toll Free Number | DM25 | None | None | 2011 | 500000 | 2218 | 497782 | 0 | 0
| Information management, communication | DM26 | Intangible Assets | Computer Software | 2011 | 900000 | 355332 | 544668 | 0 | 0
| Risk Reduction measure for drought | DM27 | None | None | 2011 | 624987 | 5757 | 619230 | 0 | 0
| Groblersburg Fire Station - water tank | DM29 | Other Assets | Machinery & Equipment | 2011 | 242600 | 62680 | 179920 | 0 | 0
Fire Fighting | Training of existing volunteers to fire fighters | IN22 | None | None | 2011 | 100000 | 0 | 100000 | 0 | 0
Economic Development | Feasibility Study of the Wildlife Centre | UE34 | None | None | 2008 | 3000000 | 2600744 | 399256 | 0 | 0
| Signage | UE42 | None | None | 2010 | 803350 | 723483 | 79867 | 0 | 0
| Modimolle & Bela Bela Surveillance Cameras | UE43 | None | None | 2010 | 800000 | 280000 | 520000 | 0 | 0
Roads & Storm Water | Completion of Modimolle Ring Road - 1.6km | RS21 | None | None | 2011 | 2690081 | 294347 | 2395734 | 0 | 0
| Bela Bela Paving Radium - 1.3km | RS40 | None | None | 2011 | 2740093 | 920456 | 1819637 | 0 | 0
| Mogalakwena Street tarring | RS41 | None | None | 2011 | 3147912 | 448278 | 2699634 | 0 | 0
Institutional Development | Procurement of movable assets | IN17 | Other Assets | Computer equipment | 2011 | 574090 | 545820 | 28270 | 0 | 0
| Performance Management System | IN24 | None | None | 2011 | 938385 | 861680 | 76705 | 0 | 0
| Integrated Financial Management System | IN27 | Intangible Assets | Computers - software & programming | 2011 | 6286945 | 13306 | 6273639 | 0 | 0
| Geographic Information System (GIS) | IN34 | Intangible Assets | Computers - software & programming | 2011 | 649806 | 589266 | 60540 | 0 | 0
| Financial Strategy | IN36 | None | None | 2011 | 500000 | 0 | 500000 | 0 | 0
Abattoir | Upgrading of the abattoir | UE29 | Other Assets | Other Buildings | 2011 | 2931934 | 1685161 | 1246773 | 0 | 0
Community Participation & Communication | Anti-fraud hotline | CO20 | None | None | 2011 | 300000 | 113492 | 186508 | 0 | 0
| Service Delivery Summit | CO24 | None | None | 2011 | 351340 | 0 | 351340 | 0 | 0
Land | CBD Development Plans for Bela Bela, Modimolle & Mogalakwena (o/s Modimolle) | LA12 | None | None | 2011 | 1339649 | 1233113 | 106536 | 0 | 0
Sports, Arts & Culture | Co-ordination of Sports, Arts & Culture | SC07 | None | None | 2011 | 1244551 | 1005835 | 238716 | 0 | 0
Entities:
List all capital projects grouped by Municipal Entity
Waterberg Economic Development Agency
No projects
References
1. List all projects with planned completion dates in current year that have been re-budgeted in the MTREF
2. Refer MFMA s30
3. Asset category and sub-category must be selected from Table A34