## Capital Works Plan
ANNEXURE H
CAPITAL WORKS PLAN 2008 - 2011
VOTE NUMBER | DEPARTMENT / VOTE | CAPTIAL ITEMS | DELIVERABLES | PLANNED START DATE | PLANNED COMPLETION DATE | 2008/07/08 Projected | 2008/07/08 Actual | 2008/08/08 Projected | 2008/08/08 Actual | 2008/09/08 Projected | 2008/09/08 Actual | 2008/10/08 Projected | 2008/10/08 Actual | 2008/11/08 Projected | 2008/11/08 Actual | 2008/12/08 Projected | 2008/12/08 Actual | 2009/01/08 Projected | 2009/01/08 Actual | 2009/02/08 Projected | 2009/02/08 Actual | 2009/03/08 Projected | 2009/03/08 Actual | 2009/04/08 Projected | 2009/04/08 Actual | 2009/05/08 Projected | 2009/05/08 Actual | 2009/06/08 Projected | 2009/06/08 Actual | CAPITAL BUDGET 2008/2009 | CAPITAL BUDGET 2009/2010 | CAPITAL BUDGET 2010/2011
2008/09 IDP
002/010 | Office of the Municipal Manager | Performance Management Sysstem | Functional automated District Wide Performance management system | 01 Aug-08 | 31 June 08 | 0 |  | 20000 |  | 20000 |  | 20000 |  | 20000 |  | 1110000 |  | 1110000 |  | 1110000 |  | 1110000 |  | 1110000 |  | 1110000 |  | 3696491 |  | 3696491 | 1000000 | 0
[6 empty] | 0 | 0 | 20000 | 0 | 20000 | 0 | 20000 | 0 | 20000 | 0 | 1110000 | 0 | 1110000 | 0 | 1110000 | 0 | 1110000 | 0 | 1110000 | 0 | 1110000 | 0 | 3696491 | 0 | 3696491 | 1000000 | 0
003/005 | Corporate Support & Shared Services | Conveyancing | To transfer fixed assets from WDM to LM, |  | 2008-06-09 | 0 | 0 | 0 | 0 | 0 | [17 empty] | 400000 |  | 400000 | 0 | 0
001/010 | Budget & Treasury Office | Procurement of Integrated Financial Management System | Integrated Financial Management System | 2008-07-01 | 2009-06-01 | 0 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 2500000 |  | 2500000 |  | 2500000 | 0 | 0
003/010 | Corporate Support & Shared Services | Partioning of existing offices | To provide additional office accomodation |  | 2008-06-09 | 0 | 0 | 0 | 0 | 40000 |  | 40000 |  | 40000 |  | 40000 |  | 40000 |  | 40000 |  | 40000 |  | 40000 |  | 400000 |  | 400000 |  | 400000 | 0 | 0
003/010 | Corporate Support & Shared Services | Upgrading of surveillance cameras | To provide a safe and secure enviroment for staff ,priotect council, assets |  | 2008-12-09 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 50000 |  | 50000 |  | 50000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 | 0 | 0
003/010 | Corporate Support & Shared Services | Section 78 Municipal Health | To comply with sec 78 MSA investigate internal & external mechanisims |  | 2008-03-09 | 0 | 0 | 0 | 0 | 20000 |  | 20000 |  | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 400000 |  | 400000 |  | 400000 | 0 | 0
[6 empty] | 0 | 0 | 10000 | 0 | 70000 | 0 | 70000 | 0 | 250000 | 0 | 300000 | 0 | 300000 | 0 | 300000 | 0 | 350000 | 0 | 350000 | 0 | 3400000 | 0 | 3800000 | 0 | 3800000 | 0 | 0
004/003 | Planning and Economic Development | Coordination of District wide LED | Facilitation of establishment of local LED Units | 2008-07-08 | 2008-07-09 | 0 |  | 0 |  | 50000 |  | 50000 |  | 180000 |  | 180000 |  | 180000 |  | 300000 |  | 300000 |  | 300000 |  | 480000 |  | 480000 |  | 480000 | 0 | 0
004/003 | Planning and Economic Development | Tourism Development | Promotion of Waterberg' unique selling points | 2008-08-08 | 2008-06-09 | 0 |  | 0 |  | 300000 |  | 300000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 800000 |  | 800000 |  | 1250000 |  | 1250000 |  | 1250000 | 1000000 | 1000000
004/003 | Planning and Economic Development | Honey Bee Project | Well developed honey production in Modimolle | 2008-08-08 | 2008-06-09 | 0 |  | 0 |  | 100000 |  | 100000 |  | 250000 |  | 250000 |  | 250000 |  | 350000 |  | 350000 |  | 350000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0
004/003 | Planning and Economic Development | Waterberg Biosphere Meander Route | Well developed community owned product | 2008-07-08 | June 09 | 0 |  | 0 |  | 300000 |  | 300000 |  | 500000 |  | 500000 |  | 500000 |  | 700000 |  | 700000 |  | 700000 |  | 900000 |  | 900000 |  | 900000 | 0 | 0
004/003 | Planning and Economic Development | Madisha Goat Co-operative | Assistance to goat farmers | 2008-07-08 | 2008-06-09 | 0 |  | 375000 |  | 475000 |  | 475000 |  | 850000 |  | 850000 |  | 850000 |  | 850000 |  | 850000 |  | 850000 |  | 850000 |  | 850000 |  | 850000 | 0 | 0
004/004 | Planning and Economic Development | Coordination and implementation of integrated Transport plan | Functional District Transport Forum | 2008-07-08 | 2008-06-09 | 0 |  | 0 |  | 0 |  | 80000 |  | 80000 |  | 200000 |  | 200000 |  | 200000 |  | 300000 |  | 300000 |  | 357000 |  | 357000 |  | 357000 | 0 | 0
004/005 | Planning and Economic Development | Policy on Land Use | Developed Policy on land Use | 2008-09-08 | 2008-03-09 | 0 |  | 0 |  | 0 |  | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 400000 |  | 400000 |  | 400000 |  | 550000 |  | 550000 |  | 550000 | 0 | 0
| Planning and Economic Development | Government Complex Township Establishment | Government Complex Establishment | 2009-04-01 | 2009-06-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 380000 |  | 760000 |  | 760000
004/005 | Planning and Economic Development | WDM District Wide Spatial development Framework Review. | Reviewed Spatial Development Framework | 2008-09-08 | 2008-03-09 | 0 |  | 0 |  | 0 |  | 200000 |  | 200000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 | 0 | 0
[6 empty] | 0 |  | 375000 |  | 1225000 |  | 1705000 | 0 | 2760000 | 0 | 2980000 | 0 | 2980000 | 0 | 3600000 | 0 | 4000000 | 0 | 4000000 | 0 | 5567000 | 0 | 5947000 | 0 | 5947000 | 1000000 | 1000000
005/002 | Infrastructure Development | Upgrade of Road Bakenberg to Mapela via Sepharane & Mmahlogo (D3507) | 14 km road upgraded from gravel to tar | 2008-05-01 | 2009-06-30 | 5100000 |  | 5100000 |  | 5100000 |  | 5100000 |  | 5100000 |  | 5100000 |  | 5100000 |  | 5100000 |  | 5100000 |  | 5100000 |  | 5100000 |  | 5100000 |  | 5100000 | 0 | 0
005/002 | Infrastructure Development | Intergrated Infrastructure Master Plan | Intergrated Infrastructure Masterplan | 2008-05-01 | 2008-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 |  | 1000000 |  | 1000000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
005/003 | Infrastructure Development | Upgrading of the Abattoir | Upgraded infrastructure | 2008-03-01 | 2009-06-30 | 0 |  | 0 |  | 0 |  | 150000 |  | 150000 |  | 150000 |  | 300000 |  | 300000 |  | 500000 |  | 500000 |  | 500000 |  | 2050000 |  | 2050000 | 0 | 0
005/008 | Infrastructure Development | Disaster Centre - Lephalale | Disaster Management Centre Completed | 2008-04-01 | 2009-03-31 | 0 |  | 0 |  | 500000 |  | 500000 |  | 1000000 |  | 1000000 |  | 2000000 |  | 2000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 | 0 | 0
005/002 | Infrastructure Development | Resealing of street in Bela Bela | Resealed street in Bela Bela | [27 empty] | 2850000 | 2000000
005/002 | Infrastructure Development | Bela Bela Township Storm water | Storm water infrastructure completed | [27 empty] | 2000000 | 0
[6 empty] | 5100000 | 0 | 5100000 | 0 | 5600000 | 0 | 5750000 | 0 | 6250000 | 0 | 7250000 | 0 | 8400000 | 0 | 8400000 | 0 | 8600000 | 0 | 8600000 | 0 | 8600000 | 0 | 10150000 | 0 | 10150000 | 4850000 | 2000000
006/009 | Office of the Executive Mayor | Communications | Implementtatble Communications Strategy | 2008-10-01 | 2009-06-30 | 0 |  | 0 |  | 0 |  | 50000 |  | 50000 |  | 80000 |  | 80000 |  | 100000 |  | 100000 |  | 150000 |  | 200000 |  | 300000 |  | 300000 | 200000 | 200000
006/009 | Office of the Executive Mayor | District Public Participation | Implementable District Pubblic Participation Strategy | 2008-07-01 | 2009-06-30 | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 150000 |  | 150000 |  | 200000 |  | 200000 |  | 300000 |  | 300000 |  | 400000 |  | 650000 |  | 650000 | 0 | 0
006/013 | Office of the Executive Mayor | Coordination of sport Arts, and Culture | Successful programmes developed on sports, arts and culture | 2008-07-31 | 2009-06-30 | 10000 |  | 150000 |  | 170000 |  | 170000 |  | 170000 |  | 250000 |  | 250000 |  | 400000 |  | 400000 |  | 700000 |  | 700000 |  | 950000 |  | 950000 | 0 | 0
[6 empty] | 110000 | 0 | 250000 | 0 | 270000 | 0 | 320000 | 0 | 370000 | 0 | 480000 | 0 | 530000 | 0 | 700000 | 0 | 800000 | 0 | 1150000 | 0 | 1300000 | 0 | 1900000 | 0 | 1900000 | 200000 | 200000
007/006 | Social Development & Community Services | Develop and review air quality plan | Approved air quality management plan | 2008-07-01 | 2009-06-30 | 0 |  |  |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 500000 |  | 500000 |  | 500000 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 500000 | 0 | 500000 | 0 | 500000 | 0 | 0
009/007 | Environmental Health | Municipal health plan | Approved municipal health plan | 2008-07-01 | 2009-06-30 | 0 |  | 0 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 10000 |  | 3892 |  | 3892 |  | 3892 |  | 3892 |  | 3892 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 10000 | 0 | 3892 | 0 | 3892 | 0 | 3892 | 0 | 3892 | 0 | 3892 | 0 | 0
Total 2008/09 IDP | [5 empty] | 5210000 | #REF! | 5755000 | #REF! | 7205000 | #REF! | 7885000 | #REF! | 9670000 | #REF! | 12140000 | #REF! | 13340000 | #REF! | 14130000 | #REF! | 14873892 | #REF! | 15223892 | #REF! | 20480892 | #REF! | 25997383 | #REF! | 25997383 | 7050000 | 3200000
2008/09 Operating Budget
002 | Office of the Municipal Manager | Strategic plan | Approved and Implementable strategic plan | 2009-01-01 | 2009-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116000 |  | 116000 |  | 116000 |  | 116000 |  | 116000 |  | 116000
002 | Office of the Municipal Manager | MSIG | District wide skills audit | 2008-09-01 | 2009-02-28 | 0 |  | 0 |  | 20000 |  | 20000 |  | 20000 |  | 120000 |  | 220000 |  | 260000 |  | 260000 |  | 260000 |  | 260000 |  | 260000 |  | 260000
002 | Office of the Municipal Manager | MSIG | development of by laws and policies | 2008-07-01 | 2009-03-31 | 20000 |  | 70000 |  | 130000 |  | 145000 |  | 160000 |  | 185000 |  | 205000 |  | 235000 |  | 275000 |  | 275000 |  | 275000 |  | 275000 |  | 275000
002 | Office of the Municipal Manager | MSIG | GAMAP/GRAP compliant fixed asssets register | 2009-03-01 | 2009-04-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 120000 |  | 200000 |  | 200000 |  | 200000 |  | 200000
[6 empty] | 20000 | 0 | 70000 | 0 | 150000 | 0 | 165000 | 0 | 180000 | 0 | 305000 | 0 | 425000 | 0 | 611000 | 0 | 771000 | 0 | 851000 | 0 | 851000 | 0 | 851000 | 0 | 851000 | 0 | 0
003/010 | Corporate Support & Shared Services | Emloyee assistance programme | To improve cllr and staff wellbeing | 2008-07-01 | 2009-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 |  | 200000 |  | 200000 |  | 200000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000 |  | 300000
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 200000 | 0 | 200000 | 0 | 200000 | 0 | 300000 | 0 | 300000 | 0 | 300000 | 0 | 300000 | 0 | 300000 | 0 | 300000 |  | 0
006/007 | Office of the Executive Mayor | Youth | implementable youth programme | 2008-07-30 | 2009-06-30 | 0 |  | 0 |  | 50000 |  | 50000 |  | 50000 |  | 200000 |  | 200000 |  | 200000 |  | 250000 |  | 250000 |  | 250000 |  | 250000 |  | 250000
006/007 | Office of the Executive Mayor | Gender | Implementable gender programme | 2008-07-30 | 2009-06-30 | 10000 |  | 20000 |  | 30000 |  | 50000 |  | 50000 |  | 50000 |  | 70000 |  | 100000 |  | 100000 |  | 100000 |  | 100000 |  | 150000 |  | 150000
006/007 | Office of the Executive Mayor | HIV/AIDS | Awareness campagins | 2008-10-01 | 2009-06-30 | 0 |  | 0 |  | 0 |  | 50000 |  | 50000 |  | 50000 |  | 90000 |  | 90000 |  | 90000 |  | 120000 |  | 120000 |  | 150000 |  | 150000
006/013 | Office of the Executive Mayor | Sport, Arts and Culture | Successful O.R. Tambo games | 2008-09-01 | 2009-06-30 | 0 |  | 0 |  | 50000 |  | 50000 |  | 50000 |  | 50000 |  | 60000 |  | 60000 |  | 80000 |  | 80000 |  | 100000 |  | 150000 |  | 150000
006/007 | Office of the Executive Mayor | Disability | Disability Desk established | 2008-07-01 | 2009-06-30 | 30000 |  | 30000 |  | 30000 |  | 40000 |  | 70000 |  | 70000 |  | 70000 |  | 80000 |  | 80000 |  | 80000 |  | 80000 |  | 100000 |  | 100000
006/010 | Office of the Executive Mayor | Twinning Agreements | Visists undertaken | 2008-07-30 | 2009-06-30 | 30000 |  | 30000 |  | 30000 |  | 100000 |  | 100000 |  | 100000 |  | 150000 |  | 150000 |  | 180000 |  | 250000 |  | 250000 |  | 250000 |  | 250000
006/010 | Office of the Executive Mayor | Executive Mayor`s Golf Challenge | Success Golf Challenge | 2009-03-01 | 2009-04-30 | 0 |  | - |  | - |  | - |  | - |  | - |  | 50 000 |  | 50000 |  | 150000 |  | 200000 |  | 200000 |  | 200000 |  | 200000
[6 empty] | 70000 | 0 | 80000 | 0 | 190000 | 0 | 340000 | 0 | 370000 | 0 | 520000 | 0 | 640000 | 0 | 730000 | 0 | 930000 | 0 | 1080000 | 0 | 1100000 | 0 | 1250000 | 0 | 1250000 | 0 | 0
Total 2008/09 Projects included in Operating Budget | [5 empty] | 120000 | 0 | 280000 | 0 | 420000 | 0 | 600000 | 0 | 660000 | 0 | 1890000 | 0 | 2030000 | 0 | 2310000 | 0 | 1510000 | 0 | 1960000 | 0 | 1980000 | 0 | 2450000 | 0 | 2450000 | 2850000 | 2000000
2007/08 Roll Over
002/009 | MM | IDP | Community participation | 2008-07-01 | 2009-05-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 200000 |  | 400000 |  | 400000 |  | 400000
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 400000 | 0 | 400000 | 0 | 400000 | 0 | 0
003/010 | CSSS | Institutional study | To undertake an institutional study | 2008-07-01 | 2009-02-28 | 5000 |  | 5000 |  | 5000 |  | 105000 |  | 105000 |  | 105000 |  | 155000 |  | 205000 |  | 255000 |  | 255000 |  | 255000 |  | 337459 |  | 337459
003/010 | CSSS | Training of fire fighting volunteers | Skills development for volunteers | 2008-07-01 | 2009-03-30 | 70000 |  | 70000 |  | 70000 |  | 70000 |  | 70000 |  | 70000 |  | 70000 |  | 120000 |  | 120000 |  | 120000 |  | 120000 |  | 245368.88 |  | 245368.88
003/010 | CSSS | Transfer of mayoral house property | Transferred land | 2008-07-01 | 2009-06-30 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 100000 |  | 100000
003/010 | CSSS | Implement MSP projects | To improve ict at Wdm & lm,s | 2008-07-01 | 2009-06-30 | 0 |  | 0 |  | 50000 |  | 50000 |  | 100000 |  | 800000 |  | 800000 |  | 1400000 |  | 1550000 |  | 1550000 |  | 1550000 |  | 2304798.98 |  | 2304798.98
| CSSS | S78 Health assessment | To comply with s78 MSA |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25000 |  | 50000 |  | 50000 |  | 50000
| CSSS | IFMS | IFMS |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 300000 |  | 300000
003/010 | CSSS | Procurement of movable assets | Effective asset management | 2008-07-01 | 2009-06-30 | 0 |  | 800000 |  | 900000 |  | 1100000 |  | 1200000 |  | 1250000 |  | 1400000 |  | 1550000 |  | 2271798.53 |  | 2271798.53 |  | 2271798.53 |  | 2271798.53 |  | 2271798.53
[6 empty] | 75000 | 0 | 875000 | 0 | 1025000 | 0 | 1325000 | 0 | 1475000 | 0 | 2225000 | 0 | 2425000 | 0 | 3275000 | 0 | 4196798.53 | 0 | 4221798.53 | 0 | 4246798.53 | 0 | 5609425.39 | 0 | 5609425.39 | 0 | 0
004/003 | Planning and Economics | Feasibility study for a Wildlife Centre | Appointment of a service provider to commission study | 2008-08-08 | 2008-12-09 | 0 |  | 0 |  | 50000 |  | 200000 |  | 350000 |  | 500000 |  | 500000 |  | 500000 |  | 500000 |  | 2993068.64 |  | 2993068.64 |  | 2993068.64 |  | 2993068.64
004/003 | Planning and Economic Development | Lephalale Agricultural Corridor | Storage Hub for food process | 2008-09-08 | 2008-12-09 | 0 |  | 0 |  | 900000 |  | 900000 |  | 900000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 3000000
004/003 | Planning and Economic Development | Tourism Development | Publications, tourism & branding material,brand exposure | 2008-07-01 | 2009-01-30 | 67000 |  | 322000 |  | 447000 |  | 451000 |  | 585000 |  | 785000 |  | 931242 |  | 931242 | 931242 | 931242 | 931242 | 931242 | 931242 | 931242 | 931242 | 931242 |  | 931241.75
004/005 | Planning and Economic Development | Policy on land use | Completed policy on land use | 2008-07-01 | 2009-04-30 | 0 |  | 0 |  | 4252 |  | 4252 |  | 4252 |  | 4252 |  | 150000 |  | 150000 |  | 150000 |  | 150000 |  | 150000 |  | 150000 |  | 150000
[6 empty] | 67000 | 0 | 322000 | 0 | 1401252 | 0 | 1555252 | 0 | 1839252 | 0 | 4289252 | 0 | 4581242 | 0 | 4581242 | 931242 | 4581242 | 931242 | 7074310.64 | 931242 | 7074310.64 | 931242 | 7074310.64 | 0 | 7074310.39 | 0 | 0
005/002 | Infrastructure Development | CMIP | Water & Sanitation | 2008-07-01 | 2008-09-30 | 0 |  | 0 |  | 1614965.34 |  | 1614965.34 |  | 1614965.34 |  | 1614965.34 |  | 1614965.34 |  | 1614965.34 |  | 1614965.34 |  | 1614965.34 |  | 1614965.34 |  | 1614965.34 |  | 1614965
005/008 | Infrastructure Development | Modimolle Disaster Centre | Completed disaster management centre | 2008-07-01 | 2008-12-30 | 0 |  | 0 |  | 520619 |  | 520619 |  | 520619 |  | 857794 |  | 857794 | 857794 | 857794 | 857794 | 857794 | 857794 | 857794 | 857794 | 857794 | 857794 | 857794 |  | 857793.53
005/001 | Infrastructure Development | Drought Relief Plan | Drought Relief Plan | 2008-07-01 | 2009-05-30 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
005/002 | Infrastructure Development | Intergrated Infrastructure Master Plan (Roll over) | Intergrated Infrastructure Masterplan | 2008-05-01 | 2008-12-01 | 0 |  | 0 |  | 0 |  | 0 |  | 150000 |  | 150000 |  | 150000 |  | 150000 |  | 150000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
005/003 | Infrastructure Development | Upgrading of the Abattoir (Roll over) | Upgraded infrastructure | 2008-03-01 | 2009-06-30 | 0 |  | 0 |  | 0 |  | 500000 |  | 500000 |  | 500000 |  | 1000000 |  | 1000000 |  | 1774096.93 |  | 1774096.93 |  | 1774096.93 |  | 1774096.93 |  | 1774096.93
005/008 | Infrastructure Development | Disaster Centre - Lephalale (Roll over) | Disaster Management Centre Completed | 2008-04-01 | 2009-03-31 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2277937.65 | 2277937.65 | 2277937.65 | 2277937.65 | 2277937.65 | 2277937.65 | 2277937.65 | 2277937.65 | 2277937.65 | 2277937.65 | 2277937.65 |  | 2277937.65
005/001 | Infrastructure Development | Northam Sewer Ext. 5 Phase 2 & Ext. 7 | Sewer reticulation network completed | 2008-03-01 | 2009-06-30 | 0 |  | 0 |  | 268740 |  | 268740 |  | 268740 |  | 368740 |  | 368740 |  | 1268740 |  | 3068740 |  | 7068740 |  | 8268740 |  | 9374639 |  | 9374638.82
005/002 | Infrastructure Development | Construction of Bridge - Rust de Winter - small holdings (EPWP) | Bridge structure completed | 2008-03-01 | 2009-06-01 | 0 |  | 0 |  | 100000 |  | 100000 |  | 500000 |  | 500000 |  | 1400000 |  | 1400000 |  | 2000000 |  | 2500000 |  | 3546062 |  | 3546062 |  | 3546062
005/006 | Infrastructure Development | Identification, auditing and maintenance of solid waste landfill sites | Legally compliant landfill sites | 2008-04-01 | 2009-06-01 | 0 |  | 0 |  | 500000 |  | 500000 |  | 1400000 |  | 1400000 |  | 2600000 |  | 2600000 |  | 3200000 |  | 3600000 |  | 3990253.87 |  | 3990253.87 |  | 3990253.87
005/006 | Infrastructure Development | Refuse Buy Back centre at Mogalakwena | Refuse Buy Back centre completed | 2008-07-01 | 2009-06-30 | 0 |  | 0 |  | 0 |  | 100000 |  | 100000 |  | 500000 |  | 500000 |  | 500000 |  | 800000 |  | 0 |  | 0 |  | 0 |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5054324.34 | 0 | 5891499.34 | 0 | 10769436.99 | 3135731.65 | 11669436.99 | 3135731.65 | 15743533.92 | 3135731.65 | 19693533.92 | 3135731.65 | 22329849.79 | 3135731.65 | 23435748.79 | 0 | 23435747.8 | 0 | 0
006/009 | Office of the Executive Mayor | Communication | implementable communications Strategy | 2008-07-01 | 2008-11-30 | - |  | - |  | - |  | 10000 |  | 10000 |  | 210000 |  | 210000 |  | 210000 |  | 210000 |  | 420141 |  | 420141 |  | 420141 |  | 420141
006/009 | Office of the Executive Mayor | Special Projects | Succesful implementation of Special projects | 2008-07-01 | 2008-11-30 | 10000 |  | 10000 |  | 120000 |  | 200000 |  | 314638.12 |  | 314638.12 |  | 314638.12 |  | 314638.12 |  | 314638.12 |  | 314638.12 |  | 314638.12 |  | 314638.12 |  | 314638.12
006/009 | Office of the Executive Mayor | District Public Participation | implementable public participation strategy | 2008-07-01 | 2008-11-30 | 450000 |  | 450000 |  | 500000 |  | 500000 |  | 500244.56 |  | 500244.56 |  | 500244.56 |  | 500244.56 |  | 500244.56 |  | 500244.56 |  | 500244.56 |  | 500244.56 |  | 500244.56
006/013 | Office of the Executive Mayor | Co-ordinate annual arts and cultural activities | Coordination of the District Arts and Culture Competitions, hosting mayoral tournament. | 2008-09-01 | 2009-01-31 | - |  | - |  | 100000 |  | 100000 |  | 100000 |  | 220000 |  | 220000 |  | 363587 |  | 363587 |  | 363587 |  | 363587 |  | 363587 |  | 363587.36
[6 empty] | 460000 | 0 | 460000 | 0 | 720000 | 0 | 810000 | 0 | 924882.68 | 0 | 1244882.68 | 0 | 1244882.68 | 0 | 1388469.68 | 0 | 1388469.68 | 0 | 1598610.68 | 0 | 1598610.68 | 0 | 1598610.68 | 0 | 1598611.04 | 0 | 0
Total Roll Over | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9293459.02 | 0 | 13650634.02 | 0 | 19020561.67 | 3135731.65 | 20914148.67 | 4066973.65 | 25910044.13 | 4066973.65 | 32788253.77 | 4066973.65 | 35649569.64 | 4066973.65 | 38118095.5 | 0 | 38118094.62 | 0 | 0