## Rescue Phase
NO | FOCUS AREA RESCUE | Baseline Finding/Key Issues | KEY INTERVENTION ACTIVITIES (Deliverables) | DESIRED RECOVERY OUTCOME (Definition: The end goal to be achieved through actions to be undertaken) | TARGET | KEY PERFORMANCE INDICATOR | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT/ FINANCIAL IMPACT | MUNICIPAL PROGRESS REPORT
[14 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR 1: FINANCIAL MANAGEMENT
1 | Budget Management (Funding Status, | The municipality approved unfunded budgets for the past years, including the current financial year 2025/26, as shown below with negative net cash funding shortfalls: • FY2025/26: (R16.3 million) FY2026/27: (R27.4 million). | Prepare and approve an adjustment budget to contain expenditure within realistically anticipated revenues to reduce the 2026/27 budget deficit to R4.9 million, resulting in a net cash deficit of R9.8 million. | Approve and adopt a funded budget | Adjustment budget with a reduced deficit to R4.9 million. | % reduction 2026/27 Adjustment Budget deficit. | In-house | In-house | CFO | 2027-01-01 | 2027-04-30 | Approved adjustment budget | % reduction in budget deficit.
2 |  |  | Introduce strict budget controls and monthly budget performance reviews |  | Reduced net cash shortfall to R9.8 million. | % reduction in the 2026/27 Budget funding shortfall. | In-house | In-house | CFO | 2026-10-01 | monthly | Monthly budget performance review reports | Improved funding of the unfunded budget.
3 |  | The budget funding plan contains long-term initiatives and lacks short-term interventions that could assist the municipality in addressing its unfunded budget position. | Update the budget funding plan for 2026/27 to include short-term strategies to enhance revenue sources and align with FRP approved budget parameters. |  |  | % increase in own revenue | In-house | In-house | CFO | 2026-10-01 | 2026-08-31 | Budget funding plan | Increase in revenue.
4 |  |  | Redesign the Budget Funding Plan into quarterly measurable actions to: - Include SMART performance indicators. - Assign accountable officials for each intervention. - Monitor implementation monthly through EXCO and Council. - Include corrective actions where targets are missed |  |  | % Revenue enhancement initiatives implemented according to plan. | In-house | In-house | CFO | 2026-10-01 | 2026-12-31 | Budget funding plan | Increase in revenue.
5 | Revenue Management | • Fire Services are required by law at the district level and play a key role in public safety. However, the current operating model is not financially sustainable if the municipality aims to meet all requirements, as the municipality does not have Service Level Agreements with the local municipalities where they are delivering the services.Although norms and standards set a goal, many municipalities across the country fall short because the funding model does not allow for full staffing and fleet requirements. | Conclude Service Level Agreements with local municipalities for firefighting services. | Sustainable municipal own sources of revenue. | SDAs concluded with all local municipalities by the end date. | No. of local municipalities with which SDAs have been concluded. | In-house | In-house | CFO | 2026-10-01 | 2026-12-31 | Service level agreements | Increase in revenue.
6
7 |  | • Disaster Management is a core district-wide coordination function and remains one of the municipality’s most important public protection responsibilities. • The municipality cannot currently fund the ideal establishment from its present revenue base. | Introduce equitable cost-sharing arrangements. |  | MPT cost-sharing arrangements concluded with all local municipalities. | No. of local municipalities with which MPT cost sharing arranegments have been concluded. | In-house | In-house | CFO | 2026-10-01 | 2026-12-31 | Service level agreements | Increase in revenue.
8 |  | At the same time, cutting overtime and constraining staffing may save money in the short term, but it weakens emergency readiness, increases operational risk, and places additional strain on already limited personnel | Recover costs from high-risk industries where legislation permits. |  | SDAs concluded with all high risk entities with the DMA by the end date. | No. of high risk entities with which SDAs are concluded | In-house | In-house | CFO | 2026-10-01 | 2026-12-31 | Signed SDA | Increase in revenue.
9 | Cash Flow Management | • WDM is unable to settle its short-term obligations, as current liabilities exceed current assets by R37.5 million in FY2024/25, and by R17.3 million in the prior year. | Confirm the availability of budget and cash flows prior to commencing with procurement processes. | Maintain sufficient liquidity to meet obligations. | Net increase in cash and cash equivalents of at least R 476 371 thousand. | Increase in cash and cash equivalents | In-house | In-house | CFO | 2026-10-01 | monthly | MFMA S71/Circular 71 Financial Ratios Assessment Report | Increase in reserves
10 |  | Cash/cost coverage ratio has been 0 months in FY2024/25 and FY2023/24, which is below the 1-3-month norm.. | Prepare rolling 12-month cash flow forecasts. |  |  |  | In-house | In-house | CFO | 2026-10-01 | monthly | Payroll reconciliations/Cashflow reports | Increased compliance
11 |  | • Short-term deposits decreased by R23 million, from R68 million in 2020 to R44.9 million in 2021. The deposits further declined by R20 million, reaching R24.8 million in 2022. | Prioritise expenditure and payments according to cash availability. |  |  |  | In-house | In-house | CFO | 2026-10-01 | monthly | Third party reconciliations/cashflow analysis. | Increased compliance
12 |  | • The current ratio has been significantly below the norm at 0.03 in FY2024/25 and 0.28 in FY2023/24. | Implement weekly cash budgets, compare against actuals and address significant variances. |  |  |  | In-house | In-house | CFO | 2026-10-01 | monthly | Weekly cash budgets | Improved cash flow management
13 | Expenditure management | The municipality incurred operating deficits for the past five financial years. This resulted in the erosion of a healthy net cash position of R44,2 million held at the end of 2020/21 | Implement a comprehensive Cost Containment Policy and achieve the following: o Apply to the bargaining council to temporarily freeze salaries and benefits annual increases. o Apply to the bargaining council to temporarily freeze salaries and benefits annual increases. o Spend less than R1.5 million on travel and subsistence in the financial year 2026/27. o Adjust the budget to eliminate spending on decorations, entertainment registration fees, long term service awards, bursaries and cleaning. o Spend R2.1 million on insurance expenses by not insuring redundant property plant and equipment items. o Spend less than R3.5 million on municipal services in the financial year 2026/27. o Spend R800k on licenses expenses. o Apply to the Auditor General’s office to cap audit fees to R2.9 million in the financial year 2025/26 audit. o Cap spending on communication to R400k in 2026/27FY. o Negotiate better terms for computer services and cap spending to R2.7 million. o Reduce spending to R180k on printing, publications and books. o Limit spending on outsourced Services to R720k by performing travel agents’ services using existing employees within the municipality. o Cap contractors’ spending to R9.5 million by reducing repairs and maintenance of building and redundant vehicles. o Obtain a council resolution to rescind its decision to pay employees a housing allowance of R1.5k instead of R1.1k as approved by the bargaining council. o Encourage employees to take their leave days and limit the leave provision to R1.2 million. | Sustainable municipal financial performance | Expenditure budget implementation indicator for 2026/27 FY below 100% in line with targeted cost containment. | % Expenditure Implementation Indicator. | In-house | In-house | Expenditure Manager | 2026-10-01 | monthly | Expenditure analysis report | Improved cash flow management
14 |  |  | Review and restrict employee benefits and travel expenditure. |  | 2026/27 Operating deficit not exceeding R4.9 million. | Net operating margin for the 2026/27 FY. | In-house | In-house | CFO | 2026-10-01 | Yearly | Budgets/S71/AFS | Reduction in operating deficit
15 |  |  | Prioritize SARS and third-party payments monthly to avoid penalties and interest. |  | Pay SARS and pension obligations by 7th each month | No. of statutory payments made by due date. | In-house | In-house | CFO | 2026-10-01 | monthly | Third party reconciliations | Increased compliance
PILLAR 4: INSTITUTIONAL
2 | Employee related cost | High employee related cost expenditure due to high salary increase and over-graded positions | Secure the Municipal Manager's formal sign-off and Council ratification of the finalized Provincial SALGA TASK Job Evaluation Outcomes Report. | Stabilize the municipality's cash position and restore longterm fiscal vaibility. | Maintain a benchmark target of less 65 per cent. | Reduction of employee related cost as % of total operating expenditure | In-house | In-house | Director: Corporate Services | 2026-10-01 | 2027-03-31 | Approved Monthly Section 71 reports (showing actual vs. budgeted expenditure). Approved Annual Budget (Table A4 and Table SA22). Quarterly Section 52(d) reports tabled to Council.
|  |  | Compile an updated, verified financial diagnostic report demonstrating budget deficits, and a negative cash-back position over the MTREF period | [6 empty] | 2026-10-01 | 2027-03-31
|  |  | Prepare and package the formal SALGBC exemption application in strict compliance with the SALGBC Main Collective Agreement criteria. | [6 empty] | 2026-10-01 | 2027-03-31
|  |  | Convene formal Local Labour Forum (LLF) engagements to consult municipal trade unions (SAMWU and IMATU) on the financial crisis and the necessity of the exemption. | [6 empty] | 2026-10-01 | 2027-03-31
|  |  | Secure an urgent Council Resolution authorizing the exemption application and formally lodge the submission with the SALGBC before the statutory deadline. | [6 empty] | 2026-10-01 | 2027-03-31
|  |  | Freeze recruitment for all non-critical, non-technical vacant positions. The filling of critical funded vacancies must be subject to a verified, positive cash-back position over the MTREF period | [6 empty] | 2026-10-01 | 2027-03-31
5 | Physical verification of the staff | Verification of staff is never conducted unless directed by AG during audit processes. | Perform an immediate data-match between the physical headcount audit results and the active system payroll register to flag variances. | Fully secured payroll integrity and proactive prevention of irregular personnel expenditure through institutionalized headcounts. | 100% of all staff physically verified annually. | Fully secured payroll integrity and proactive prevention of irregular personnel expenditure through institutionalized headcounts. | In house | In-house | Director: Corporate Services | 2026-10-01 | 2027-03-31 | Monthly payroll reconciliation reports signed off by the CFO | improved physical verification of staff
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Review and update
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Review and updated

## Sheet1 (hidden)
FOCUS AREA RESCUE | Baseline Finding/Key Issues | DESIRED OUTCOME | ACTIVITY: RESCUE PHASE
Budget Management (Funding Status, | The municipality approved unfunded budgets for the past years, including the current financial year 2025/26, as shown below with negative net cash funding shortfalls: • FY2025/26: (R16.3 million) FY2026/27: (R27.4 million). | Approve and adopt a funded budget | Prepare and approve an adjustment budget to contain expenditure within realistically anticipated revenues to reduce the 2026/27 budget deficit to R8,1 million, resulting in a net cash deficit of R21,1 million.
Introduce strict budget controls and monthly budget performance reviews
| The budget funding plan contains long-term initiatives and lacks short-term interventions that could assist the municipality in addressing its unfunded budget position. |  | Update the budget funding plan for 2026/27 to include short-term strategies to enhance revenue sources and align with FRP approved budget parameters.
Redesign the Budget Funding Plan into quarterly measurable actions. - Include SMART performance indicators. - Assign accountable officials for each intervention. - Monitor implementation monthly through EXCO and Council. - Include corrective actions where targets are missed
Revenue Management | • Fire Services are required by law at the district level and play a key role in public safety. However, the current operating model is not financially sustainable if the municipality aims to meet all requirements, as the municipality does not have Service Level Agreements with the local municipalities where they are delivering the services. |  | • Ring-fence equitable share for legislated district functions.
| • Although norms and standards set a goal, many municipalities across the country fall short because the funding model does not allow for full staffing and fleet requirements. |  | • Conclude Service Level Agreements with local municipalities for firefighting services.
| • Disaster Management is a core district-wide coordination function and remains one of the municipality’s most important public protection responsibilities. • The municipality cannot currently fund the ideal establishment from its present revenue base. |  | • Introduce equitable cost-sharing arrangements.
| At the same time, cutting overtime and constraining staffing may save money in the short term, but it weakens emergency readiness, increases operational risk, and places additional strain on already limited personnel |  | • Recover costs from high-risk industries where legislation permits.
Cash Flow Management | • WDM is unable to settle its short-term obligations, as current liabilities exceed current assets by R37.5 million in FY2024/25, and by R17.3 million in the prior year. • | Municipality maintains sufficient liquidity to meet obligations. | • Confirm the availability of budget and cash flows prior to commencing with procurement processes.
| Cash/cost coverage ratio has been 0 months in FY2024/25 and FY2023/24, which is below the 1-3-month norm.. |  | ·Prepare rolling 12-month cash flow forecasts.
| • Short-term deposits decreased by R23 million, from R68 million in 2020 to R44.9 million in 2021. The deposits further declined by R20 million, reaching R24.8 million in 2022. |  | ·Prioritise expenditure and payments according to cash availability.
| • The current ratio has been significantly below the norm at 0.03 in FY2024/25 and 0.28 in FY2023/24. |  | · Introduce weekly cash management meetings.
Expenditure management | The municipality incurred operating deficits for the past five financial years. This resulted in the erosion of a healthy net cash position of R44,2 million held at the end of 2020/21 | Sustainable municipal financial performance. | Implement a comprehensive Cost Containment Policy and achieve the following: o Apply to the bargaining council to temporarily freeze salaries and benefits annual increases. o Apply to the bargaining council to temporarily freeze salaries and benefits annual increases. o Spend less than R1.5 million on travel and subsistence in the financial year 2026/27. o Adjust the budget to eliminate spending on decorations, entertainment registration fees, long term service awards, bursaries and cleaning. o Spend R2.1 million on insurance expenses by not insuring redundant property plant and equipment items. o Spend less than R3.5 million on municipal services in the financial year 2026/27. o Spend R800k on licenses expenses. o Apply to the Auditor General’s office to cap audit fees to R2.9 million in the financial year 2025/26 audit. o Cap spending on communication to R400k in 2026/27FY. o Negotiate better terms for computer services and cap spending to R2.7 million. o Reduce spending to R180k on printing, publications and books. o Limit spending on outsourced Services to R720k by performing travel agents’ services using existing employees within the municipality. o Cap contractors’ spending to R9.5 million by reducing repairs and maintenance of building and redundant vehicles. o Obtain a council resolution to rescind its decision to pay employees a housing allowance of R1.5k instead of R1.1k as approved by the bargaining council. o Encourage employees to take their leave days and limit the leave provision to R1.2 million.
Review and restrict employee benefits and travel expenditure.
Prioritize SARS and third-party payments monthly to avoid penalties and interest.
Creditors management | Trade payables significantly increased by 358.05 per cent from R3.6 million in the FY2023/24 to R16.4 million in the FY2024/25 due to cash flow constraints and a lack of adequate cost containment of controllable costs. | Reduction of outstanding creditors and improved payment discipline. | • Eliminate interest expenses by negotiating with creditors to waive interest charges on overdue accounts.
| • Creditor’s payment period significantly deteriorated by 325.11 per cent from 33 days in the FY2023/24 to 141 days in the FY2024/25. |  | • Negotiate payment arrangements with SARS, pension funds and major suppliers.
• Prioritise statutory deductions.
• Monitor creditor ageing monthly.
• Prevent accumulation of new arrears.

## Stabilisation Phase
NO | FOCUS AREA STABILISATION | Baseline Finding/Key Issues | KEY INTERVENTION ACTIVITIES (Deliverables) | DESIRED RECOVERY OUTCOME (Definition: The end goal to be achieved through actions to be undertaken) | TARGET | KEY PERFORMANCE INDICATOR | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT/ FINANCIAL IMPACT | MUNICIPAL PROGRESS REPORT
[14 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR 1: FINANCIAL MANAGEMENT
1 | Budget Management (Funding Status, | • The municipality approved unfunded budgets for the past years, including the current financial year 2025/26, as shown below with negative net cash funding shortfalls: o FY2020/21: R44.2 million o FY2021/22: R24.6 million o FY2022/23: R11.2 million o FY2024/25: R2.6 million o FY2025/26: (R16.3 million) • Failure to contain expenditure resulted in the depletion of the municipality’s reserves and incurrence of operating deficits for the past five financial years: o FY2020/21: (R15.5 million) o FY2021/22: (R27.5 million) o FY2022/23: (R16.7 million) o FY2023/24: (R21.2 million) o FY2024/25: (R24.4 million) • No sufficient reserves to cover all financial obligations. | Prepare and approve the 2027/28 MTREF budget to contain expenditure within realistically anticipated revenues and reduce the budget deficit to R3.6 million and the net cash deficit to R7.8 million. | Approve and adopt a funded budget | Approved 2027/298MTREF budget with an reduced operating deficit to R3.6 million. | % Reduction 2027/28 MTREF Budget deficit. | In-house | In-house | CFO | 2027-01-01 | 2027-06-30 | Approved adjustment budget | % reduction in budget deficit.
3 | Revenue Management | The abattoir operations are running at a loss. | Dispose of the abattoir in compliance with section 14 of the MFMA. Labor Relations Act and regulations thereon. | Discontinued and disposed abattoir. | Abattoir disposed at fair or market value in line valuation report. | Amount of revenue raised from the proceed of sale | In-house | In-house | CFO | 2026-10-01 | Yearly | Sale/auction reports. | Increase in avaialable cash and reduction in expenditure
4 | Cost-reflective tariffs | • The district provides technical and institutional support to locals, but the current fee structure neither recognizes nor compensates the district for this role, e.g., Appeal Authority and Municipal Planning Tribunal (MPT). • Municipal functions are not breaking even and are operating at year–on–year losses. | Prepare a business plan and apply for provincial and national disaster management funding. | Sustainable municipal own sources of revenue. | Approved business plan submitted by end date. | Increase in Disaster Relief funding | In-house | In-house | Revenue manager & CFO | 2027-01-01 | 2027-06-30 | Approved of business plan/application | Increase in revenue
5 |  |  | Introduce cost-reflective tariffs where legally permissible. |  | 5% increase in revenue | % increase in revenue | In-house | In-house | Revenue manager & CFO | 2027-01-01 | 2027-06-30 | Approved Council tariff structure and resolution | Increase in revenue
6 |  |  | Enter into private partnerships with the private sector. |  | 5% increase in revenue | % increase in revenue | In-house | In-house | Revenue manager & CFO | 2027-01-01 | 2027-06-30 | Signed/approved PPP agreements | Increase is revenue and reduction in operating expenditure
| Cash Flow Management and Cost Containment | • WDM is unable to settle its short-term obligations, as current liabilities exceed current assets by R37.5 million in FY2024/25, and by R17.3 million in the prior year. • Cash/cost coverage ratio has been 0 months in FY2024/25 and FY2023/24, which is below the 1-3-month norm. • Short-term deposits decreased by R23 million, from R68 million in 2020 to R44.9 million in 2021. The deposits further declined by R20 million, reaching R24.8 million in 2022. • The current ratio has been significantly below the norm at 0.03 in FY2024/25 and 0.28 in FY2023/24. | Improve investment management of surplus funds. | Attain and maintain sufficient liquidity to meet obligations. | Cash coverage improves to at least 1 month of operational expenditure. | No of months cash/cost coverage | In-house | In-house | CFO | 2027-01-01 | Monthly | S71 reports/MFMA Circular 71 ratios | Increase in cash and cash equivelants
7 |  |  |  |  | 100% Salaries and statutory obligations paid on time every month. | No of third-parties paid by 7th of each month | In-house | In-house | CFO | 2027-01-01 | Monthly | S71 reports/Bank statements | Increase in cash reserves
8 |  |  | Build cash-backed reserves over time. |  | Cash coverage improves to at least 1 month of operational expenditure. | % Increase in cash and cash equivalents | In-house | In-house | CFO | 2027-01-01 | Monthly | S71 reports/Bank statements | Increase in cash reserves
9 | Expenditure management | • Actual operating expenditure for FY2024/25 was R194.4 million, 4.36 per cent below the budgeted R196.2 million. However, overall expenditure remains high due to controllable costs not being eliminated. | Implement a comprehensive Cost Containment Policy and achieve the following: • Spend less than R1.5 million on travel and subsistence in the financial year 2027/28 onwards. • Spend less than R1.5 million on travel and subsistence in the financial year 2027/28 onwards. • Adjust the budget to eliminate spending on decorations, entertainment registration fees, long term service awards, bursaries and cleaning. • Spend R2.1 million on insurance expenses by not insuring redundant property plant and equipment items. • Spend less than R3.5 million on municipal services. • Spend R800k on licenses expenses. • Apply to the Auditor General’s office to cap audit fees to R3.0 million in the financial year 2027/28 onwards. • Cap spending on communication to R400k. • Limit spending on computer services to R2.7 million. • Reduce spending to R180k on printing, publications and books. • Limit spending on outsourced Services to R720k by performing travel agents’ services using existing employees within the municipality. • Cap contractors’ spending to R9.5 million by reducing repairs and maintenance of building and redundant vehicles. • Obtain a council resolution to rescind its decision to pay employees a housing allowance of R1.5k instead of R1.1k as approved by the bargaining council. • Encourage employees to take their leave days and limit the leave provision to R1.2 million. | Sustainable municipal financial performance. | Expenditure budget implementation indicator for 2026/27 FY below 100% in line with targeted cost containment. | % Expenditure Implementation Indicator. | In-house | In-house | Expenditure Manager | 2026-10-01 | monthly | Expenditure analysis/S71 &52 D reports | Improved cash flow management
10 | mSCOA | • Other expenditure includes repair & maintenance costs, contracted services, travel costs, bursaries, and a whole range of expenditure items. • AFS does not include segmented figures for the respective services. • Financial statements do not explicitly disclose contracted services and most of the contracted services are disclosed as part of general expenditure. actual figures in the MTREF are different from those reflected in the detailed general ledger. | Fully align the chart of accounts with mSCOA requirements. | Improved credibility and intergrity of municipal reporting data | 100% mSCOA compliance | 100% mSCOA compliance | In-house | In-house | mSCOA champion | 2026-10-01 | Monthly | Data strings | Increased compliance
11 |  |  | Classify expenditure correctly by function and segment. |  |  |  | In-house | In-house | mSCOA champion | 2026-10-01 | Monthly | Data strings | Increased compliance
12 |  |  | Improve financial reporting, cash management and expenditure controls. |  |  |  | In-house | In-house | mSCOA champion | 2026-10-01 | Monthly | Data strings | Increased compliance
13 |  |  | Train finance officials on mSCOA compliance. |  |  |  | In-house | In-house | mSCOA champion | 2026-10-01 | Monthly | Training manuals and attendance registers | Increased compliance
14 |  |  | Perform monthly reconciliations between the general ledger, trail balance, income registers and sub-ledger. |  |  |  | In-house | In-house | mSCOA champion | 2026-10-01 | Monthly | Monthly reconciliations | Increased compliance
1 | Capital Programme and PMU | PMU not fully capacitated or commercialised. Weak grant scanning. No systematic fee income | Approve interim PMU mandate, potential services and priority project list |  |  |  | In-house/DBSA/MISA | In-house/DBSA/MISA | Manager: Infrastructure Development | 2027-01-01 | 2027-12-31 | Council/management resolution. PMU concept note. Project register | Foundation for future fee income and grant access
|  |  | Create grant pipeline and funding calendar for Treasury, DBSA, MISA and sector grants |  |  |  | In-house/DBSA/MISA | In-house/DBSA/MISA | Manager: Infrastructure Development | 2027-01-01 | 2027-12-31 | Grant pipeline. Submissions. Acknowledgement letters. Tracking dashboard | Potential to unlock grant funding
|  |  | Negotiate pilot PMU/implementing-agent support agreements with selected local municipalities |  |  |  | In-house/DBSA/MISA | In-house/DBSA/MISA | Manager: Infrastructure Development | 2027-01-01 | 2027-12-31 | Signed Moues/SLAs. Project briefs. Fee proposals. Progress reports | Potential implementing-agent and project-management fee income
2 | Water Services | Proposed WSA function carries debt and legal risks | Complete WSA feasibility, legal review and business model |  |  |  | In-house/DWS/DBSA | In-house/DWS/DBSA | Manager: Infrastructure Development | 2027-01-01 | 2027-12-31 | Feasibility report. Legal opinion. Business case. Council resolution | Fund through reprioritisation/external support. Risk-reduction step
|  |  | Prioritise low-risk water support business cases: laboratory, maintenance, package plants, shared services |  |  |  | In-house/DWS/DBSA | In-house/DWS/DBSA | Manager: Infrastructure Development | 2027-01-01 | 2027-12-31 | Business cases. Costing models. Draft SLAs. Concept notes | Prepares future service-fee income.
|  |  | Prepare district water-testing laboratory implementation plan and client engagement |  |  |  | In-house/DWS/DBSA | In-house/DWS/DBSA | Manager: Infrastructure Development | 2027-01-01 | 2027-12-31 | Client register. Tariff schedule. Lab plan. Business model | Potential future testing-fee income
3 | Development Planning | No fee-sharing for MPT, Appeal, and planning inputs. Limited monetisation. Possible land cost leakage | Conduct cost-of-service study for MPT, Appeal Authority, building-plan fire comments and spatial data services |  |  |  | In-house/COGSTA | In-house/COGSTA | Manager: Planning & Economic Development | 2027-01-01 | 2027-12-31 | Final costing report. Management approval | Basis for new fee income
|  |  | Negotiate proportional fee-sharing model with local municipalities, and implement. |  |  |  | In-house/COGSTA | In-house/COGSTA | Manager: Planning & Economic Development | 2027-01-01 | 2027-12-31 | Engagement minutes. Draft agreements. Tariff framework | Target new fee income without major capital cost
|  |  | Complete district land audit and identify monetisation-ready sites |  |  |  | In-house/COGSTA | In-house/COGSTA | Manager: Planning & Economic Development | 2027-01-01 | 2027-12-31 | Land audit report. Property register. Concept notes | Potential rental income and reduced holding costs
|  |  | Review and adopt tariff by-laws for planning, land-use and paid spatial-data services |  |  |  | In-house/COGSTA | In-house/COGSTA | Manager: Planning & Economic Development | 2027-01-01 | 2027-12-31 | Draft/adopted by-law. Tariff schedule | Target new service-fee income
4 | Economic Development | LED not sufficiently linked to financial recovery. Weak revenue focus. Poor project packaging. WDA not yet operational | Finalise Waterberg Development Agency (WDA) business case |  |  |  | In-house/PT/DBSA | In-house/PT/DBSA | Manager: Planning & Economic Development | 2027-01-01 | 2027-12-31 | Business case. Council resolution. Implementation roadmap | Platform for future revenue and investment facilitation
|  |  | Prepare catalytic project packaging pipeline for tourism, agriculture, logistics and land-linked opportunities |  |  |  | In-house/PT/DBSA | In-house/PT/DBSA | Manager: Planning & Economic Development | 2027-01-01 | 2027-12-31 | Project concept notes. Investor packs. Funding submissions | Potential PPPs, investment and facilitation income
|  |  | Run structured partner/funder engagement and monetise land-linked opportunities |  |  |  | In-house/PT/DBSA | In-house/PT/DBSA | Manager: Planning & Economic Development | 2027-01-01 | 2027-12-31 | Meeting records. Moues. EOIs | Potential lease income and PPP opportunities
5 | Abattoir | Abattoir is loss-making, downgraded, capacity constrained, and lacks a bankable model. Buildings and equipment in poor condition. Low tariff. | Consider selling the abattoir facilities as a going concern |  |  |  | In-house/PT/DBSA | In-house/PT/DBSA | Manager: Planning & Economic Development | 2027-01-01 | 2027-12-31 | Revenue from sales | Revenue and Cost reduction. Saving of the average expenditure of R8.2m/ year
6 | Municipal Health Service | Current service model has weak cost recovery. Inadequate EHPs. Limited revenue recovery from services. Inadequate monitoring equipment | Develop lawful service-recovery model for inspections, permits, certificates and enforcement |  |  |  | In-house | In-house | Manager: Social Development and Community Development | 2027-01-01 | 2027-12-31 | Service-recovery policy. Fee schedule. Legal review | Target new lawful fee income.
|  |  | Conclude MOUs with universities/stakeholders and plan permanent offices/environmental units |  |  |  | In-house | In-house | Manager: Social Development and Community Development | 2027-01-01 | 2027-12-31 | Signed MOUs. Land/office report. Budget submission | Potential cost relief through partnerships. medium-term capacity benefit
7 | Environmental and Air Pollution | Weak monitoring and enforcement. Environmental unit underdeveloped. Revenue from licensing, fines and compliance charges is not fully realised. AQMP implementation gaps. | Approve and fill Senior Environmental Officer function |  |  |  | In-house | In-house | Manager: Social Development and Community Development | 2027-01-01 | 2027-12-31 | Organogram. Council approval. Appointment letter | Enables future cost recovery
|  |  | Review and gazette by-laws and tariff for environmental compliance fees and charges |  |  |  | In-house | In-house | Manager: Social Development and Community Development | 2027-01-01 | 2027-12-31 | Draft by-law. Legal opinion. Council resolution and gazette | Target medium-term compliance-fee income
|  |  | Strengthen AQMP implementation, inspections and partnerships for climate finance |  |  |  | In-house | In-house | Manager: Social Development and Community Development | 2027-01-01 | 2027-12-31 | AQMP implementation plan. Moues. Funding applications | Potential grant/climate-finance access and reduced compliance risk
8 | Fire Services | Mandatory but inadequately funded service. Staffing, fleet, station and equipment gaps. Weak cost recovery | Develop lawful fire service recovery model for industrial and commercial levies, standby and event fees |  |  |  | In-house/COGSTA | In-house/COGSTA | Manager: Social Development and Community Development | 2027-01-01 | 2027-12-31 | Costing model. Legal review. Tariff proposal. Council item | Target new supplementary revenue. Avoid unfunded expansion
|  |  | Negotiate annual district-local contributions and asset-use arrangements |  |  |  | In-house/COGSTA | In-house/COGSTA | Manager: Social Development and Community Development | 2027-01-01 | 2027-12-31 | Draft Moues/SLAs. Engagement minutes. Funding framework | Potential cost sharing and partial recovery of district fire costs. Potential revenue of about R300k per month to offset the budget deficit (at R1.3m for 2024/25 FY)
|  |  | Implement lower-cost stabilisation measures: mutual aid, volunteers, skid units and Working on Fire (WOF) support |  |  |  | In-house/COGSTA | In-house/COGSTA | Manager: Social Development and Community Development | 2027-01-01 | 2027-12-31 | Moues. training registers. Procurement/support records | Fund through reprioritisation/donations/external support. improves readiness at lower cost
9 | Disaster Management | Inadequately funded core function. Weak technology, staffing, logistics and proactive funding | Prepare funding motivation to Treasury and COGTA and support Local Government Equitable Share (LGES) review for essential services |  |  |  | In-house/COGSTA | In-house/COGSTA | Manager: Social Development and Community Development | 2027-07-01 | 2027-12-31 | Submission letters. Motivation report. Meeting records | Aims to secure external support
PILLAR 3: GOVERNANCE
1 | Information & Communications Technology Governance | Outdated or inadequate IT hardware, infrastructure and software | Continue prioritising upgrading of IT hardware, infrastructure and systems using the funding from COGSTA as well as other budget resources while ensuring that all the ICT applications at the municipality are integrated into the municipality’s financial system. |  |  |  | In-house/COGTA | In-house/COGTA | Director Corporate & Shared Services | 2027-04-01 | 2028-09-20 | ICT Steering Committee Quarterly Reports to Council | Operational efficiency
|  | Business Continuity Plan has not been reviewed. | Update the Business Continuity Plan and other relevant ICT policies as soon as possible after completion of IT hardware, infrastructure and systems upgrades. |  |  |  | In-house | In-house | Director Corporate & Shared Services | 2027-04-01 | 2028-09-20 | Updated Business Continuity Plan and ICT Policies | Operational efficiency
PILLAR 4: INSTITUTIONAL
1 | Employee related cost | High employee related cost expenditure due to salary increase and over-graded positions | Conduct an institutional assessment across all directorates to identify and map redundant, overlapping, or non-core administrative posts. | Stabilize the municipality's cash position and restore longterm fiscal vaibility. |  | In-house | Director: Corporate Services | 2026-07-01 | 2027-06-30 | Reduction of employee related cost as % of total operating expenditure |  | Finalised Job Evaluation
|  |  | Migrate employees to the newly graded TASK salary scales and update the staff establishment to reflect right-sized departmental structures. |  |  | In-house | Director: Corporate Services
|  |  | Identify and formally expunge all non-critical, redundant, and long-vacant unfunded posts (209 positions) from the active organogram. |  |  | In-house | Director: Corporate Services |  |  |  | Monthly payroll reconciliation reports signed off by the CFO
|  |  | Review and reconcile all municipal housing allowance payroll data against the official SALGBC circulars to isolate specific overpayments. |  |  | In-house | Director: Corporate Services |  |  |  | Approved Monthly Section 71 reports (showing actual vs. budgeted expenditure).
|  |  | Convene structured consultations within the LLF with SAMWU and IMATU to present the audit findings, discuss the overpayment corrections, and manage labour relations risk. |  |  | In-house | Director: Corporate Services |  |  |  | Approved Annual Budget (Table A4 and Table SA22).
|  |  | Effect corrected housing allowance caps directly onto the payroll system and initiate recovery processes for un-entitled overpayments where legally viable |  |  | In-house | Director: Corporate Services |  |  |  | Quarterly Section 52(d) reports tabled to Council.
|  |  | Update and revise the internal Municipal Housing Allowance Policy to strictly match standard SALGBC thresholds and framework conditions |  |  | In-house | Director: Corporate Services
2 | Physical verification of the staff | Verification of staff is never conducted unless directed by AG during audit processes. | Draft and adopt an internal SOP that mandates scheduled, quarterly physical headcount verifications and biometric/payroll cross-checks. | Fully secured payroll integrity and proactive prevention of irregular personnel expenditure through institutionalized headcounts. |  | In-house | Director: Corporate Services | 2026-07-01 | 2027-06-30 | Percentage of active payroll staff physically verified against HR records. | Approved Annual Staff Verification Project Plan.
|  |  | Execute automated and physical verification cycles across all municipal directorates, ensuring every employee physically signs in with proof of identity. |  |  | In-house |  |  |  |  | Signed-off verification registers per department.
|  |  | Submit quarterly payroll integrity reports directly to Internal Audit and the Audit Committee for oversight and risk mitigation tracking. |  |  | In-house |  |  |  |  | Signed verification report tabled to Council
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lets include the targeted deficit reduction for the current financial year in line with the suggested expenditure reductions.

## Sustainability Phase
NO | FOCUS AREA SUSTAINABILITY | Baseline Finding/Key Issues | KEY INTERVENTION ACTIVITIES (Deliverables) | RESOURCES REQUIRED | RESOURCES MOBILISED | RESPONSIBLE | START DATE | END DATE | KEY PERFORMANCE INDICATOR | PORTFOLIO OF EVIDENCE | BUDGET PARAMETER/ REVENUE TARGET/ SPENDING LIMIT/ FINANCIAL IMPACT | MUNICIPAL PROGRESS REPORT
[12 empty] | STEPS TAKEN | PROGRESS MADE | FINANCIAL IMPACT | OTHER NOTEWORTHY DEVELOPMENTS
PILLAR ONE: GOVERNANCE
The strategies and activities for this phase will be informed by progress made on the first 2 phases (Rescue and Stabilisation)
PILLAR TWO: INSTITUTIONAL
The strategies and activities for this phase will be informed by progress made on the first 2 phases (Rescue and Stabilisation)
PILLAR THREE: FINANCIAL MANAGEMENT
The strategies and activities for this phase will be informed by progress made on the first 2 phases (Rescue and Stabilisation)
PILLAR FOUR: SERVICE DELIVERY
The strategies and activities for this phase will be informed by progress made on the first 2 phases (Rescue and Stabilisation)