## D1=Contract report 0910
ANNEXURE D 1 : WDM CONTRACTS ENTERED INTO DURING THE 09/10 AS AT 31 MARCH 2013
# | Tender Number | IDP Project # | Project Description | Date Awarded | Service Provider/ Contractor | Amount Awarded | SLA signed | On-site start date | Scope | No. of jobs | SLA completion date | Actual completion Date | SLA Extension | Dpt | Manager`s comment | Challenges
1 | WDM/2008/30 | 15108 | Provision of the banking service | 2009-09-03 | First National Bank | SCHEDULE | 2009-08-31 | 2009-08-31 | Banking Services | 1 | 2014-10-25 | Not yet | None | CFO | Current bank account well managed, bank charges reasonable, prompt service | None
2 | WDM/2009/11 | CO20 | Anti Fraud Hotline | 2009-10-19 | Deloite and Touche | 464997 | 2010-03-12 | 2010-03-15 | Establishing an Anti-Fraud Hotline for WDM | 1 | 2013-03-15 | 2013-03-31 | None | MM | The free Fraud Hotline has been created and the hotline is operational. Contract with Deloitte ended, to be managed internally. | Done
3 | WDM/2009/08 ext | 15168 | Extension of the Insurance Cover | 2009-11-02 | AON SOUTH AFRICA | 356064.32 | 2009-11-02 | 2009-10-30 | Insurance cover for Building combined section, theft, glass, fidelity, personal accident, stated benefits, public liability and motor fleet. | 0 | 2012-11-01 | 2013-01-31 | Yes | CSSS | Extension is until 31 Jan 2013 until finalisation of new tender, which was done and AON was appointed for another 3 year term. | Done
|  |  | TOTAL |  |  | 821061.32