## D1=Contract report 0910
ANNEXURE D 1 : WDM CONTRACTS ENTERED INTO DURING THE 09/10 AS AT 30 JUNE 2012
# | Tender Number | IDP Project # | Project Description | Date Awarded | Service Provider/ Contractor | Amount Awarded | SLA signed | On-site start date | Scope | No. of jobs | SLA completion date | Actual completion Date | SLA Extension | Dpt | Manager`s comment | Challenges
1 | WDM/2008/30 | 15108 | Provision of the banking service | 2009-09-03 | First National Bank | SCHEDULE | 2009-08-31 | 2009-08-31 | Banking Services | 1 | 2014-10-25 | Not yet | None | CFO | Current bank account well managed, bank charges reasonable, prompt service | None
2 | WDM/2009/11 | CO20 | Anti Fraud Hotline | 2009-10-19 | Deloite and Touche | 464997 | 2010-03-12 | 2010-03-15 | Establishing an Anti-Fraud Hotline for WDM | 1 | 2013-03-15 | Not yet | Yes | MM | The free Fraud Hotline has been created and the hotline is operational. | None
3 | WDM/2008/18 ext | 15170, 15203, 17770, 17870 | Extension on Provision of Security Services | 2009-11-02 | Fawcett Security Services | 961199.76 | 2009-02-20 | 2009-10-30 | Deployment of additional Security guards to provide security service | 6 | 2012-02-28 | Not yet | None | CSSS | No updated comment | No updated comment
4 | WDM/2009/08 ext | 15168 | Extension of the Insurance Cover | 2009-11-02 | AON SOUTH AFRICA | 356064.32 | 2009-11-02 | 2009-10-30 | Additional insurance cover for Building combined section, theft, glass, fidelity, personal accident, stated benefits, public liability and motor fleet. | 8 | 2012-11-01 | Not yet | None | CSSS | No updated comment | No updated comment
5 | WDM/2009/10-21 | DIN28 | Donor Funding | 2009-11-02 | Global Business Solutions | 425700 | 2009-11-04 | 2009-11-04 | Develop a Donor/Funding management strategy & source funding on a commission basis. | 2 | 2012-11-03 | Not yet | None | CFO | No business plans are being submitted to Global Business for sourcing funding. | Under utilisation of current service provider available.
|  |  | TOTAL |  |  | 2207961.08
No comment submitted