## D2=Contract report 1011
ANNEXURE D 2 :- WDM CONTRACTS ENTERED INTO DURING 10/11 AS AT 31 MARCH 2012
NO | Tender Number | IDP Project # | Project Description | Date Awarded | Service Provider/ Contractor | Amount Awarded (Vat excl) | SLA signed | On-site start date | Scope | SLA completion date | Actual completion Date | SLA Extension | Dpt | Manager`s comment | Challenges
1 | Limitted Bidding | DUE 43 | Security surveillance cameras | 2010-07-07 | Waterberg Chamber of Commerce | 800000 | 2010-08-05 | 2010-07-08 | Supply and installation of security surveillance cameras for the Waterberg District Municipality | 2011-03-31 | In progress | None | PED | Modimolle section complete. On 17 Nov '11 Bela-Bela Municipality confirmed that they will not be involved in the CCTV Camera Project. | Bela Bela participation
2 | WDM/2008/18 ext | 17770, 17870 | Extension of Security Services to the Lephalale Disaster Centre | 2009-11-02 | Fawcett Security Services | 393264.09 | N/A | 2010-08-04 | Security Services to Lephalale Disaster Centre 24 hours 7 days per week. | 2012-02-20 | In progress | None | CSSS | No updated comment | No updated comment
3 | WDM/2009-10/26 | 15024 | Photocopier machines | 2010-07-06 | Data Master Office Automatic CC | 624129.24 | 2010-08-02 | 2010-08-01 | Operating lease of photocopying machines. | 2013-07-30 | In progress | None | CSSS | No updated comment | No updated comment
4 | WDM2010/11-07 | Per project | Publication of tenders,vacant posts and other related notices | 2010-11-25 | Human Communication | Price schedule | 2010-12-01 | 2010-12-01 | Publication of tenders,vacant posts and other related notices of WDM in various newspapers | 2013-11-30 | In progress | None | BTO | Service satisfactory | None
5 | WDM2010/11-14 | DM-014 | Supply of 4x4 open bush pumper | 2010-11-25 | Fire Raiders | 747565.9386 | 2010-12-07 | 2010-11-29 | Manufacturing and supply of 4x4 open deck bush pumper for Thabazimbi | 2011-11-29 | 2011-07-29 | None | Disaster | Project completed within time frame | None
6 | WDM/2010-11/13 | DM-08 | Supply of 4x4 major pumper | 2010-11-25 | Marce Fire Fighting | 3494193.5965 | 2011-01-05 | 2011-01-03 | Manufacturing ,supply & registry of a 4x4 rescue major pumper for Mogalakwena | 2011-11-03 | 2011-12-03 | 03-Nov-11 to 03- Dec-11 (1 month) | Disaster | Fire truck delivered December 2011. Awaiting final registration and road worthy licensing documents. | Vehicle delivered but final payment withheld until registration is complete.
7 | WDM/2010-11/12 | UE029 | Upgrading of the WDM abattoir | 2010-12-22 | Immaculate Management Services | 3754678.97 | 2011-01-19 | ? | Upgrading & refurbishment of the existing WDM abattoir (Phase 2). | Cancelled | Cancelled | None | ID | Contract was cancelled due to non-delivery | approval obtained to utilise subcontractors
8 | WDM/2010-11/11 | SE013 | Development of the emission inventory | 2010-12-22 | Bembani Sustainability training (Pty)Ltd | 317500 | 2011-01-20 | 2011-01-17 | Develop emissions inventory system and forcasting techniques for all 4 source categories. | 2011-06-30 | 2011-06-01 | None | SDS | The after care of 6 months has been completed | None
9 | WDM/2010-11/23 | DM-24 | Develop Early Warnings system And the determination of flood lines At Mabaleng, Modimolle | 2011-03-01 | The Sysman Group | 600004.8 | 2011-03-14 | 2011-03-08 | Investigation of the causes of floods at Mabaleng settlements and the determination of flood lines along the Sand River for 1:100 year | 2011-03-08 | 2011-07-08 | Yes, from 09-Jul-11 to 31-Jul-11) | Disaster | Project completed | None
10 | WDM/2010-11/24 | DM-22 | Developing incident management System | 2011-03-01 | Disaster Risk Management | 299022 | 2011-03-14 | 2011-03-14 | Developing incident management System for the MDC & LDC | 2011-03-14 | 2011-08-14 | Yes, from 15-Jul-11 to 15 Aug-11) | Disaster | Project complete with 3X year maintanance contract | None
11 | WDM/2010-11/26 | DM-26 | Compatible Information Management, Communication and Dissemination System | 2011-03-01 | Disaster Risk Management | 777751.32 | 2011-03-14 | 2011-03-14 | Developing Compatible Information Management, Communication and Dissemination System for MDC & LDC which is linked to mogalakwena and Thabazimbi Fire stations | 2011-03-14 | 2011-07-14 | Yes, from 15-Jul-11 to 15 Aug-11) | Disaster | Project complete | None
12 | WDM 10/11 | 15126 | GRAP 17 measurement of assets | 2011-04-01 | Ducharme Consulting | 158600 | 2011-04-01 | 2011-04-01 | Staff training on assets verification & impairment indicators and residual values. | 2011-06-30 | 2011-08-31 | None | BTO | Completed | None
13 | WDM/2010/11-25 | DM027 | Risk reduction measures for drought | 2011-05-31 | M. W. Sebela Boreholes cc | 619230.78 | 2011-06-24 | Not yet | Drilling and fully equipping 6X boreholes at Mogalakwena, Lephalale and Thabazimbi Local Municipalities. | 2011-10-07 | Not yet | 2012-03-19 | Disaster | Contractor passed away October 2011. 4 Boreholes completed. Outstanding - last 2 Boreholes at Thabazimbi (Regorogile) and Mogalakwena (Mapela). Project expiry date was 07 Oct 2011, extended to Dec 2011. Meeting held with family, extended by further 2 months (now 5 monts total) from 18 January 2012 to 19 March 2012. | The main Contractor Mr. Willem Sebela passed away on 5 Oct 11.
12585940.7351