## Rollover (hidden)
Annexure C
PROJECT STATUS REPORT - ROLLED OVER PROJECTS
2011-10-24
PROJ NO | PROJECT NAME | PROJ YEAR | Operating | Capital | BUDGET AMOUNT | PAID P/YEARS | UNSPENT AT 30 JUNE 2011 | SPENT 11/12 YEAR | REMAINING | Savings Oct 2011 | LAST PMT | RESP MAN | COMMENTS BY MANAGER
1 | Municipal Environmental Health & Environmental Management
SE-05 | Waste Management - development of landfill sites - initiation of partnerships | 2011 |  |  | 926359 | 390674.72 | 535684.28 | 535684.28 | 0 |  | 2011-08-24 | SDCS | Project completed.
SE-13 | Air Quality Emissions Inventory | 2011 | 320735 |  | 320735 | 288984.92 | 31750.08 | 0 | 31750.08 |  |  | SDCS | Project completed in June 2011, the remaining funds is for aftercare.
[5 empty] | 1247094 | 679659.64 | 567434.36 | 535684.28 | 31750.08
2 | DISASTER MANAGEMENT
DM-02 | Lephalale Disaster Centre Environmental Impact Assessment | 2010 |  | 36555 | 2567202 | 2530647 | 36555 | 36555 | 0 |  | 2011-08-17 | PED | Project complete.
DM-08 | Mogalakwena - new Rescue Pumper | 2011 |  | 3497733 | 3497733 | 3539.71 | 3494193.29 | 1747096.8 | 1747096.49 |  | 2011-10-20 | MMO | The 50% payment after the 1st site inspection was conducted by Messrs. D M Sithole, T van Deventer and J vander Merwe in the USA, Florida State, Ocala E-ONE Plant. The 4X4 Major Urban Rescue Pumper is 100% complete waiting to be shipped to South Africa.
DM-17 | Bela Bela Skid Units & Equipment for main fire station, Masakhane, Pienaarsrivier & Rapotokwane | 2011 |  | 1285759 | 1285759 | 665078.59 | 620680.41 | 620680.41 | 0 |  | 2011-10-20 | MMO | Project complete.
DM-22 | Incident Management System | 2011 |  | 307218 | 307218 | 207217.6 | 100000.4 | 100000.4 | 0 |  | 2011-08-15 | MMO | Project complete.
DM-23 | Disaster Risk Awareness Program | 2011 | 119780 |  | 119780 | 107279.27 | 12500.73 | 12500.73 | 0 |  | 2011-07-29 | MMO | Project complete.
DM-24 | Early Warning System of Flood lines | 2011 |  | 614218 | 614218 | 403649.17 | 210568.83 | 156226.32 | 54342.51 |  | 2011-09-28 | MMO | Project complete.
DM-25 | Disaster Risk Management Toll Free Number & promotional signage | 2011 | 500000 |  | 500000 | 2217.6 | 497782.4 | 1630.86 | 496151.54 |  | 2011-09-26 | MMO | Limitted bidding approved by MM for appointing Telkom SA for the development of a Toll Free number. Delays are caused by Telkom. Promotional Signage's re-advert closed on 29 August 2011 , was Evaluated on 06 October 2011 and awaiting to be tabled before the Bid Adjudication Committee (BAC).
DM-26 | Information management, communication & dissemination system | 2011 |  | 900000 | 900000 | 355332.26 | 544667.74 | 409514.01 | 135153.73 |  | 2011-08-29 | MMO | The project is completed. final invoice paid. This includes a 3 years maintanance/support services to be done for the UNITI System by Disaster Management Solutions (DMS) .
DM-27 | Risk reduction measures for drought | 2011 | 624987 |  | 624987 | 5757.31 | 619229.69 | 309615.39 | 309614.3 |  | 2011-09-20 | MMO | The Contractor Mr. M W Sebela passed away on 5 October 2011. Thus far 2 Boreholes at Mokopane (Segole & Sodoma) and 2 Boreholes at Lephalale (Ga-Seleka & Madibaneng) were completed. They were working on completing the last 2 Boreholes at Thabazimbi (Regorogile) and Mogalakwena (Mapela). Project expiry date was Friday, 07 October 2011, application for 1X month extension period received 3 October was approved by MM before his sudden death. Memo written to MM 19 October 2011 for his further advice and direction in this regard to ensure that this project if fully completed.
DM-29 | Groblersbrug Port of Entry / Tom Burke Satellite Fire Station - Water Trailer & Equipm & Steenbokpan & Bulgerivier Satellite Fire Station - Water Trailer & Equipment & Villages / Witpoort Fire Station - Equipment | 2011 |  | 242600 | 242600 | 62679.72 | 179920.28 | 0 | 179920.28 |  |  | MMO | Invitation was placed on the WDM notice board for the 2X Ultra High Pressure Fire Fighting Skid Units for Lephalale local municipality, SCM evaluated, but 90Days validity period expired before project was approved. Project has been re-advertised on WDM notice board.
[5 empty] | 10659497 | 4343398.23 | 6316098.77 | 3393819.92 | 2922278.85
3 | Fire Fighting
IN-22 | Upgrading of existing trained volunteers to minimum requirements for full time fire fighters (phase 2) | 2011 | 100000 |  | 100000 | 0 | 100000 | 96875 | 3125 |  | 2011-09-08 | CSSS | The service provider has been appointed to do the training and the shortfall will be defrayed from the MSIG vote and implementation commenced in October 2011.
[5 empty] | 100000 | 0 | 100000 | 96875 | 3125
4 | Local Economic Development & Tourism
UE-34 | Feasibility Study of the Wildlife Centre | 2008 | 399255.63 |  | 3000000 | 2600744.37 | 399255.63 | 0 | 399255.63 |  |  | PED | Feasibility Study complete. PED has requested permission from OTP to transfer the remaining savings to Beautification of Vaalwater project, no response yet.
UE-42 | Signage | 2009 & 2010 | 79867.08 |  | 803350 | 723482.92 | 79867.08 | 0 | 79867.08 |  |  | PED | Project complete. The savings will be used for Billboard hire, completed the specifications and ready for notice board and website advert.
UE-43 | Modimolle & Bela Bela Security Cameras | 2010 | 520000 |  | 800000 | 280000 | 520000 | 60000 | 460000 |  | 2011-08-10 | PED | Modimolle Security Cameras installed and operational. Still awaiting Bela Bela Municipality to come on board for installation of cameras in their town. PED sent them a letter requesting their project plan, no response yet. WDM's MM will facilitate a meeting with Bela Bela Municipality's MM to come up with the wayfoward.
[5 empty] | 4603350 | 3604227.29 | 999122.71 | 60000 | 939122.71
5 | ROADS & STORM WATER
RS-21 | Completion of Modimolle Ring Road in Phagameng - 1,603km | 2010 & 2011 | 2395734.35 |  | 2690081 | 294346.65 | 2395734.35 | 1827123.3 | 568611.05 |  | 2011-10-17 | ID | Project Completed. Amount outstanding is for contingencies until snaglist is completed plus 5% retention for 12 months.
RS-40 | Bela Bela Paving - Radium - 1.3km | 2011 | 2740093 |  | 2740093 | 920455.9 | 1819637.1 | 1592047.27 | 227589.83 |  | 2011-09-26 | ID | Project Completed. Amount outstanding is for contingencies until snaglist is completed plus 5% retention for 12 months.
RS041 | Mogalakwena Streets tarring | 2010 & 2011 |  |  | 3147912 | 448277.62 | 2699634.38 | 1097202.77 | 1602431.61 |  | 2011-10-04 | ID | Project Completed. Awaiting for last invoice and remaining amount outstanding is for contingencies until snaglist is completed plus protective clothing plus 5% retention for 12 months.
[5 empty] | 8578086 | 1663080.17 | 6915005.83 | 4516373.34 | 2398632.49
6 | Municipal Support & Institutional Development
IN-17 | Procurement of Movable Assets | 2011 |  | 574090 | 574090 | 545819.53 | 28270.47 | 28270.47 | 0 |  | 2011-07-26 | CSSS | Project complete.
IN-24 | Performance Management System (PMS) | 2011 | 938385 |  | 938385 | 861679.7 | 76705.3 | 0 | 76705.3 |  |  | MMO | Still awaiting firnal invoices to be submitted by IPM for 10/11 year work done.
IN-27 | Integrated Financial Management System | 2010 & 2011 |  | 6273639.4 | 6286945 | 13305.6 | 6273639.4 | 0 | 6273639.4 | 31000 |  | CSSS | Appointed Munsoft for supply of the IFMS for WDM, Bela Bela & Thabazimbi following SCM Regulations 32 procurement using the public tender of another organ of state in September & October 2011. Modimolle LM has also appointed Munsoft for their IFMS in June 2011. Approached Lephalale LM for the next phase of the roll-out, still awaiting confirmation.
IN-34 | Geographic Information System (GIS) | 2011 |  | 649806 | 649806 | 589266.1 | 60539.9 | 29539.5 | 31000.4 | -31000 | 2011-09-26 | CSSS | Project complete. Remaining funds to be transferred to IFMS to procure Disaster Modules for LMs. There is currently a shortfall on IFMS for this purpose.
IN-36 | Financial Strategy | 2011 | 500000 |  | 500000 | 0 | 500000 | 0 | 500000 |  |  | BTO | A number of institutions were contacted for specs since municipalities haven't done this yet. Specifications has been sourced, all will be reviewed & combined to our needs. Since the project was recommended by IPM, we will first review whether there is still a need to continue with this project.
[5 empty] | 8949226 | 2010070.93 | 6939155.07 | 57809.97 | 6881345.1
7 | ABATTOIR
UE-29 | Upgrading of the abattoir (phase 2) | 2011 |  | 2931934 | 2931934 | 1685161.19 | 1246772.81 | 598575.32 | 648197.49 |  | 2011-08-15 | ID | Contract for the main contractor has been terminated. Sub contractors completing the outstanding works.
[5 empty] | 2931934 | 1685161.19 | 1246772.81 | 598575.32 | 648197.49
8 | COMMUNITY PARTICIPATION & GOOD GOVERNANCE
CO-20 | Anti-fraud Hotline | 2010 & 2011 | 186507.73 |  | 300000 | 113492.27 | 186507.73 | 0.02 | 186507.71 |  | 2011-06-24 | MMO | The invoices for the monthly remainder for June, July, August,September,October 2011 has been submitteed for processing
CO-24 | District Batho Pele Activities | 08&09 | 351340 |  | 351340 | 0 | 351340 | 1529 | 349811 |  | 2011-10-20 | EMO | Project completed
[5 empty] | 651340 | 113492.27 | 537847.73 | 1529.02 | 536318.71
9 | LAND
LA-12 | CBD Development Plan & Implementation (Bela Bela, Modimolle & Mogalakwena) | 2011 | 1339649 |  | 1339649 | 1233113.42 | 106535.58 | 106535.09 | 0.49 |  | 2011-07-13 | PED | Project complete.
[5 empty] | 1339649 | 1233113.42 | 106535.58 | 106535.09 | 0.49
12 | SPORTS,ARTS AND CULTURE
SC-07 | Co-ordination of Sports, Arts and Culture | 2010 | 238716.35 |  | 1244551 | 1005834.65 | 238716.35 | 238716.35 | 0 |  | 2011-08-24 | EMO | Project complete.
[5 empty] | 1244551 | 1005834.65 | 238716.35 | 238716.35 | 0
|  |  | 11355050.14 | 17313552.4 | 40304727 | 16338037.79 | 23966689.21 | 9605918.29 | 14360770.92
28668602.54
| TOTAL ROLLOVER |  |  |  | 23966689.21
| TOTAL SPENT UP TO 24 October 2011 |  |  |  | 9605918.29
| ACTUAL % SPENT |  |  |  | 40.08%

## Annexuere D3
ANNEXURE D 3 :- WDM CONTRACTS ENTERED INTO DURING 11/12 AS AT 30 SEPTEMBER 2012
# | Tender Number | PROJ NO | PROJECT NAME | PROJ YEAR | Dpt | Operating | Capital | 10/11 Roll Over | 11/12 IDP | Total Budget | PAID 11/12 YEAR | REMAINING | Committed | Motivated for 12/13 roll over | Date Awarded | Service Provider/ Contractor | Amount Awarded (Vat excl) | Amount Awarded (Vat incl) | SLA signed | On-site start date | Scope | SLA completion date | Actual completion Date | SLA Extension | Dpt | Manager`s comment | Challenges
1 | WDM/2011-12/08 | DM032 | Fire Station Standby Generator Refurbishment - Mogalakwena | 2012 | Disaster |  | 0 |  | 96631 | 96631 | 1630.86 | 95000.14 | 95000 |  | 2011-11-22 | Marce Marketing CC | 93840.19 | 82315.9561 | 2012-02-06 | 3 months | Delivery of a refurbished of a Toyota Dyna to WDM | 2012-04-06 | 2012-08-25 | Yes | Disaster | Project completed | None
2 | WDM/2011-12/13 | DM036 | Thabazimbi Water Tank | 2012 | Disaster |  | 0 |  | 1097231 | 1097231 | 1630.86 | 1095600.14 | 1095600 |  | 2011-11-22 | Fire and Emergency Vehicle (Pty) Ltd | 1248984 | 1095600 | 2012-02-06 | 7 months | Delivery of a 4x2 6000L water tanker to WDM | 2012-08-06 | 2012-10-19 | Yes | Disaster | Project completed | None
3 | WDM/2011-12/11 | DM 17 & 37 | Bela Bela Medium Pumper Vehicle & Equipment | 2012 | Disaster |  | 0 |  | 1691240 | 1691240 | 846435.26 | 844804.74 | 844804 |  | 2011-11-22 | Fire Raiders (Pty) Ltd | 1926154.03 | 1689608.7982 | 2012-02-08 | 7 Months | Delivery of a 4x4 double cab medium pumper & mounted fire fighting Equipments to WDM,registration & road worthy licensing of the trailer | 2012-08-08 | 2012-10-19 | Yes | Disaster | Project completed | None
4 | WDM/2011-12/14 | DM038 | Modimolle - Medium Double Cab Rapid Intervention Vehicle | 2012 | Disaster |  | 0 |  | 1138152 | 1138152 | 569890.94 | 568261.06 | 568260 |  | 2011-12-13 | Fire Raiders (Pty) Ltd | 1295632.97 | 1136520.1491 | 2012-02-08 | 7 Months | Delivery of a 4x2Double cab with fire fighting vehicle and it must be registered & road worthy licensed to WDM | 2012-08-08 | 2012-09-28 | Yes | Disaster | Project completed | None
5 |  | UE034 | Feasibility Study of the Wildlife Centre / Vaalwater Beautification (project Wildlife Study) | 2012 | PED | 789744 |  | 399255.63 | 450000 | 849255.63 | 59511.37 | 789744.26 | 390489 | 789744 | [12 empty] | None
6 | LIMITED BIDDING | UE040 | Waterberg Biosphere Meander Reserve | 2012 | PED | 100000 |  |  | 200000 | 200000 | 123933.89 | 76066.11 | 0 | 100000 | 2011-08-24 | Waterberg Biosphere Reserve | 100000 | 100000 | 2011-10-10 | 2012-07-01 |  | 2013-06-30 | 2013-06-30 | No | PED | None | None
7 | WDM/2011-12/26 | RS021 | Completion of Modimolle Ring Road | 2012 | ID |  |  | 2395734.35 | 2200000 | 4595734.35 | 2455011.97 | 2140722.38 | 1753172 |  | 2012-05-08 | Mafafo Building Construction | 1726310 | 1967993 | 2012-05-22 | 2012-05-22 |  | 2012-09-22 | 2012-09-22 | No | ID | None | None
8 | WDM/2011-12/25 | RS040 | Completion of Bela Bela Street Paving | 2012 | ID |  |  | 1819637.1 | 1500000 | 3319637.1 | 2096511.91 | 1223125.19 | 1047827 |  | 2012-05-08 | Mmamokgoshi Construction | 1596610 | 1820136 | 2012-05-23 | 2012-05-23 |  | 2012-09-23 | 2012-09-23 | No | ID | None | None
10 | LIMITED BIDDING | IN024 | PMS | 2012 | MM |  |  | 76705.3 | 1662000 | 1738705.3 | 1433848.3 | 304857 | 304065 |  | 2012-02-24 | Institute for Performance Management | 1661208 | 1893777 | 2011-05-19 | 2011-11-30 |  | 2012-06-30 | 2012-09-30 | Yes | OMM | None | None
11 | LIMITED BIDDING | IN027 | Integrated Financial Management System | 2012 | CSSS |  |  | 6273639.4 | 2000000 | 8273639.4 | 4201801.89 | 4071837.51 | 0 | 4000000 | 2011-09-07 | Munsoft (Pty) Ltd | 1593546 |  | 2012-11-01 | 2012-11-01 |  | 2032-10-31 | Not yet | No | BTO | Project successful | None
12 | ORGAN OF STATE | IN035 | Lephalale Municipal Turnaround Strategy Support | 2012 | MM |  |  |  | 850000 | 850000 | 323575.5 | 526424.5 | 96424.5 |  | 2012-04-04 | Lephalale Municipality | 420000 | 420000 | 2012-04-13 | 2012-06-30 |  | 2012-08-13 | 2012-11-30 | Yes | OMM | None | None
13 | ORGAN OF STATE | IN041 | District Wide VPN Network | 2012 | CSSS |  |  |  | 1700000 | 1700000 | 0 | 1700000 | 0 | 1700000 | 2012-06-28 | SITA | 4640667 | 5290360 | 2012-06-28 | 2012-07-01 |  | 2015-06-30 | 2015-06-30 | No | CSSS | None | None
14 | WDM/2011-12/21 | CO009 | Communication | 2012 | EMO |  |  |  | 450000 | 450000 | 18030.86 | 431969.14 | 431644 |  | 2012-11-22 | 7th Question Marketing and Communications | 431644 | 431644 | 2012-02-08 | 2012-02-08 |  | 2013-01-08 | 2013-01-08 | No | OEM | Project stalled | adherence to specifications
15 | LIMITED BIDDING | CO020 | Anti-fraud helpline | 2012 | MM |  |  | 186507.73 | 150000 | 336507.73 | 79824.28 | 256683.45 | 218673 | [13 empty] | None
16 | WDM/2011-12/28 | IN039 | IT Audit | 2012 | MM |  |  |  | 500000 | 500000 | 308862.72 | 191137.28 | 0 |  | 2012-05-08 | Sema Integrated Solutions | 393145 | 448185 | 2012-05-31 | 2012-04-06 |  | 2012-08-30 | 2012-08-30 | No | OMM | None | None
17 | WDM/2011-12/22 AND WDM/2011-12/23 | LA012 | CBD Development Plan & implementation (Mookg & Thab) Roll over - Bela Bela, Modi & Mog | 2012 | PED |  |  | 106535.58 | 1000000 | 1106535.58 | 613176.7 | 493358.88 | 318509 |  | 2012-12-20 | Joint Venture MOK Development Consultants and Plan and Associates | 818509 | 993100 | 2012-02-16 | 2012-02-16 |  | 2012-08-16 | 2012-08-16 | No | PED | None | None
17946250.19
Formulas:
Actual completion Date = [SLA completion date]
On-site start date = [SLA signed]