## Q4
ANNEXURE E:-PROJECT PROCUREMENT PLANNING TEMPLATE :2011/2012 FINANCIAL YEAR AS AT 30 JUNE 2012
Priorities | Project no. | PROJECT NAME | Dept | Project Manager | Department | Approved Budget | Method of Procurement | TOR/ Quote/ Plan Submission Date | Date for BSC Meeting | Advert Date | Advert closing date | BEC Meeting date | BAC Meeting date | Appoint-ment date | Anticipated SLA signing date | Implementation starting date | Completion date | Challenges | Procurement Process Completed
10/11 Roll Overs
| DM-29 | Groblersbrug Witpoort Satellite Fire Station - Equipment | Disaster | Moses / Dan |  | 179920.28 | Notice Board | 2011-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Was re-advertised in October 2011 due to expiry of validity period | No
| UE-34 | Feasibility Study of the Wildlife Centre | PED | Mike |  | 399255.63 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Awaiting permission from OTP to utilised funds for Vaalwater Beautification | No
| IN-27 | Integrated Financial Management System | BTO | Nadine |  | 6273639.4 | S32 organ of state | N/A | N/A | N/A | N/A | N/A | 2011-10-20 | 2011-09-07 | 2011-11-03 | 2011-11-03 | 2012-06-30 | None | Yes
| IN-36 | Financial Strategy | BTO | Nadine |  | 500000 | Tender | 2011-11-30 | 2011-12-05 | 2011-12-09 | 2011-12-23 | 2012-01-09 | 2012-01-16 | 2012-01-20 | 2012-01-31 | 2012-02-01 | 2012-05-30 | Drafting specifications as no benchmark is available | No
1 |  | Municipal Environmental Health & Environmental Management
| SE015 | Review Air Quality Management Plan | SDCS | Stanley | SDCS | 300000 | TENDER | 2011-07-22 | 2011-08-10 | 2011-08-14 | 2011-09-02 | 2011-10-03 | 2011-11-09 | 2011-09-07 | 2011-09-14 | 2011-10-01 | 2012-03-31 | Possibilities for DEA to embark on the same project. | No
| SE016 | Dispersion modelling | SDCS | Stanley | SDCS | 250000 | TENDER | 2011-07-22 | 2011-07-10 | 2011-08-14 | 2011-09-02 | 2011-10-03 | 2011-11-09 | 2011-09-07 | 2011-09-14 | 2011-10-01 | 2012-03-31 | None | No
| SE017 | Development of Mabatlane landfill site | SDCS | Rubeen | SDCS | 1750000 | TENDER | 2011-07-22 | 2011-07-29 | 2011-09-18 | 2011-10-07 | 2011-11-02 | 2011-11-09 | 2011-09-07 | 2011-09-14 | 2011-10-01 | 2012-03-31 | Service Provider has been appointed. | Yes
| SE011 | Training of Green Scorpions | SDCS | Lily | SDCS | 50000 | Quotes | 2012-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-05-31 | 2012-12-31 | None | No
| SE012 | Arbor Day Programme | SDCS | Lily | SDCS | 10000 | Quotes | 2011-09-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-09-30 | 2011-10-30 | None | No
| SE014 | Working for Water Programme | SDCS | Lily | SDCS | 50000 | Quotes | 2012-03-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-03-30 | 2012-04-30 | None | No
2410000
2 |  | Disaster Management
| DM030 | Purchase of Fire Engine for high rise buildings - LDC | Disaster | Moses | Disaster | 3800000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-25 | 2011-10-05 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Specifications to be reworked - insufficient budget. | No
| DM031 | Purchase of Hazmat Trailer - LDC | Disaster | Moses | Disaster | 350000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-26 | 2011-10-05 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Service Provider has been appointed and SLA has been signed. | Yes
| DM029 | Witpoort Fire Station Equipment - mobile office LLM | Disaster | Moses | Disaster | 150000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-19 | 2011-08-25 | 2011-11-09 | 2011-08-31 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Notice board evaluation completed, to be approved | No
| DM032 | Fire Station Standby Generator Refurbishment - Mog | Disaster | Moses | Disaster | 100000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-25 | 2011-10-05 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Service Provider has been appointed and SLA has been signed. | Yes
| DM033 | Refurbishment of Toyota Dyna for training - Mogalakwena | Disaster | Moses | Disaster | 100000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-25 | 2011-10-04 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Same as above | Yes
| DM034 | Refurbishment of Unimog Fire Engine - Mogalakwena | Disaster | Moses | Disaster | 300000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-25 | 2011-10-04 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Same as above | Yes
| DM011 | Mogalakwena Equipment | Disaster | Moses | Disaster | 1300000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-26 | 2011-10-05 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Same as above | Yes
| DM014 | Thabazimbi Equipment | Disaster | Moses | Disaster | 650000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-26 | 2011-10-05 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Limited bidding - evaluation report was reffered back to BEC by BAC on the meeting of 22 June 2012. | No
| DM035 | Thabazimbi Hazmat Trailer | Disaster | Moses | Disaster | 350000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-26 | 2011-10-05 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Service Provider has been appointed and SLA has been signed. | Yes
| DM036 | Thabazimbi Water Tank | Disaster | Moses | Disaster | 800000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-25 | 2011-10-05 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Same as above | Yes
| DM016 | Mookgophong - repair of Toyota Landcruiser plus new equipment | Disaster | Moses | Disaster | 400000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-25 | 2011-10-05 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Same as above | Yes
| DM037 | Bela Bela - Medium Pumper vehicle | Disaster | Moses | Disaster | 1600000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-25 | 2011-10-05 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Same as above | Yes
| DM017 | Bela Bela Equipment | Disaster | Moses | Disaster | 250000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-19 | 2011-08-25 | 2011-08-29 | 2011-08-31 | 2011-09-07 | 2011-09-01 | 2012-03-31 | Same as above | Yes
| DM038 | Modimolle - Medium Double Cab Rapid Intervention Vehicle | Disaster | Moses | Disaster | 1200000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-25 | 2011-10-05 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Same as above | Yes
| DM006 | Modimolle Equipment | Disaster | Moses | Disaster | 250000 | TENDER | 2011-07-22 | 2011-08-01 | 2011-08-07 | 2011-08-26 | 2011-10-05 | 2011-11-09 | 2011-11-18 | 2011-12-05 | 2011-09-01 | 2012-03-31 | Limited bidding - evaluation report was reffered back to BEC by BAC on the meeting of 22 June 2012. | No
11600000
3 |  | Local Economic Development & Tourism
| UE031 | Co-ordination of district wide LED | PED | Mike M | PED | 50000 | On going | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-06-30 | None | No
| UE038 | Tourism | PED | Betty | PED | 650000 | Quotes | 2011-10-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-02-28 | 2011-06-30 | None | No
| UE040 | Waterberg Biosphere Meander Reserve | PED | Betty | PED | 100000 | Co-funding -BAC ITEM | 2011-07-28 | N/A | N/A | N/A | N/A | 2011-07-28 | N/A | N/A | N/A | 2011-06-30 | None | No
| UE041 | WEDA | PED | Mike M | PED | 1500000 | On going | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-06-30 | None | No
| UE034 | Vaalwater Beautification (project Wildlife Study)-Signage Board | PED | Betty | PED | 450000 | Tender & Quotes | 2011-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-03-31 | Still need consultation with LM`s & to be done after Mabatlane`s street construction is completed. | No
| UE047 | Bela Bela Flea Market | PED | Betty | PED | 250000 | Co-funding with Bela -Bela | 2011-10-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-12-31 | Evaluation Report will be presented in the next BAC Meeting | No
3000000
4 |  | Municipal Roads & Stormwater
| SA032 | Mookgophong Township sewer connection (Consultant& Contractor) | ID | Jacky | ID | 3000000 | Tender | 2011-07-22 | 2011-07-28 | 2011-08-07 | 2011-08-26 | 2011-08-30 | 2011-09-02 | 2011-09-07 | 2011-09-14 | 2011-10-01 | 2012-03-31 | The project has been re-advertised and is at the evaluation stage. | No
| RS021 | Completion of Modimolle Ring Road (Contractor) | ID | Jacky | ID | 2200000 | Extension & Tender | 2011-07-31 | 2011-08-31 | 2011-09-04 | 2011-09-23 | 2011-09-26 | 2011-10-20 | 2011-10-01 | 2011-10-07 | 2011-10-01 | 2011-10-30 | Service Provider has been appointed and SLA has been signed. | Yes
| RS040 | Completion of Bela Bela Street Paving (Contractor) | ID | Jacky | ID | 1500000 | Extension & Tender | 2011-07-31 | 2011-08-31 | 2011-09-04 | 2011-09-23 | 2011-09-26 | 2011-10-20 | 2011-10-01 | 2011-10-07 | 2011-10-01 | 2011-08-30 | Service Provider has been appointed and SLA has been signed. | Yes
| RS041 | Completion of Khutsong Street in Mahwelereng (Phase 2 )(Contractor) | ID | Jacky | ID | 1500000 | Extension & Tender | 2011-07-31 | 2011-08-31 | 2011-09-04 | 2011-09-23 | 2011-09-26 | 2011-09-29 | 2011-10-01 | 2011-10-07 | 2011-10-01 | 2011-09-30 | Tenderd received have been evaluated and will be presentd in the next BAC meeting. | No
8200000
5 |  | Municipal Support & Institutional Development
| IN024 | PMS | MM | Phineas | CSSS | 1662000 | Extension | Quote | N/A | N/A | N/A | N/A | N/A | 2011-10-25 | 2011-11-11 | 2011-07-01 | 2012-06-30 | None | Yes
| IN027 | IFMS | BTO | Phineas & Nadine | CSSS | 1500000 | S32 organ of state | N/A | N/A | N/A | N/A | N/A | 2011-10-20 | 2011-09-07 | 2011-11-03 | 2011-11-03 | 2012-06-30 | Confirmation from Mookgophong & Lephalale for participating in the tender roll-out | Yes
| IN017 | Procurement of movable assets | CSSS | Phineas & Bob | CSSS | 1200000 | Tender & Quotes | 2011-07-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | None | No
| IN017 | Procurement of mayoral car | CSSS | Phineas | CSSS |  | Tender | 2011-07-09 | 2011-07-12 | 2011-07-11 | 2011-07-19 | 2011-07-21 | 2011-07-29 | 2011-08-17 | 2011-11-05 | 2011-09-01 | 2011-09-01 | None | Yes
| IN021 | Procurement of IT equipment | CSSS | Keoma | CSSS | 1103000 | Tender& Quotes | 2011-07-22 | 2011-07-28 | 2011-08-07 | 2011-08-26 | 2011-08-30 | 2011-09-02 | 2011-09-07 | 2011-09-14 | 2011-10-01 | 2012-03-31 | None | No
| IN035 | Lephalale Municipal Turnaround Strategy Support | MM | Mokopane & Phineas | MM | 1000000 | Organ of State /Quotes | On going | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-05-30 | None | No
| IN040 | Council Chamber Recording System | CSSS | Bob & Phineas |  | 500000 | S32 organ of state | N/A | N/A | N/A | N/A | N/A | N/A | ? | ? | ? | ? | Service Provider has been appointed through S32 and SLA has been signed. | Yes
| IN043 | Installation of CCTV Cameras | CSSS | Bob & Phineas |  | 500000 | S32 organ of state | N/A | N/A | N/A | N/A | N/A | N/A | ? | ? | ? | ? | Service Provider has been appointed through S32 and SLA has been signed. | Yes
| IN041 | District Wide VPN Network | CSSS | Keoma | CSSS | 1700000 | Tender | 2011-07-22 | 2011-07-28 | 2011-08-07 | 2011-08-26 | 2011-08-30 | 2011-09-02 | 2011-09-07 | 2011-09-14 | 2011-10-01 | 2012-03-31 | None | No
| IN042 | Procurement of Diesel Generator | CSSS | Phineas | CSSS | 500000 | Tender | 2011-07-22 | 2012-01-23 | 2012-01-29 | 2012-02-17 | ? | ? | ? | ? | ? | ? | The project has been re-advertised and is at the evaluation stage. | No
9665000
6 |  | Communicity Participation & Good Governance
| CO009 | Communication (Newsletter) | EMO | Pat | EMO | 450000 | Tender | 2011-07-22 | 2011-07-26 | 2011-08-07 | 2011-08-29 | 2011-10-03 | 2011-11-09 | 2011-09-07 | 2011-09-14 | 2011-10-01 | 2012-06-30 | Service Provider has been appointed and SLA has been signed. | Yes
| CO011 | District Public Participation - EMO | EMO | Peter | EMO | 1000000 | Quotes | On Going | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-30 | None | No
| CO012 | District Public Participation - IDP | MM | Lindiwe | MM | 400000 | Quotes | On Going | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-30 | None | No
| CO014 | Learning & sharing (twinning agreement) | EMO | Pat | EMO | 100000 | Quotes | On-Going | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-11-30 | None | No
| CO020 | Anti-fraud helpline | MM | Malose | MM | 150000 | Awarded | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-30 | None | Yes
| CO013 | Production of Diaries for Cllrs & Traditional Leaders | EMO | Pat | EMO | 30000 | Quotes | 2011-07-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-10-30 | None | No
| CO017 | HIV/AIDS Awareness Programs | EMO | Malowa | EMO | 150000 | Quotes | 2011-07-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-30 | None | No
| CO016 | Gender & Elderly People Programs | EMO | Malowa | EMO | 250000 | Quotes | 2011-07-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-30 | None | No
| CO019 | Youth Programs | EMO | Malowa | EMO | 200000 | Quotes | 2011-07-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-30 | None | No
| CO018 | People with Disability Programs | EMO | Peter | EMO | 200000 | Quotes | 2011-07-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-30 | None | No
| IN039 | IT Audit | MM | Malose | MM | 500000 | TENDER | 2011-07-22 | 2011-08-11 | 2011-08-07 | 2011-08-26 | 2011-08-29 | 2011-09-02 | 2011-09-07 | 2011-09-14 | 2011-10-01 | 2012-01-31 | None | No
| CO026 | Councillor Induction | EMO | Peter | MM | 150000 | Quotes | 2011-07-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-08-30 | None | Yes
| CO027 | Inauguration of Council | EMO | Malowa | MM | 200000 | Quotes | 2011-07-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-07-29 | 2011-08-06 | None | Yes
3780000
7 |  | Land
| LA012 | CBD Development Plan (Mookgophong & Thabazimbi) | PED | Phathu | PED | 1000000 | Tender | 2011-07-22 | 2011-08-10 | 2011-08-14 | 2011-09-02 | 2011-10-03 | 2011-11-09 | 2011-09-07 | 2011-09-14 | 2011-10-01 | 2012-03-31 | Service Provider has been appointed and SLA has been signed. | Yes
1000000
8 |  | Transport
| TR007 | Coordination of Transport | PED | Thabo | PED | 100000 | Quotes | On-Going | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-05-30 | None | No
100000
9 |  | Safety & Security
| CO023 | Establishment & Coordination of Safety & Security Forum | EMO | Peter | EMO | 75000 | Quotes | On-Going | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-30 | None | No
75000
10 |  | Sports, Arts & Culture
| SC012 | Executive Mayor's Marathon | EMO | Joseph | EMO | 300000 | Quotes | 2011-02-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-02-28 | 2011-03-31 | None | No
| SC009 | OR Tambo Games | EMO | Joseph | EMO | 400000 | Quotes | 2011-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-03-31 | 2011-05-31 | None | No
| SC011 | District Cultural Festival | EMO | Joseph | EMO | 100000 | Quotes | 2011-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-09-01 | 2011-10-31 | None | No
| CO015 | Coordination of Moral Regeneration | EMO | Joseph | EMO | 100000 | Quotes | 2011-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-10-01 | 2011-11-30 | None | No
900000
11 |  | Electricity
| EL006 | Upgrade of electrisity sub station Modimolle | ID | Makhudu | ID | 1000000 | Transfer to LM`s | N/A | N/A | N/A | N/A | N/A | N/A | N/A | MOU for last year will apply | 2011-08-31 | 2011-09-30 | None | Yes
| EL007 | Upgrade of electrisity sub station Mogalakwena | ID | Makhudu | ID | 2000000 | Transfer to LM`s | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-08-31 | 2011-08-31 | 2011-09-30 | None | No
3000000
43730000
Note on C53: tmaluleke: Disaster Recovery Solution