## Ann E Procurement Planning
ANNEXURE E: PROJECT PROCUREMENT PLANNING TEMPLATE: 2012/13 FINANCIAL YEAR AS AT 30 SEPTEMBER 2012
Dpt | Proj # | PROJECT NAME | Total Capital | Total Operational | Dept | Project Manger | Total Budget | Tender Number | Procurement Method | TOR/Quote/ Plan Submission Date | BSC Meeting Date | Advert Date | Compulsory Briefing Session | Advert Closing Date | BEC Meeting Date | BEC Meeting Date | BAC Meeting Date | Appointment Date | Envisaged Date of SLA | Implementation Date | Procurement Process Completed | Comments | PROJECTED EXPENDITURE - YEAR TO DATE
[5 empty] | Dept | [17 empty] | July | August | September | October | November | December | January | February | March | April | May | June
Municipal Environmental Health & Environmental Management
09 | SE003 | Development of BelaBela landfill site | 0 | 1750000 | SDCS | Tebogo | 1750000 | WDM/2012-13/11 | Tender |  | 2012-05-29 | 8 and 10 July 2012 | 2012-07-18 | 2012-07-27 | 2012-08-03 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | The project will be re- advertised on an open tender as proper consultation was not done with ID. This resulted in the tender not being advertised on CIDB and also without the CIDB Grading. The specifications had material technical errors. | 0 | 480000 | 960000 | 1255000 | 1550000 | 1550000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000
09 | SE018 | Feasibility study for regional toxic landfill site (MTEF = implementation) | 0 | 450000 | SDCS | John | 450000 | WDM/2012-13/16 | Tender |  | 2012-05-29 | 15 and 17 July 2012 | N/A | 2012-08-03 | 2012-08-06 | 2012-09-19 | 2012-10-22 | 2012-10-29 | 2012-10-31 | 2012-11-01 | No | The project will be re- advertised on an open tender as no service provider met the minimum requirements of tender. | 0 | 0 | 150000 | 250000 | 350000 | 350000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
07 | SE019 | Procurement and installation of air quality monitoring equipments | 490000 | 10000 | SDCS | Stanley | 500000 | WDM/2012-13/12 | Tender |  | 2012-05-29 | 8 and 10 July 2012 | 2012-07-19 | 2012-07-27 | 2012-08-03 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | The project was referred back by BAC, to BEC and project manager to reduce the scope of work and re-score. | 0 | 0 | 200000 | 300000 | 400000 | 400000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
07 | SE020 | Air Quality Lekgotla | 0 | 50000 | SDCS | Lilly | 50000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
09 | SE021 | Waste & Environment Lekgotla | 0 | 50000 | SDCS | Lilly | 50000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
09 | HW008 | World Food Day | 0 | 50000 | SDCS | Lilly | 50000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  |  | 490000 | 2360000 |  |  | 2850000
Disaster Management
08 | DM025 | Disaster Risk Management Toll Free Number & promotional signage (roll over) | 0 | 496152 | Disaster | Dan | 496152 |  | S32 Procurement |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-26 | 2012-11-30 | 2012-12-01 | No | The landline number has been secured and awaiting Telkom's activation. Promotion of signage is awaiting approval from HOD Dept of Road and Transport. | [11 empty] | 496152
08 | DM030 | Lephalale - Major Heavy Duty Pumper (roll over) | 3795000 | 3369 | Disaster | Dan | 3798369 |  | Tender |  | 2012-10-31 | 2012-11-18 | N/A | 2012-12-07 | 2012-12-10 | 2012-12-10 | 2012-12-14 | 2012-12-18 | 2012-12-23 | 2012-01-01 | No | None | [11 empty] | 3798369
08 | DM020 | Review of Waterberg Disaster Risk Management Plan & Framework | 0 | 200000 | Disaster | Dan | 200000 |  | Notice Board |  | 2012-11-09 | 2012-11-18 | N/A | 2012-12-07 | 2012-12-10 | 2012-12-10 | 2012-12-14 | 2012-12-18 | 2012-12-23 | 2012-01-01 | No | None | 0 | 0 | 50000 | 100000 | 150000 | 150000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
08 | DM039 | 4x2 Medium Mobile Command Unit (Fully equipped) | 697000 | 3000 | Disaster | Dan | 700000 | WDM/2012-13/01 | Tender |  | 2012-06-04 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | The project was advertised with an MIB as a tender condition. The project manager was not clear as to the correct documentation to be submitted. Objections from bidders were received.BAC referred it back to BEC for re-evaluation. | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 700000 | 700000 | 700000
08 | DN040 | Mogalakwena - 40 army tents & 6 bales relief blankets | 417000 | 3000 | Disaster | Dan | 420000 | WDM/2012-13/08 | Tender |  | 2012-06-07 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | None | 3000 | 3000 | 3000 | 3000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000
08 | DM027 | Mogalakwena - Drought Relief 2 boreholes (not 6) | 0 | 230000 | Disaster | Dan | 230000 | WDM/2012-13/10 | Tender |  | 2012-06-07 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | The specifications were not aligned to the budget. The project will be re-advertised. | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 230000 | 230000 | 230000 | 230000 | 230000
08 | DM041 | Lephalale - 4x4 Major Urban Rescue Pumper & equipment | 947000 | 3000 | Disaster | Dan | 950000 | WDM/2012-13/02 | Tender |  | 2012-06-04 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | Same as DM 039 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000
08 | DM029 | Lephalale - equipment (compressor & scba sets) | 237000 | 3000 | Disaster | Dan | 240000 | WDM/2012-13/09 | Tender |  | 2012-06-07 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000
08 | DM029 | Lephalale Villages Witpoort - equipment (roll over) | 328289 | 0 | Disaster | Dan | 328289 |  | Tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | The project name change was done, from mobile office to lephalale fire fighting equipments. The project will be advertised on a notice board. | [11 empty] | 328289
08 | DM027 | Lephalale - Drought Relief 2 boreholes (not 4) | 0 | 230000 | Disaster | Dan | 230000 | WDM/2012-13/10 | Tender |  | 2012-06-07 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | Same as DM 027. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 230000 | 230000 | 230000 | 230000
08 | DM042 | Bela Bela - 4x2 double cab RIV fully equipped | 697000 | 3000 | Disaster | Dan | 700000 | WDM/2012-13/03 | Tender |  | 2012-06-04 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | Same as DM 039 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 700000 | 700000 | 700000
08 | DM040 | Thabazimbi - 20 army tents & 3 bales relief blankets | 207000 | 3000 | Disaster | Dan | 210000 | WDM/2012-13/08 | Tender |  | 2012-06-07 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | None | 3000 | 3000 | 3000 | 3000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000
08 | DM015 | Thabazimbi - 1 4x4 LDV with 1 skid unit & equipment (NOT 2) | 447000 | 3000 | Disaster | Dan | 450000 | WDM/2012-13/05 | Tender |  | 2012-06-04 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 450000 | 450000 | 450000
08 | DM014 | Thabazimbi - Equipment (compressor & scba sets) | 237000 | 3000 | Disaster | Dan | 240000 | WDM/2012-13/09 | Tender |  | 2012-06-07 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 240000 | 240000 | 240000 | 240000 | 240000
08 | DM014 | Thabazimbi - Equipment (roll over) | 622691 | 0 | Disaster | Dan | 622691 |  | Tender |  | 2012-02-21 | 2012-04-17 | N/A | 2012-05-08 | 2012-05-16 | 2012-05-16 | 2012-06-22 | 2012-11-28 | 2012-11-30 | 2012-12-01 | No | The project was referred back to BEC for re-evaluation. | [11 empty] | 622691
08 | DM043 | Mookgophong - Medium Bush Pumper & equipment | 947000 | 3000 | Disaster | Dan | 950000 | WDM/2012-13/04 | Tender |  | 2012-06-04 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | Same as DM 039 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 950000 | 950000 | 950000
08 | DM044 | Modimolle - 1 (not 3) 4x4 LDVs with skid units | 447000 | 3000 | Disaster | Dan | 450000 | WDM/2012-13/09 | Tender |  | 2012-06-04 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 450000 | 450000 | 450000
08 | DM045 | Modimolle - Heavy Duty foam canon trailer | 298000 | 2000 | Disaster | Dan | 300000 | WDM/2012-13/07 | Tender |  | 2012-06-04 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | None | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 300000 | 300000 | 300000 | 300000 | 300000
08 | DM006 | Modimolle - Equipment (compressor & scba sets) | 237000 | 3000 | Disaster | Dan | 240000 | WDM/2012-13/09 | Tender |  | 2012-06-07 | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 240000 | 240000 | 240000 | 240000 | 240000
08 | DM006 | Modimolle - Equipment (roll over) | 248369 | 0 | Disaster | Dan | 248369 |  | Tender |  | 2012-02-21 | 2012-04-17 | N/A | 2012-05-08 | 2012-05-16 | 2012-05-16 | 2012-06-22 | 2012-11-28 | 2012-11-30 | 2012-12-01 | No | Same as DM 014 | [11 empty] | 248369
08 | DM046 | Modimolle - Refurbishment of Iveco Truck | 0 | 200000 | Disaster | Dan | 200000 | WDM/2012-13/06 | Tender |  | 2012-06-04 | 8 and 10 July 2012 | 2012-07-19 | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000
|  |  | 10809349 | 1394521 |  |  | 12203870
Local Economic Development & Tourism
04 | UE040 | WEDA (roll over) | 0 | 1499300 | PED | Michael | 1499300 |  | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-30 | No | None | [11 empty] | 1499300
04 | UE047 | Bela Bela Flea market (Roll over) | 0 | 242495 | PED | Matete | 242495 |  | Tender |  | 2012-04-19 | 20 and 22 May 2012 | N/A | 2012-06-08 |  | 2012-10-29 |  | ? | ? | ? | No | The evaluation report will be submitted in the BAC meeting of 7 Nov 2012. | [11 empty] | 242495
04 | UE031 | Co-ordination of district wide LED | 0 | 100000 | PED | Michael | 100000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 20000 | 20000 | 35000 | 35000 | 65000 | 80000 | 100000 | 100000
04 | UE038 | Tourism (see below) | 0 | 0 | [29 empty] | 0
|  | - Getaway Show | 0 | 250000 | PED | Michael | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 80000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
|  | - Tourism Month Celebrations | 0 | 25000 | PED | Michael | 25000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
|  | - Mabatlane Wildlife Festival | 0 | 250000 | PED | Michael | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 100000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
|  | - Youth Development in Tourism | 0 | 50000 | PED | Michael | 50000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
|  | - Marula Festival | 0 | 250000 | PED | Michael | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 250000 | 250000 | 250000 | 250000 | 250000
|  | - Tourism Indaba | 0 | 300000 | PED | Michael | 300000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 230000 | 300000 | 300000 | 300000
|  | - Career Expo | 0 | 50000 | PED | Michael | 50000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  | - Publications & Brochures | 0 | 0 | PED | Michael | 0 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Local Tourism Association Support | 0 | 25000 | PED | Michael | 25000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 6250 | 12500 | 12500 | 18750 | 18750 | 18750 | 18750 | 18750 | 25000 | 25000 | 25000
04 | UE040 | Waterberg Biosphere Meander Reserve | 0 | 200000 | PED | Michael | 200000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 50000 | 50000 | 50000 | 100000 | 100000 | 100000 | 150000 | 150000 | 150000 | 200000
04 | UE040 | Waterberg Biosphere Meander Reserve (roll over LEDET grant) | 0 | 100000 | PED | Betty | 100000 |  | BAC item cofunding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | [11 empty] | 100000
04 | UE-43 | Modimolle Security Cameras | 0 | 100000 | PED | Michael | 100000 |  | BAC item cofunding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 25000 | 25000 | 25000 | 50000 | 50000 | 50000 | 75000 | 75000 | 75000 | 100000
|  |  | 0 | 3441795 |  |  | 3441795
Municipal Roads & Stormwater
05 | RS041 | Completion of Streets in Mahwelereng (roll over) | 0 | 1676351 | ID | Jacky | 1676351 |  | Tender |  |  | 2012-05-20 | 2012-05-25 | 2012-06-08 |  | 2012-08-01 | 3 and 4 Oct 2012 | 2012-10-08 | 2012-10-29 | 2012-11-01 | Yes | None | 0 | 0 | 0 | 500000 | 1200000 | 1476351 | 1676351 | 1676351 | 1676351 | 1676351 | 1676351 | 1676351
05 | RS040 | Completion of Bela Bela Street Paving | 0 | 570000 | ID | Bernice | 570000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | None | 0 | 0 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000
05 | RS042 | Upgrading of streets in Marapong Township | 0 | 2000000 | ID | Bernice | 2000000 | WDM/2012-13/14 | Tender |  |  | 15 and 17 July 2012 | 2012-07-20 | 2012-08-03 | 2012-08-07 | 2012-09-19 | 2012-10-22 | 2012-11-13 | 2012-11-20 | 2012-12-01 | Yes | None | 5000 | 5000 | 5000 | 105000 | 105000 | 120000 | 120000 | 800000 | 1500000 | 1800000 | 2000000 | 2000000
05 | RS043 | Upgrading of streets in Regorogile Township | 0 | 2000000 | ID | Bernice | 2000000 | WDM/2012-13/15 | Tender |  |  | 15 and 17 July 2012 | 2012-07-20 | 2012-08-03 | 2012-08-07 | 2012-09-19 | 2012-10-22 | 2012-11-13 | 2012-11-20 | 2012-12-01 | Yes | None | 5000 | 5000 | 5000 | 105000 | 105000 | 120000 | 120000 | 800000 | 1500000 | 1800000 | 2000000 | 2000000
|  |  | 0 | 6246351 |  |  | 6246351
Municipal Support & Institutional Development
03 | IN042 | Procurement of Diesel Generator (roll over) | 494805 | 0 | CSSS |  | 494805 |  | Tender |  | 2012-06-07 | 8 and 10 July 2012 | 2012-07-18 | 2012-07-27 | 2012-08-03 | 2012-08-08 | 2012-10-22 | 2012-11-13 | 2012-11-20 | 2012-12-01 | Yes |  | 0 | 0 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805
03 | IN017 | Procurement of movable assets (see below) | [31 empty] | 0
|  | - Institutional requests | 560000 | 20000 | CSSS | Maureen | 580000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | The project is implemented on a need basis. | 0 | 0 | 80000 | 80000 | 80000 | 280000 | 280000 | 280000 | 580000 | 580000 | 580000 | 580000
|  | - 23 seater minibus | 400000 | 10000 | CSSS | Phineas | 410000 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2012-01-09 | 2012-01-17 | 2012-02-01 | No | None | 0 | 10000 | 10000 | 380000 | 380000 | 380000 | 380000 | 380000 | 410000 | 410000 | 410000 | 410000
|  | - Procurement of municipal pool vehicles | 700000 | 10000 | CSSS | Phineas | 710000 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2012-01-09 | 2012-01-17 | 2012-02-01 | No | None | 0 | 10000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 610000 | 610000 | 610000 | 710000
03 | IN017 | Procurement of movable assets (roll over) | 81372 | 0 | CSSS | Maureen | 81372 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | The project is implemented on a need basis. | [5 empty] | 81372 | 81372 | 81372 | 81372 | 81372 | 81372 | 81372
03 | IN021 | Procurement of IT equipment | 300000 | 0 | CSSS | Keoma | 300000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | The project is implemented on a need basis. | 0 | 0 | 80000 | 80000 | 80000 | 160000 | 160000 | 160000 | 240000 | 240000 | 240000 | 300000
03 | IN021 | Procurement of IT equipment (roll over) | 276414 | 0 | CSSS | Keoma | 276414 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | The project is implemented on a need basis. | [5 empty] | 276414 | 276414 | 276414 | 276414 | 276414 | 276414 | 276414
03 | IN044 | District Wide procurement of IT equipment to be VOIP compatible | 0 | 500000 | CSSS | Keoma | 500000 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2012-01-09 | 2012-01-17 | 2012-02-01 | No | None | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
02 | IN024 | PMS | 0 | 300000 | CSSS | Limited Bidding | 300000 |  | Tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ? | ? | ? | Yes | None | 0 | 0 | 75000 | 75000 | 75000 | 150000 | 150000 | 150000 | 225000 | 225000 | 225000 | 300000
03 | IN027 | District Wide Integrated Financial Management Systems | 350000 | 3150000 | CSSS | Limited Bidding | 3500000 |  | Tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ? | ? | ? | No | None | 0 | 0 | 0 | 0 | 1850000 | 1850000 | 1850000 | 2750000 | 2750000 | 2750000 | 2750000 | 3500000
03 | IN043 | Installation of WDM CCTV Cameras - MDC & Abattoir | 1000000 | 0 | CSSS | Phineas | 1000000 |  | S32 Procurement |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-08-13 | 2012-09-03 | 2012-09-03 | Yes | None | 0 | 0 | 0 | 0 | 0 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 1000000
02 | IN045 | District Wide Audit System | 0 | 350000 | CSSS | Phineas | 350000 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2012-01-09 | 2012-01-17 | 2012-02-01 | No | None | 0 | 0 | 50000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000
03 | IN046 | Installation of new lift in WDM Head Office Building | 497000 | 3000 | CSSS | Phineas | 500000 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2012-01-09 | 2012-01-17 | 2012-02-01 | No | None | 0 | 3000 | 3000 | 3000 | 3000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
|  |  | 4659591 | 4343000 |  |  | 9002591
Communicity Participation & Good Governance
06 | CO009 | Communication | 0 | 500000 | OEM | Pat | 500000 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2012-01-09 | 2012-01-17 | 2012-02-01 | No | None | 0 | 50000 | 100000 | 200000 | 200000 | 250000 | 250000 | 250000 | 350000 | 350000 | 500000 | 500000
06 | CO013 | Production of Diaries for Cllrs & Traditional Leaders | 0 | 40000 | OEM | Pat | 40000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | None | 0 | 0 | 0 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
06 | CO011 | District IDP Public Participation Programme - EMO | 0 | 900000 | OEM | Peter | 900000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 30000 | 30000 | 280000 | 280000 | 280000 | 530000 | 530000 | 530000 | 780000 | 780000 | 900000 | 900000
02 | CO012 | District IDP Strategic Planning Programme - MMO | 0 | 402000 | OMM | Philemon | 402000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None |  | 0 | 0 | 30000 | 30000 | 30000 | 180000 | 180000 | 180000 | 280000 | 280000 | 402000
06 | CO014 | Learning & sharing (twinning agreement) | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 60000 | 60000 | 60000 | 60000 | 100000 | 100000 | 100000 | 100000 | 150000 | 150000 | 150000
06 | CO016 | Gender Programs | 0 | 700000 | OEM | Peter | 700000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 300000 | 300000 | 300000 | 300000 | 600000 | 600000 | 600000 | 600000 | 700000 | 700000 | 700000
06 | new | Senior Citizens | 0 | 400000 | OEM | Peter | 400000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 300000 | 300000 | 300000 | 350000 | 350000 | 400000 | 400000 | 400000
06 | CO017 | HIV/AIDS Awareness Programs | 0 | 550000 | OEM | Peter | 550000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 50000 | 50000 | 250000 | 250000 | 450000 | 450000 | 450000 | 550000 | 550000 | 550000 | 550000
06 | CO018 | People with Disability Programs | 0 | 450000 | OEM | Peter | 450000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 10000 | 10000 | 10000 | 20000 | 20000 | 350000 | 350000 | 350000 | 450000 | 450000 | 450000 | 450000
06 | CO019 | Youth Programs | 0 | 650000 | OEM | Joseph | 650000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 150000 | 150000 | 150000 | 250000 | 250000 | 250000 | 250000 | 250000 | 650000 | 650000
02 | CO020 | Anti-fraud helpline | 0 | 50000 | OMM | Malose | 50000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 7000 | 14000 | 21000 | 28000 | 35000 | 42000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
06 | CO024 | Batho Pele Programme | 0 | 350000 | OEM | Peter | 350000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000
06 | CO028 | Farm Workers Empowerment | 0 | 250000 | OEM | Peter | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
06 | CO029 | Domestic Workers Empowerment | 0 | 250000 | OEM | Peter | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 150000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
06 | CO030 | Back to School Campaign | 0 | 100000 | OEM | Peter | 100000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
06 | CO031 | Mandela Day Celebration | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 120000 | 120000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
06 | CO032 | Children | 0 | 260000 | OEM | Peter | 260000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 160000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000
|  |  | 0 | 6152000 |  |  | 6152000
Land
04 | LA012 | CBD Development Plan Lephalale | 0 | 500000 |  |  | 500000 |  | Tender |  | 2012-08-01 | 12 and 14 Aug 2012 | 2012-08-16 | 2012-08-31 | 2012-09-20 | 2012-09-20 | 2012-10-22 | 2012-11-13 | 2012-11-20 | 2012-12-01 | Yes | None | 10000 | 10000 | 10000 | 10000 | 130000 | 130000 | 130000 | 350000 | 350000 | 350000 | 500000 | 500000
04 | LA007 | Review of Spatial Development Framework | 0 | 550000 |  |  | 550000 |  | Tender |  | 2012-08-01 | 12 and 14 Aug 2012 | 2012-08-16 | 2012-08-31 | 2012-09-20 | 2012-09-20 | 2012-10-22 | 2012-11-13 | 2012-11-20 | 2012-12-01 | Yes | None | 10000 | 10000 | 10000 | 160000 | 160000 | 160000 | 380000 | 380000 | 380000 | 550000 | 550000 | 550000
|  |  | 0 | 1050000 |  |  | 1050000
Sports, Arts & Culture
06 | SC012 | Executive Mayor's Marathon | 0 | 200000 | OEM | Peter | 200000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 200000 | 200000 | 200000
06 | CO-22 | Golf & Life Skills Development for Youth | 0 | 200000 | OEM | Peter | 200000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
06 | SC010 | Women in Sport | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
06 | SC013 | Mayoral Golf Classic | 0 | 200000 | OEM | Peter | 200000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 200000 | 200000 | 200000 | 200000 | 200000
06 | SC014 | Disability Sport | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
06 | SC009 | Sport Development( Olympics) | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 50000 | 50000 | 50000 | 50000 | 100000 | 100000 | 100000 | 100000 | 150000 | 150000 | 150000
06 | CO015 | Coordination of Moral Regeneration | 0 | 200000 | OEM | Peter | 200000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 50000 | 50000 | 50000 | 100000 | 100000 | 100000 | 150000 | 150000 | 150000 | 200000
06 | CO033 | Heritage Celebration | 0 | 200000 | OEM | Peter | 200000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
06 | CO034 | Traditional Leadership development Programme | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | None | 0 | 0 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
|  |  | 0 | 1600000 |  |  | 1600000
Water & Sanitation
05 | SA033 | Provision of household VIP sanitation at Lephalale and Mogalakwena | 0 | 1000000 | ID | Bernice | 1000000 |  |  |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2012-01-09 | 2012-01-17 | 2012-02-01 | No | None | 0 | 5000 | 5000 | 5000 | 305000 | 605000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
05 | SA031 | Northam Sewer Extension 5 | 0 | 168000 | ID | Bernice | 168000 |  |  |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2012-01-09 | 2012-01-18 | 2012-02-01 | No | None | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000
05 | SA032 | Mookgophong Township Sewer Connection | 0 | 3000000 | ID | Bernice | 3000000 | WDM/2011-12/31 | Tender |  |  | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 2012-10-22 | 2012-11-13 | 2012-11-20 | 2012-12-01 | Yes | This information relates to the appointment of a consultants. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1500000 | 2500000 | 3000000
05 | SA032 | Mookgophong Township Sewer Connection (roll over) | 0 | 2998121 | ID | Bernice | 2998121 | WDM/2011-12/31 | Tender |  |  | 8 and 10 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-08 | 2012-10-22 | 2012-11-13 | 2012-11-20 | 2012-12-01 | Yes | This information relates to the appointment of a consultants. | 0 | 5000 | 5000 | 255000 | 405000 | 410000 | 410000 | 1700000 | 2998121 | 2998121 | 2998121 | 2998121
|  |  | 0 | 7166121 |  |  | 7166121
Electricity
05 | EL006 | ESCOM Electricity upgrade - co-funding in Modimolle | 0 | 1500000 | ID | Bernice | 1500000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Funds were transferred to Modimolle Local Municipality on 24 Aug 2012. | 0 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
05 | EL008 | Electricity upgrade - co-funding in Lephalale | 0 | 650000 | ID | Bernice | 650000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Funds were transferred to Lephalale Local Municipality on 26 Oct 2012. | 0 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000
05 | EL009 | Electricity upgrade - co-funding in Bela Bela | 0 | 850000 | ID | Bernice | 850000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Funds were transferred to Bela-Bela Local Municipality on 26 Oct 2012. | 0 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000
05 | EL010 | Upgrade of Ga-Seleka drop in center | 0 | 500000 | ID | Bernice | 500000 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2012-01-09 | 2012-01-18 | 2012-02-01 | No | None | 0 | 5000 | 5000 | 5000 | 155000 | 355000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
|  |  | 0 | 3500000 |  |  | 3500000
Abattoir
05 | UE029 | Upgrade of the abattoir (roll over) | 1034310 | 0 | ID | Jacky | 1034310 |  | Limited Bidding |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-10-08 | 2012-10-08 | 2012-11-01 | Yes | Various service providers were appointed on 8 Oct 2012 because the SLA with service provider who was appointed through open tender was terminated due to poor performance. | 0 | 0 | 40000 | 840000 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310
|  |  | 1034310 | 0 |  |  | 1034310
|  | Total | 16993250 | 37253788 |  |  | 54247038 | [15 empty] | 630000 | 5291250 | 8554305 | 11756305 | 17088555 | 22511692 | 25858692 | 30880692 | 35908813 | 41605063 | 43895063 | 53212728
54247038
IDP 12/13 Expenditure per Department:
| 001 | CFO | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 002 | MM | 0 | 1102000 | [18 empty] | 7000 | 14000 | 146000 | 483000 | 490000 | 572000 | 730000 | 730000 | 805000 | 905000 | 905000 | 1102000
| 003 | MCSSS | 3807000 | 3693000 | [18 empty] | 0 | 23000 | 473000 | 843000 | 2693000 | 4920000 | 4920000 | 5820000 | 6540000 | 6540000 | 6540000 | 7500000
| 004 | MPED | 0 | 2650000 | [18 empty] | 250000 | 576250 | 682500 | 832500 | 978750 | 1103750 | 1438750 | 1808750 | 2093750 | 2355000 | 2575000 | 2650000
| 005 | MID | 0 | 12238000 | [18 empty] | 178000 | 3188000 | 3758000 | 3958000 | 4408000 | 4938000 | 5478000 | 6838000 | 8738000 | 10338000 | 11738000 | 12238000
| 006 | MEMO | 0 | 7300000 | [18 empty] | 160000 | 970000 | 1600000 | 2450000 | 3160000 | 4980000 | 5230000 | 5330000 | 6080000 | 6380000 | 7050000 | 7300000
| 007 | MSDCS | 490000 | 60000 | [18 empty] | 0 | 0 | 200000 | 300000 | 450000 | 450000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000
| 008 | Disaster | 5815000 | 895000 | [18 empty] | 35000 | 35000 | 85000 | 135000 | 809000 | 809000 | 2273000 | 3275000 | 3275000 | 6710000 | 6710000 | 6710000
| 009 | Health | 0 | 2300000 | [18 empty] | 0 | 480000 | 1110000 | 1505000 | 2000000 | 2000000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000
| 020 | Abattoir | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total per dpt | 10112000 | 30238000 | [18 empty] | 630000 | 5286250 | 8054500 | 10506500 | 14988750 | 19772750 | 22919750 | 26651750 | 30381750 | 36078000 | 38368000 | 40350000
|  | Quarterly spending targets | [22 empty] | 14.85% |  |  | 36.45% |  |  | 56.01% |  |  | 74.38%
|  | 12/13 original IDP | 40350000
|  | 11/12 Roll Over | 0
40350000