## Ann E Procurement Planning
ANNEXURE E: PROJECT PROCUREMENT PLANNING TEMPLATE: 2012/13 FINANCIAL YEAR AS AT 31 DECEMBER 2012
Dpt | Proj # | PROJECT NAME | Total Capital | Total Operational | Dept | Project Manger | Total Budget | Tender Number | Procurement Method | TOR/Quote/ Plan Submission Date | BSC Meeting Date | Advert Date | Compulsory Briefing Session | Advert Closing Date | BEC Meeting Date | BEC Meeting Date | BAC Meeting Date | Appointment Date | Envisaged Date of SLA | Implementation Date | Procurement Process Completed | Comments | PROJECTED EXPENDITURE - YEAR TO DATE
[5 empty] | Dept | [17 empty] | July | August | September | October | November | December | January | February | March | April | May | June
Municipal Environmental Health & Environmental Management
09 | SE003 | Development of BelaBela landfill site | 0 | 1750000 | SDCS | Tebogo | 1750000 | WDM/2012-13/11 | Tender |  | 2013-01-15 | 27/28 Jan 2013 | 2013-02-01 | 2013-02-15 | 2012-08-03 | 2013-02-21 | 2013-02-28 | 2013-03-08 | 2013-03-14 | 2013-03-14 | No | The project will be re- advertised on an open tender as proper consultation was not done with ID. This resulted in the tender not being advertised on CIDB and also without the CIDB Grading. The specifications had material technical errors. | 0 | 480000 | 960000 | 1255000 | 1550000 | 1550000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000
09 | SE018 | Feasibility study for regional toxic landfill site | 0 | 450000 | SDCS | John | 450000 | WDM/2012-13/16 | Tender |  | 2013-01-24 | 3/4 Feb 13 | 2013-02-08 | 2013-02-22 | 2012-08-06 | 2013-02-28 | 2013-03-06 | 2013-03-13 | 2013-03-20 | 2013-03-22 | No | The project will be re- advertised on an open tender as no service provider met the minimum requirements of tender.Awaiting for specification | 0 | 0 | 150000 | 250000 | 350000 | 350000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
07 | SE019 | Procurement and installation of air quality monitoring equipments | 490000 | 10000 | SDCS | Stanley | 500000 | WDM/2012-13/12 | Tender |  | 2013-01-24 | 3/4 Feb 13 | 2013-02-08 | 2013-02-22 | 2012-08-06 | 2013-02-28 | 2013-03-06 | 2013-03-13 | 2013-03-20 | 2013-03-22 | No | The project will be re- advertised on an open tender as no service provider met the minimum requirements of tender.Awaiting for specification | 0 | 0 | 200000 | 300000 | 400000 | 400000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
07 | SE020 | Air Quality Lekgotla | 0 | 50000 | SDCS | Lilly | 50000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
09 | SE021 | Waste & Environment Lekgotla | 0 | 50000 | SDCS | Lilly | 50000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
09 | HW008 | World Food Day | 0 | 50000 | SDCS | Lilly | 50000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  |  | 490000 | 2360000 |  |  | 2850000
Disaster Management
08 | DM025 | Disaster Risk Management Toll Free Number & promotional signage (roll over) | 0 | 496152 | Disaster | Dan | 496152 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-26 | 2012-11-30 | 2012-12-01 | No | The landline number has been secured and awaiting Telkom's activation. Promotion of signage is awaiting approval from HOD Dept of Road and Transport. | PROJECTED EXPENDITURE - YEAR TO DATE June: 496152
08 | DM030 | Lephalale - Major Heavy Duty Pumper (roll over) | 3795000 | 3369 | Disaster | Dan | 3798369 |  | Tender |  | 2012-10-31 | 2012-11-18 | N/A | 2012-12-07 | 2012-12-10 | 2012-12-10 | 2012-12-14 | 2012-12-18 | 2012-12-23 | 2012-01-01 | Yes | None | PROJECTED EXPENDITURE - YEAR TO DATE June: 3798369
08 | DM020 | Review of Waterberg Disaster Risk Management Plan & Framework | 0 | 200000 | Disaster | Dan | 200000 |  | Notice Board |  | 2013-06-29 | 2013-08-12 | 2013-08-16 | 2013-08-31 | 2012-12-10 | 2013-10-11 | 2013-10-22 | 2012-12-18 | 2012-12-23 | 2012-01-01 | Yes | None | 0 | 0 | 50000 | 100000 | 150000 | 150000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
08 | DM039 | 4x2 Medium Mobile Command Unit (Fully equipped) | 905308 | 3000 | Disaster | Dan | 908308 | WDM/2012-13/01 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-01 | 3 and 4 Oct 2012 | 2012-12-12 | 2012-12-20 | 2013-01-22 | Yes | none | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 700000 | 700000 | 908308
08 | DM040 | Mogalakwena - 40 army tents & 6 bales relief blankets. Thabazimbi - 20 army tents & 3 bales blankets | 373875 | 3000 | Disaster | Dan | 376875 | WDM/2012-13/08 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-11-28 | 2012-12-05 | 2013-01-22 | Yes | None | 3000 | 3000 | 3000 | 3000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 376875
08 | DM027 | Mogalakwena & Lephalale - Drought Relief 2 boreholes each | 0 | 460000 | Disaster | Dan | 460000 | WDM/2012-13/10 | Tender |  | 2013-01-24 | 3 & 4 Jan 13 | 2013-02-08 | 2013-02-22 | 1 and 2 Aug 2012 | 2013-02-28 | 2013-03-06 | 2013-03-13 | 2013-03-20 | 2013-03-22 | No | The specifications were not aligned to the budget. The project will be re-advertised.Waiting for revised specifications | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 230000 | 230000 | 230000 | 230000 | 460000
08 | DM041 | Lephalale - 4x4 Major Urban Rescue Pumper & equipment | 1469858 | 3000 | Disaster | Dan | 1472858 | WDM/2012-13/02 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-01 | 3 and 4 Oct 2012 | 2012-12-12 | 2012-12-20 | 2013-01-22 | Yes | none | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 950000 | 950000 | 950000 | 950000 | 950000 | 1472858
08 | DM029 | Lephalale - equipment (compressor & scba sets) | 237000 | 3000 | Disaster | Dan | 240000 | WDM/2012-13/09 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-14 | 2012-01-25 | 2012-02-04 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000
08 | DM029 | Lephalale Villages Witpoort - equipment (roll over) | 315063 | 0 | Disaster | Dan | 315063 |  | Tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | The project name change was done, from mobile office to lephalale fire fighting equipments. The project will be advertised on a notice board. | PROJECTED EXPENDITURE - YEAR TO DATE June: 315063
08 | DM042 | Bela Bela - 4x2 double cab RIV fully equipped | 434862 | 3000 | Disaster | Dan | 437862 | WDM/2012-13/03 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-01 | 3 and 4 Oct 2012 | 2012-12-12 | 2013-12-20 | 2013-01-02 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 700000 | 700000 | 437862
08 | DM015 | Thabazimbi - 1 4x4 LDV with 1 skid unit & equipment (NOT 2) | 436171 | 3000 | Disaster | Dan | 439171 | WDM/2012-13/05 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-14 | 2013-01-22 | 2013-01-22 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 450000 | 450000 | 439171
08 | DM014 | Thabazimbi - Equipment (compressor & scba sets) | 237000 | 3000 | Disaster | Dan | 240000 | WDM/2012-13/09 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-12 | 2013-01-25 | 2013-02-04 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 240000 | 240000 | 240000 | 240000 | 240000
08 | DM014 | Thabazimbi - Equipment (roll over) | 622691 | 0 | Disaster | Dan | 622691 |  | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-12 | 2013-01-22 | 2013-01-22 | Yes | None | PROJECTED EXPENDITURE - YEAR TO DATE June: 622691
08 | DM043 | Mookgophong - Medium Bush Pumper & equipment | 770606 | 3000 | Disaster | Dan | 773606 | WDM/2012-13/04 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-12 | 2013-01-25 | 2013-02-04 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 950000 | 950000 | 773606
08 | DM044 | Modimolle - 1 (not 3) 4x4 LDVs with skid units | 431546 | 3000 | Disaster | Dan | 434546 | WDM/2012-13/09 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-14 | 2013-01-22 | 2013-02-04 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 450000 | 450000 | 434546
08 | DM045 | Modimolle - Heavy Duty foam canon trailer | 298000 | 2000 | Disaster | Dan | 300000 | WDM/2012-13/07 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-11-29 | 2013-01-25 | 2013-02-04 | Yes | None | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 300000 | 300000 | 300000 | 300000 | 300000
08 | DM006 | Modimolle - Equipment (compressor & scba sets) | 237000 | 3000 | Disaster | Dan | 240000 | WDM/2012-13/09 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-12 | 2012-01-25 | 2012-02-04 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 240000 | 240000 | 240000 | 240000 | 240000
08 | DM006 | Modimolle - Equipment (roll over) | 248369 | 0 | Disaster | Dan | 248369 |  | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-12 | 2013-01-22 | 2013-02-04 | Yes | None | PROJECTED EXPENDITURE - YEAR TO DATE June: 248369
08 | DM046 | Modimolle - Refurbishment of Iveco Truck | 0 | 200000 | Disaster | Dan | 200000 | WDM/2012-13/06 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | 2012-07-19 | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-01 | 3 and 4 Oct 2012 | 2012-11-28 | 2013-01-22 | 2013-02-04 | Yes | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000
08 | DM032 | Fire Station Standby Generator Refurbishment - Mogalakwena (roll over) | 95000 | 0 | Disaster | Dan | 95000 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed | PROJECTED EXPENDITURE - YEAR TO DATE June: 95000
08 | DM036 | Thabazimbi Water Tank (roll over) | 1095600 | 0 | Disaster | Dan | 1095600 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed | PROJECTED EXPENDITURE - YEAR TO DATE June: 1095600
08 | DM037 | Bela Bela Medium Pumper Vehicle & equipment (roll over) | 844804 | 0 | Disaster | Dan | 844804 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed | PROJECTED EXPENDITURE - YEAR TO DATE June: 844804
08 | DM038 | Modimolle - Medium Double Cab RIV (roll over) | 568260 | 0 | Disaster | Dan | 568260 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed | PROJECTED EXPENDITURE - YEAR TO DATE June: 568260
|  |  | 13416013 | 1391521 |  |  | 14807534
Local Economic Development & Tourism
04 | UE040 | WEDA (roll over) | 0 | 1499300 | PED | Michael | 1499300 |  | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-30 | Ad hoc | None | PROJECTED EXPENDITURE - YEAR TO DATE June: 1499300
04 | UE047 | Bela Bela Flea market (Roll over) | 0 | 242495 | PED | Matete | 242495 |  | Tender |  | 2012-06-19 | 20 & 22 May 2012 | N/A | 2012-06-08 |  | 2012-06-19 | 2012-11-13 | 2012-12-12 | 2013-01-30 | 2013-02-04 | Yes | SLA awaiting for signature | PROJECTED EXPENDITURE - YEAR TO DATE June: 242495
04 | UE031 | Co-ordination of district wide LED | 0 | 100000 | PED | Michael | 100000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 20000 | 20000 | 35000 | 35000 | 65000 | 80000 | 100000 | 100000
04 | UE034 | Wildlife Centre - Vaalwater Beautification (roll over) |  | 789744 | PED | Michael | 789744 |  | None |  | None | None | None | None | None | None | None | None | None | None | No | No communication to date
04 | UE038 | Tourism (see below) | 0 | 0 | [18 empty] | PROJECTED EXPENDITURE - YEAR TO DATE June: 0
|  | - Getaway Show | 0 | 250000 | PED | Michael | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 80000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
|  | - Tourism Month Celebrations | 0 | 25000 | PED | Michael | 25000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
|  | - Mabatlane Wildlife Festival | 0 | 250000 | PED | Michael | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 100000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
|  | - Youth Development in Tourism | 0 | 50000 | PED | Michael | 50000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
|  | - Marula Festival | 0 | 250000 | PED | Michael | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 250000 | 250000 | 250000 | 250000 | 250000
|  | - Tourism Indaba | 0 | 300000 | PED | Michael | 300000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 230000 | 300000 | 300000 | 300000
|  | - Career Expo | 0 | 50000 | PED | Michael | 50000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  | - Publications & Brochures | 0 | 0 | PED | Michael | 0 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Local Tourism Association Support | 0 | 25000 | PED | Michael | 25000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 6250 | 12500 | 12500 | 18750 | 18750 | 18750 | 18750 | 18750 | 25000 | 25000 | 25000
04 | UE040 | Waterberg Biosphere Meander Reserve | 0 | 200000 | PED | Betty | 200000 |  | BAC item cofunding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-29 | 2013-01-10 | 2013-01-10 | Yes | None | 0 | 0 | 50000 | 50000 | 50000 | 100000 | 100000 | 100000 | 150000 | 150000 | 150000 | 200000
04 | UE040 | Waterberg Biosphere Meander Reserve (roll over LEDET grant) | 0 | 100000 | PED | Betty | 100000 |  | BAC item cofunding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-13 | 2013-01-10 | 2013-01-10 | Yes | None | PROJECTED EXPENDITURE - YEAR TO DATE June: 100000
04 | UE-43 | Modimolle Security Cameras | 0 | 100000 | PED | Michael | 100000 |  | BAC item cofunding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-15 | 2012-11-28 | 2012-11-28 | Yes | None | 0 | 0 | 25000 | 25000 | 25000 | 50000 | 50000 | 50000 | 75000 | 75000 | 75000 | 100000
|  |  | 0 | 4231539 |  |  | 4231539
Municipal Roads & Stormwater
05 | RS021 | Completion of Modimolle ring road (roll over) | 0 | 2511774 | ID | Jacky | 2511774 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Current year was only extension | 0 | 0 | 0 | 500000 | 1200000 | 1476351 | 1676351 | 1676351 | 1676351 | 1676351 | 1676351 | 2511774
05 | RS041 | Completion of Streets in Mahwelereng (roll over) | 0 | 1644619 | ID | Jacky | 1644619 |  | Tender |  | 2012-08-08 | 2012-05-20 | 2012-05-25 | 2012-06-08 |  | 2012-08-01 | 3 and 4 Oct 2012 | 2012-11-28 | 2013-01-29 | 2013-01-29 | No | None | 0 | 0 | 0 | 500000 | 1200000 | 1476351 | 1676351 | 1676351 | 1676351 | 1676351 | 1676351 | 1644619
05 | RS040 | Completion of Bela Bela Street Paving | 0 | 570000 | ID | Bernice | 570000 |  | PY | N/A | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed | 0 | 0 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000
05 | RS040 | Completion of Bela Bela Street Paving (roll over) | 0 | 883805 | ID | Bernice | 883805 |  | PY | N/A | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed
05 | RS042 | Upgrading of streets in Marapong Township | 0 | 2000000 | ID | Bernice | 2000000 | WDM/2012-13/14 | Tender |  | 2012-06-29 | 15 & 17 July 2012 | 2012-07-20 | 2012-08-03 | 2012-08-07 | 2012-09-19 | 2012-10-22 | 2012-12-12 | 2013-01-14 | 2013-01-14 | Yes | None | 5000 | 5000 | 5000 | 105000 | 105000 | 120000 | 120000 | 800000 | 1500000 | 1800000 | 2000000 | 2000000
05 | RS043 | Upgrading of streets in Regorogile Township | 0 | 2000000 | ID | Bernice | 2000000 | WDM/2012-13/15 | Tender |  | 2012-06-29 | 15 & 17 July 2012 | 2012-07-20 | 2012-08-03 | 2012-08-07 | 2012-09-19 | 2012-10-22 | 2012-11-28 | 2013-01-14 | 2013-01-14 | Yes | None | 5000 | 5000 | 5000 | 105000 | 105000 | 120000 | 120000 | 800000 | 1500000 | 1800000 | 2000000 | 2000000
|  |  | 0 | 9610198 |  |  | 9610198
Municipal Support & Institutional Development
03 | IN042 | Procurement of Diesel Generator (roll over) | 494805 | 0 | CSSS |  | 494805 |  | Tender |  | 2012-06-07 | 8 & 9 July 2012 | 2012-07-18 | 2012-07-27 | 2012-08-03 | 2012-08-08 | 2012-10-22 | 2012-12-12 | 2013-01-16 | 2013-01-16 | Yes |  | 0 | 0 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805
03 | IN017 | Procurement of movable assets (see below) | [20 empty] | PROJECTED EXPENDITURE - YEAR TO DATE June: 0
|  | - Institutional requests | 560000 | 20000 | CSSS | Maureen | 580000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | The project is implemented on a need basis. | 0 | 0 | 80000 | 80000 | 80000 | 280000 | 280000 | 280000 | 580000 | 580000 | 580000 | 580000
|  | - 23 seater minibus | 400000 | 10000 | CSSS | Phineas | 410000 |  | Tender |  | 2013-01-15 | 28 & 29 JAN | 2013-02-01 | 2013-02-15 | 2012-12-18 | 2013-02-21 | 2013-02-28 | 2013-03-08 | 2013-03-14 | 2013-03-15 | No | None | 0 | 10000 | 10000 | 380000 | 380000 | 380000 | 380000 | 380000 | 410000 | 410000 | 410000 | 410000
|  | - Procurement of municipal pool vehicles | 700000 | 10000 | CSSS | Phineas | 710000 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2013-01-09 | 2013-01-17 | 2013-02-01 | No | None | 0 | 10000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 610000 | 610000 | 610000 | 710000
03 | IN017 | Procurement of movable assets (roll over) | 381372 | 0 | CSSS | Maureen | 381372 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | The project is implemented on a need basis. | PROJECTED EXPENDITURE - YEAR TO DATE December: 81372; PROJECTED EXPENDITURE - YEAR TO DATE January: 81372; PROJECTED EXPENDITURE - YEAR TO DATE February: 81372; PROJECTED EXPENDITURE - YEAR TO DATE March: 81372; PROJECTED EXPENDITURE - YEAR TO DATE April: 81372; PROJECTED EXPENDITURE - YEAR TO DATE May: 81372; PROJECTED EXPENDITURE - YEAR TO DATE June: 381372
03 | IN021 | Procurement of IT equipment | 300000 | 0 | CSSS | Keoma | 300000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | The project is implemented on a need basis. | 0 | 0 | 80000 | 80000 | 80000 | 160000 | 160000 | 160000 | 240000 | 240000 | 240000 | 300000
03 | IN021 | Procurement of IT equipment (roll over) | 274157 | 0 | CSSS | Keoma | 274157 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | The project is implemented on a need basis. | PROJECTED EXPENDITURE - YEAR TO DATE December: 276414; PROJECTED EXPENDITURE - YEAR TO DATE January: 276414; PROJECTED EXPENDITURE - YEAR TO DATE February: 276414; PROJECTED EXPENDITURE - YEAR TO DATE March: 276414; PROJECTED EXPENDITURE - YEAR TO DATE April: 276414; PROJECTED EXPENDITURE - YEAR TO DATE May: 276414; PROJECTED EXPENDITURE - YEAR TO DATE June: 274157
03 | IN044 | District Wide procurement of IT equipment to be VOIP compatible | 0 | 500000 | CSSS | Keoma | 500000 |  | Tender |  | 2013-01-15 | 28 & 29 JAN | 2013-02-01 | 2013-02-15 | 2012-12-18 | 2013-02-21 | 2013-02-28 | 2013-03-08 | 2013-03-14 | 2013-03-15 | No | None | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
02 | IN024 | PMS | 0 | 300000 | MM | Philemon | 300000 |  | Tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ? | ? | ? | Yes | None | 0 | 0 | 75000 | 75000 | 75000 | 150000 | 150000 | 150000 | 225000 | 225000 | 225000 | 300000
02 | IN024 | PMS (roll over) | 0 | 304065 | MM | Philemon | 304065 |  | Tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ? | ? | ? | Yes | None | 0 | 0 | 75000 | 75000 | 75000 | 150000 | 150000 | 150000 | 225000 | 225000 | 225000 | 304065
03 | IN027 | District Wide Integrated Financial Management Systems | 350000 | 3150000 | CSSS | Nadine | 3500000 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-09-07 | 2011-11-01 | 2011-11-01 | Yes | Further roll-out through LMs | 0 | 0 | 0 | 0 | 1850000 | 1850000 | 1850000 | 2750000 | 2750000 | 2750000 | 2750000 | 3500000
03 | IN027 | District Wide Integrated Financial Management Systems (roll over) | 50000 | 3150000 | CSSS | Nadine | 3200000 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-09-07 | 2011-11-01 | 2011-11-01 | Yes | Further roll-out through LMs | 0 | 0 | 0 | 0 | 1850000 | 1850000 | 1850000 | 2750000 | 2750000 | 2750000 | 2750000 | 3200000
03 | IN043 | Installation of WDM CCTV Cameras - MDC & Abattoir | 1002257 | 0 | CSSS | Phineas | 1002257 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-08-13 | 2012-09-03 | 2012-09-03 | Yes | None | 0 | 0 | 0 | 0 | 0 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 1002257
02 | IN045 | District Wide Audit System | 0 | 350000 | MM | Malose | 350000 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2013-01-09 | 2013-01-17 | 2013-02-01 | No | None | 0 | 0 | 50000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000
03 | IN046 | Installation of new lift in WDM Head Office Building | 497000 | 3000 | CSSS | Phineas | 500000 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2013-01-09 | 2013-01-17 | 2013-02-01 | No | None | 0 | 3000 | 3000 | 3000 | 3000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
02 | IN035 | Lephalale Turnaround Strategy | 0 | 526425 | MM | Philemon | 526425 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PY | PY | PY | Yes | None | 0 | 0 | 0 | 0 | 0 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 526425
03 | IN041 | District Wide VPN Network | 0 | 1700000 | CSSS | Keoma | 1700000 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-10-01 | 2012-10-01 | 2012-10-31 | Yes | None | 0 | 0 | 0 | 0 | 0 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 1700000
|  |  | 5009591 | 10023490 |  |  | 15033081
Communicity Participation & Good Governance
06 | CO009 | Communication | 0 | 450000 | OEM | Pat | 450000 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2013-01-09 | 2013-01-17 | 2013-02-01 | No | None | 0 | 50000 | 100000 | 200000 | 200000 | 250000 | 250000 | 250000 | 350000 | 350000 | 500000 | 450000
06 | CO009 | Communication (roll over) | 0 | 431644 | OEM | Pat | 431644 |  | Tender |  | 2012-11-09 | 2012-11-25 | 2012-12-04 | 2012-12-14 | 2012-12-18 | 2012-12-18 | 2012-12-21 | 2013-01-09 | 2013-01-17 | 2013-02-01 | No | None | 0 | 50000 | 100000 | 200000 | 200000 | 250000 | 250000 | 250000 | 350000 | 350000 | 500000 | 431644
06 | CO013 | Production of Diaries for Cllrs & Traditional Leaders | 0 | 40000 | OEM | Pat | 40000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
06 | CO011 | District IDP Public Participation Programme - EMO | 0 | 900000 | OEM | Peter | 900000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 30000 | 30000 | 280000 | 280000 | 280000 | 530000 | 530000 | 530000 | 780000 | 780000 | 900000 | 900000
02 | CO012 | District IDP Strategic Planning Programme - MMO | 0 | 402000 | OMM | Philemon | 402000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None |  | 0 | 0 | 30000 | 30000 | 30000 | 180000 | 180000 | 180000 | 280000 | 280000 | 402000
06 | CO014 | Learning & sharing (twinning agreement) | 0 | 200000 | OEM | Peter | 200000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 60000 | 60000 | 60000 | 60000 | 100000 | 100000 | 100000 | 100000 | 150000 | 150000 | 200000
06 | CO016 | Gender Programs | 0 | 700000 | OEM | Peter | 700000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 300000 | 300000 | 300000 | 300000 | 600000 | 600000 | 600000 | 600000 | 700000 | 700000 | 700000
06 | CO035 | Senior Citizens | 0 | 400000 | OEM | Peter | 400000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 300000 | 300000 | 300000 | 350000 | 350000 | 400000 | 400000 | 400000
06 | CO017 | HIV/AIDS Awareness Programs | 0 | 550000 | OEM | Peter | 550000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 50000 | 50000 | 250000 | 250000 | 450000 | 450000 | 450000 | 550000 | 550000 | 550000 | 550000
06 | CO018 | People with Disability Programs | 0 | 450000 | OEM | Peter | 450000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 10000 | 10000 | 10000 | 20000 | 20000 | 350000 | 350000 | 350000 | 450000 | 450000 | 450000 | 450000
06 | CO019 | Youth Programs | 0 | 650000 | OEM | Joseph | 650000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 150000 | 150000 | 150000 | 250000 | 250000 | 250000 | 250000 | 250000 | 650000 | 650000
02 | CO020 | Anti-fraud helpline | 0 | 50000 | OMM | Malose | 50000 |  | Tender | N/A | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | None | 7000 | 14000 | 21000 | 28000 | 35000 | 42000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
02 | CO020 | Anti-fraud helpline (roll over) | 0 | 179565 | OMM | Malose | 179565 |  | Tender | N/A | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | None | 7000 | 14000 | 21000 | 28000 | 35000 | 42000 | 50000 | 50000 | 50000 | 50000 | 50000 | 179565
02 | IN039 | IT Audit (roll over) | 0 | 94957 | OMM | Malose | 94957 |  | Tender | N/A | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | None | 7000 | 14000 | 21000 | 28000 | 35000 | 42000 | 50000 | 50000 | 50000 | 50000 | 50000 | 94957
06 | CO024 | Batho Pele Programme | 0 | 350000 | OEM | Peter | 350000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000
06 | CO028 | Farm Workers Empowerment | 0 | 250000 | OEM | Peter | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
06 | CO029 | Domestic Workers Empowerment | 0 | 250000 | OEM | Peter | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 150000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
06 | CO030 | Back to School Campaign | 0 | 100000 | OEM | Peter | 100000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
06 | CO031 | Mandela Day Celebration | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 120000 | 120000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
06 | CO032 | Children | 0 | 260000 | OEM | Peter | 260000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 160000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000
|  |  | 0 | 6858166 |  |  | 6858166
Land
04 | LA012 | CBD Development Plan Lephalale | 0 | 500000 |  |  | 500000 |  | Tender |  | 2012-08-01 | 12 & 14 Aug 2012 | N/A | 2012-08-31 | 2012-09-20 | 2012-10-11 | 2012-10-22 | 2012-11-28 | 2013-01-25 | 2013-01-25 | Yes | None | 10000 | 10000 | 10000 | 10000 | 130000 | 130000 | 130000 | 350000 | 350000 | 350000 | 500000 | 500000
04 | LA012 | CBD Development Plan BB, Modimolle, Mogalakwena (roll over) | 0 | 318509 |  |  | 318509 |  | Tender |  | PY | PY | N/A | PY | PY | PY | PY | PY | PY | PY | Yes | None | 10000 | 10000 | 10000 | 10000 | 130000 | 130000 | 130000 | 350000 | 350000 | 350000 | 500000 | 318509
04 | LA007 | Review of Spatial Development Framework | 0 | 550000 |  |  | 550000 |  | Tender |  | 2012-08-01 | 12 & 14 Aug 2012 | N/A | 2012-08-31 | 2012-09-20 | 2012-10-11 | 2012-10-22 | 2012-11-28 | 2013-01-25 | 2013-01-25 | Yes | None | 10000 | 10000 | 10000 | 160000 | 160000 | 160000 | 380000 | 380000 | 380000 | 550000 | 550000 | 550000
|  |  | 0 | 1368509 |  |  | 1368509
Sports, Arts & Culture
06 | SC012 | Executive Mayor's Marathon | 0 | 200000 | OEM | Peter | 200000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 200000 | 200000 | 200000
06 | CO-22 | Golf & Life Skills Development for Youth | 0 | 200000 | OEM | Peter | 200000 |  | Limited bidding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-01 | 2012-11-01 | 2012-12-01 | Yes | None | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
06 | SC010 | Women in Sport | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
06 | SC013 | Mayoral Golf Classic | 0 | 200000 | OEM | Peter | 200000 |  | Limited bidding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-10-01 | 2012-10-01 | 2013-02-01 | Yes | None | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 200000 | 200000 | 200000 | 200000 | 200000
06 | SC014 | Disability Sport | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
06 | SC009 | Sport Development (Olympics) | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 50000 | 50000 | 50000 | 50000 | 100000 | 100000 | 100000 | 100000 | 150000 | 150000 | 150000
06 | CO015 | Coordination of Moral Regeneration | 0 | 199732 | OEM | Peter | 199732 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 50000 | 50000 | 50000 | 100000 | 100000 | 100000 | 150000 | 150000 | 150000 | 199732
06 | CO033 | Heritage Celebration | 0 | 200268 | OEM | Peter | 200268 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200268
06 | CO034 | Traditional Leadership development Programme | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
|  |  | 0 | 1600000 |  |  | 1600000
Water & Sanitation
05 | SA033 | Provision of household VIP sanitation at Lephalale and Mogalakwena | 0 | 1000000 | ID | Bernice | 1000000 |  | tender |  | 2013-01-24 | 3 & 4 feb | 2013-02-08 | 2013-02-22 | 2012-12-18 | 2013-02-28 | 2013-03-06 | 2013-03-13 | 2013-03-20 | 2013-03-22 | No | Awaiting Specs | 0 | 5000 | 5000 | 5000 | 305000 | 605000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
05 | SA031 | Northam Sewer Extension 5 | 0 | 168000 | ID | Bernice | 168000 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project complete | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000
05 | SA032 | Mookgophong Township Sewer Connection | 0 | 3000000 | ID | Bernice | 3000000 | WDM/2011-12/31 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | 2012-07-17 | 2012-07-27 | 1 and 2 Aug 2012 | 2012-09-19 | 2012-10-22 | 2012-12-12 | 2013-01-14 | 2013-01-14 | Yes | This information relates to the appointment of a consultants. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1500000 | 2500000 | 3000000
05 | SA032 | Mookgophong Township Sewer Connection (roll over) | 0 | 2998121 | ID | Bernice | 2998121 | WDM/2011-12/31 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | 2012-07-17 | 2012-07-27 | 1 and 2 Aug 2012 | 2012-09-19 | 2012-10-22 | 2012-12-12 | 2013-01-14 | 2013-01-14 | Yes | This information relates to the appointment of a consultants. | 0 | 5000 | 5000 | 255000 | 405000 | 410000 | 410000 | 1700000 | 2998121 | 2998121 | 2998121 | 2998121
|  |  | 0 | 7166121 |  |  | 7166121
Electricity
05 | EL006 | ESCOM Electricity upgrade - co-funding in Modimolle | 0 | 1500000 | ID | Bernice | 1500000 |  | Co-funding LM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Funds were transferred to Modimolle Local Municipality on 24 Aug 2012. | 0 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
05 | EL008 | Electricity upgrade - co-funding in Lephalale | 0 | 650000 | ID | Bernice | 650000 |  | Co-funding LM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Funds were transferred to Lephalale Local Municipality on 26 Oct 2012. | 0 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000
05 | EL009 | Electricity upgrade - co-funding in Bela Bela | 0 | 850000 | ID | Bernice | 850000 |  | Co-funding LM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Funds were transferred to Bela-Bela Local Municipality on 26 Oct 2012. | 0 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000
05 | EL010 | Upgrade of Ga-Seleka drop in center | 0 | 500000 | ID | Bernice | 500000 |  | Tender |  | 2013-01-24 | 3 & 4 feb 2013 | 2013-02-08 | 2013-02-22 | 2012-12-18 | 2013-02-28 | 2013-03-06 | 2013-03-13 | 2013-03-20 | 2013-03-22 | No | Awaiting specs | 0 | 5000 | 5000 | 5000 | 155000 | 355000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
|  |  | 0 | 3500000 |  |  | 3500000
Abattoir
05 | UE029 | Upgrade of the abattoir (roll over) | 1034310 | 0 | ID | Jacky | 1034310 |  | Limited Bidding |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-10-08 | 2012-10-08 | 2012-11-01 | Yes | Various service providers were appointed on 8 Oct 2012 because the SLA with service provider who was appointed through open tender was terminated due to poor performance. | 0 | 0 | 40000 | 840000 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310
|  |  | 1034310 | 0 |  |  | 1034310
|  | Total | 19949914 | 48109544 |  |  | 68059458 | [15 empty] | 651000 | 5376250 | 8778305 | 12594305 | 20403555 | 28142043 | 31705043 | 37617043 | 42820164 | 48516414 | 51106414 | 65351599
68059458
IDP 12/13 Expenditure per Department:
| 001 | CFO | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 002 | MM | 0 | 1102000 | [18 empty] | 7000 | 14000 | 146000 | 483000 | 490000 | 572000 | 730000 | 730000 | 805000 | 905000 | 905000 | 1102000
| 003 | MCSSS | 3809257 | 3693000 | [18 empty] | 0 | 23000 | 473000 | 843000 | 2693000 | 4920000 | 4920000 | 5820000 | 6540000 | 6540000 | 6540000 | 7502257
| 004 | MPED | 0 | 2650000 | [18 empty] | 250000 | 576250 | 682500 | 832500 | 978750 | 1103750 | 1438750 | 1808750 | 2093750 | 2355000 | 2575000 | 2650000
| 005 | MID | 0 | 12238000 | [18 empty] | 178000 | 3188000 | 3758000 | 3958000 | 4408000 | 4938000 | 5478000 | 6838000 | 8738000 | 10338000 | 11738000 | 12238000
| 006 | MEMO | 0 | 7300000 | [18 empty] | 160000 | 970000 | 1600000 | 2450000 | 3160000 | 4980000 | 5230000 | 5330000 | 6080000 | 6380000 | 7050000 | 7300000
| 007 | MSDCS | 490000 | 60000 | [18 empty] | 0 | 0 | 200000 | 300000 | 450000 | 450000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000
| 008 | Disaster | #REF! | #REF! | [18 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 009 | Health | 0 | 2300000 | [18 empty] | 0 | 480000 | 1110000 | 1505000 | 2000000 | 2000000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000
| 020 | Abattoir | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total per dpt | #REF! | #REF! | [18 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Quarterly spending targets | [20 empty] | PROJECTED EXPENDITURE - YEAR TO DATE September: #REF!; PROJECTED EXPENDITURE - YEAR TO DATE December: #REF!; PROJECTED EXPENDITURE - YEAR TO DATE March: #REF!; PROJECTED EXPENDITURE - YEAR TO DATE June: #REF!
|  | 12/13 original IDP | 40350000
|  | 11/12 Roll Over | 0
40350000