## Ann E Procurement Planning
ANNEXURE E: PROJECT PROCUREMENT PLANNING TEMPLATE: 2012/13 FINANCIAL YEAR AS AT 31MARCH 2013
Dpt | Proj # | PROJECT NAME | Total Capital | Total Operational | Dept | Project Manger | Total Budget | Tender Number | Procurement Method | TOR/Quote/ Plan Submission Date | BSC Meeting Date | Advert Date | Compulsory Briefing Session | Advert Closing Date | BEC Meeting Date | BEC Meeting Date | BAC Meeting Date | Appointment Date | Envisaged Date of SLA | Implementation Date | Procurement Process Completed | Comments | PROJECTED EXPENDITURE - YEAR TO DATE
[5 empty] | Dept | [17 empty] | July | August | September | October | November | December | January | February | March | April | May | June
Municipal Environmental Health & Environmental Management
09 | SE003 | Development of BelaBela landfill site | 0 | 1750000 | SDCS | Tebogo | 1750000 | WDM/2012-13/11 | Tender |  | 2013-01-15 | 2013-02-10 | 2013/02/15 & 22 | 2013-03-08 | 2012-08-03 | 2013-03-26 | 2013-04-10 | 2013-04-23 | 2013-04-30 | 2013-04-30 | No | The evaluation report was presented in the BAC on the 10 April 2013. | 0 | 480000 | 960000 | 1255000 | 1550000 | 1550000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 1750000
09 | SE018 | Feasibility study for regional toxic landfill site | 0 | 450000 | SDCS | John | 450000 | WDM/2012-13/16 | Tender |  | 2013-04-19 | 2013-04-28 | 2013-05-06 | 2013-05-13 | 2012-08-06 | 2013-05-23 | 2013-05-30 | 2013-06-06 | 2013-06-13 | 2013-06-13 | No | The project will be re- advertised on an open tender as no service provider met the minimum requirements of tender.Awaiting for specification | 0 | 0 | 150000 | 250000 | 350000 | 350000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
07 | SE019 | Procurement and installation of air quality monitoring equipments | 490000 | 10000 | SDCS | Stanley | 500000 | WDM/2012-13/12 | Tender |  | 2013-01-24 | 2013-04-28 | 2013-05-06 | 2013-05-13 | 2012-08-06 | 2013-05-23 | 2013-05-30 | 2013-06-06 | 2013-06-13 | 2013-06-13 | No | The project will be re- advertised on an open tender as no service provider met the minimum requirements of tender.Awaiting for specification | 0 | 0 | 200000 | 300000 | 400000 | 400000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
07 | SE020 | Air Quality Lekgotla | 0 | 50000 | SDCS | Lilly | 50000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
09 | SE021 | Waste & Environment Lekgotla | 0 | 50000 | SDCS | Lilly | 50000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
09 | HW008 | World Food Day | 0 | 50000 | SDCS | Lilly | 50000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  |  | 490000 | 2360000 |  |  | 2850000
Disaster Management
08 | DM025 | Disaster Risk Management Toll Free Number & promotional signage (roll over) | 0 | 496152 | Disaster | Dan | 496152 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-26 | 2012-11-30 | 2012-12-01 | No | The landline number has been secured and awaiting Telkom's activation. Promotion of signage is awaiting approval from HOD Dept of Road and Transport. | PROJECTED EXPENDITURE - YEAR TO DATE June: 496152
08 | DM030 | Lephalale - Major Heavy Duty Pumper (roll over) | 3795000 | 3369 | Disaster | Dan | 3798369 |  | Tender |  | 2012-10-31 | 2012-11-18 | N/A | 2012-12-07 | 2012-12-10 | 2012-12-10 | 2012-12-14 | 2012-12-18 | 2012-12-23 | 2012-01-01 | Yes | None | PROJECTED EXPENDITURE - YEAR TO DATE June: 3798369
08 | DM020 | Review of Waterberg Disaster Risk Management Plan & Framework | 0 | 200000 | Disaster | Dan | 200000 |  | Notice Board |  | 2013-06-29 | 2013-08-12 | 2013-08-16 | 2013-08-31 | 2012-12-10 | 2013-10-11 | 2013-10-22 | 2012-12-18 | 2012-12-23 | 2012-01-01 | Yes | None | 0 | 0 | 50000 | 100000 | 150000 | 150000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
08 | DM039 | 4x2 Medium Mobile Command Unit (Fully equipped) | 905308 | 3000 | Disaster | Dan | 908308 | WDM/2012-13/01 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-01 | 3 and 4 Oct 2012 | 2012-12-12 | 2012-12-20 | 2013-01-22 | Yes | none | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 700000 | 700000 | 908308
08 | DM040 | Mogalakwena - 40 army tents & 6 bales relief blankets. Thabazimbi - 20 army tents & 3 bales blankets | 373875 | 3000 | Disaster | Dan | 376875 | WDM/2012-13/08 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-11-28 | 2012-12-05 | 2013-01-22 | Yes | None | 3000 | 3000 | 3000 | 3000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 376875
08 | DM027 | Mogalakwena & Lephalale - Drought Relief 2 boreholes each | 0 | 460000 | Disaster | Dan | 460000 | WDM/2012-13/10 | Tender |  | 2013-01-24 | 2013-04-28 | 2013-05-06 | 2013-05-13 | 2012-08-06 | 2013-05-23 | 2013-05-30 | 2013-06-06 | 2013-06-13 | 2013-06-13 | No | The specifications were not aligned to the budget. The project will be re-advertised.Waiting for revised specifications | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 230000 | 230000 | 230000 | 230000 | 460000
08 | DM041 | Lephalale - 4x4 Major Urban Rescue Pumper & equipment | 1469858 | 3000 | Disaster | Dan | 1472858 | WDM/2012-13/02 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-01 | 3 and 4 Oct 2012 | 2012-12-12 | 2012-12-20 | 2013-01-22 | Yes | none | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 950000 | 950000 | 950000 | 950000 | 950000 | 1472858
08 | DM029 | Lephalale - equipment (compressor & scba sets) | 237000 | 3000 | Disaster | Dan | 240000 | WDM/2012-13/09 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-14 | 2012-01-25 | 2012-02-04 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000
08 | DM029 | Lephalale Villages Witpoort - equipment (roll over) | 315063 | 0 | Disaster | Dan | 315063 |  | Tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No | The project name change was done, from mobile office to lephalale fire fighting equipments. The project will be advertised on a notice board. | PROJECTED EXPENDITURE - YEAR TO DATE June: 315063
08 | DM042 | Bela Bela - 4x2 double cab RIV fully equipped | 434862 | 3000 | Disaster | Dan | 437862 | WDM/2012-13/03 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-01 | 3 and 4 Oct 2012 | 2012-12-12 | 2013-12-20 | 2013-01-02 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 700000 | 700000 | 437862
08 | DM015 | Thabazimbi - 1 4x4 LDV with 1 skid unit & equipment (NOT 2) | 436171 | 3000 | Disaster | Dan | 439171 | WDM/2012-13/05 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-14 | 2013-01-22 | 2013-01-22 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 450000 | 450000 | 439171
08 | DM014 | Thabazimbi - Equipment (compressor & scba sets) | 237000 | 3000 | Disaster | Dan | 240000 | WDM/2012-13/09 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-12 | 2013-01-25 | 2013-02-04 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 240000 | 240000 | 240000 | 240000 | 240000
08 | DM014 | Thabazimbi - Equipment (roll over) | 622691 | 0 | Disaster | Dan | 622691 |  | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-12 | 2013-01-22 | 2013-01-22 | Yes | None | PROJECTED EXPENDITURE - YEAR TO DATE June: 622691
08 | DM043 | Mookgophong - Medium Bush Pumper & equipment | 770606 | 3000 | Disaster | Dan | 773606 | WDM/2012-13/04 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-12 | 2013-01-25 | 2013-02-04 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 950000 | 950000 | 773606
08 | DM044 | Modimolle - 1 (not 3) 4x4 LDVs with skid units | 431546 | 3000 | Disaster | Dan | 434546 | WDM/2012-13/09 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-14 | 2013-01-22 | 2013-02-04 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 450000 | 450000 | 434546
08 | DM045 | Modimolle - Heavy Duty foam canon trailer | 298000 | 2000 | Disaster | Dan | 300000 | WDM/2012-13/07 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-11-29 | 2013-01-25 | 2013-02-04 | Yes | None | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 300000 | 300000 | 300000 | 300000 | 300000
08 | DM006 | Modimolle - Equipment (compressor & scba sets) | 237000 | 3000 | Disaster | Dan | 240000 | WDM/2012-13/09 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-12 | 2012-01-25 | 2012-02-04 | Yes | None | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 240000 | 240000 | 240000 | 240000 | 240000
08 | DM006 | Modimolle - Equipment (roll over) | 248369 | 0 | Disaster | Dan | 248369 |  | Tender |  | 2012-06-07 | 8 & 9 July 2012 | N/A | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-02 | 3 and 4 Oct 2012 | 2012-12-12 | 2013-01-22 | 2013-02-04 | Yes | None | PROJECTED EXPENDITURE - YEAR TO DATE June: 248369
08 | DM046 | Modimolle - Refurbishment of Iveco Truck | 0 | 200000 | Disaster | Dan | 200000 | WDM/2012-13/06 | Tender |  | 2012-06-04 | 8 & 9 July 2012 | 2012-07-19 | 2012-07-27 | 1 and 2 Aug 2012 | 2012-08-01 | 3 and 4 Oct 2012 | 2012-11-28 | 2013-01-22 | 2013-02-04 | Yes | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000
08 | DM032 | Fire Station Standby Generator Refurbishment - Mogalakwena (roll over) | 95000 | 0 | Disaster | Dan | 95000 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed | PROJECTED EXPENDITURE - YEAR TO DATE June: 95000
08 | DM036 | Thabazimbi Water Tank (roll over) | 1095600 | 0 | Disaster | Dan | 1095600 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed | PROJECTED EXPENDITURE - YEAR TO DATE June: 1095600
08 | DM037 | Bela Bela Medium Pumper Vehicle & equipment (roll over) | 844804 | 0 | Disaster | Dan | 844804 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed | PROJECTED EXPENDITURE - YEAR TO DATE June: 844804
08 | DM038 | Modimolle - Medium Double Cab RIV (roll over) | 568260 | 0 | Disaster | Dan | 568260 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed | PROJECTED EXPENDITURE - YEAR TO DATE June: 568260
|  |  | 13416013 | 1391521 |  |  | 14807534
Local Economic Development & Tourism
04 | UE040 | WEDA (roll over) | 0 | 1499300 | PED | Michael | 1499300 |  | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-06-30 | Ad hoc | None | PROJECTED EXPENDITURE - YEAR TO DATE June: 1499300
04 | UE047 | Bela Bela Flea market (Roll over) | 0 | 242495 | PED | Matete | 242495 |  | Tender |  | 2012-06-19 | 20 & 22 May 2012 | N/A | 2012-06-08 |  | 2012-06-19 | 2012-11-13 | 2012-12-12 | 2013-01-30 | 2013-02-04 | Yes | SLA signed | PROJECTED EXPENDITURE - YEAR TO DATE June: 242495
04 | UE031 | Co-ordination of district wide LED | 0 | 100000 | PED | Michael | 100000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 20000 | 20000 | 35000 | 35000 | 65000 | 80000 | 100000 | 100000
04 | UE034 | Wildlife Centre - Vaalwater Beautification (roll over) |  | 789744 | PED | Michael | 789744 |  | None |  | None | None | None | None | None | None | None | None | None | None | No | No communication to date
04 | UE038 | Tourism (see below) | 0 | 0 | [18 empty] | PROJECTED EXPENDITURE - YEAR TO DATE June: 0
|  | - Getaway Show | 0 | 250000 | PED | Michael | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 80000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
|  | - Tourism Month Celebrations | 0 | 25000 | PED | Michael | 25000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
|  | - Mabatlane Wildlife Festival | 0 | 250000 | PED | Michael | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 100000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
|  | - Youth Development in Tourism | 0 | 50000 | PED | Michael | 50000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000
|  | - Marula Festival | 0 | 250000 | PED | Michael | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 250000 | 250000 | 250000 | 250000 | 250000
|  | - Tourism Indaba | 0 | 300000 | PED | Michael | 300000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 230000 | 300000 | 300000 | 300000
|  | - Career Expo | 0 | 50000 | PED | Michael | 50000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  | - Publications & Brochures | 0 | 0 | PED | Michael | 0 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | - Local Tourism Association Support | 0 | 25000 | PED | Michael | 25000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 6250 | 12500 | 12500 | 18750 | 18750 | 18750 | 18750 | 18750 | 25000 | 25000 | 25000
04 | UE040 | Waterberg Biosphere Meander Reserve | 0 | 200000 | PED | Betty | 200000 |  | BAC item cofunding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-29 | 2013-01-10 | 2013-01-10 | Yes | None | 0 | 0 | 50000 | 50000 | 50000 | 100000 | 100000 | 100000 | 150000 | 150000 | 150000 | 200000
04 | UE040 | Waterberg Biosphere Meander Reserve (roll over LEDET grant) | 0 | 100000 | PED | Betty | 100000 |  | BAC item cofunding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-13 | 2013-01-10 | 2013-01-10 | Yes | None | PROJECTED EXPENDITURE - YEAR TO DATE June: 100000
04 | UE-43 | Modimolle Security Cameras | 0 | 100000 | PED | Michael | 100000 |  | BAC item cofunding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-15 | 2012-11-28 | 2012-11-28 | Yes | None | 0 | 0 | 25000 | 25000 | 25000 | 50000 | 50000 | 50000 | 75000 | 75000 | 75000 | 100000
|  |  | 0 | 4231539 |  |  | 4231539
Municipal Roads & Stormwater
05 | RS021 | Completion of Modimolle ring road (roll over) | 0 | 2511774 | ID | Jacky | 2511774 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Current year was only extension | 0 | 0 | 0 | 500000 | 1200000 | 1476351 | 1676351 | 1676351 | 1676351 | 1676351 | 1676351 | 2511774
05 | RS041 | Completion of Streets in Mahwelereng (roll over) | 0 | 1644619 | ID | Jacky | 1644619 |  | Tender |  | 2012-08-08 | 2012-05-20 | 2012-05-25 | 2012-06-08 |  | 2012-08-01 | 3 and 4 Oct 2012 | 2012-11-28 | 2013-01-29 | 2013-01-29 | Yes | None | 0 | 0 | 0 | 500000 | 1200000 | 1476351 | 1676351 | 1676351 | 1676351 | 1676351 | 1676351 | 1644619
05 | RS040 | Completion of Bela Bela Street Paving | 0 | 570000 | ID | Bernice | 570000 |  | PY | N/A | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed | 0 | 0 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000 | 570000
05 | RS040 | Completion of Bela Bela Street Paving (roll over) | 0 | 883805 | ID | Bernice | 883805 |  | PY | N/A | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project completed
05 | RS042 | Upgrading of streets in Marapong Township | 0 | 2000000 | ID | Bernice | 2000000 | WDM/2012-13/14 | Tender |  | 2012-06-29 | 15 & 17 July 2012 | 2012-07-20 | 2012-08-03 | 2012-08-07 | 2012-09-19 | 2012-10-22 | 2012-12-12 | 2013-01-14 | 2013-01-14 | Yes | Consultant have been appointed.We have advertised for contractor . | 5000 | 5000 | 5000 | 105000 | 105000 | 120000 | 120000 | 800000 | 1500000 | 1800000 | 2000000 | 2000000
05 | RS043 | Upgrading of streets in Regorogile Township | 0 | 2000000 | ID | Bernice | 2000000 | WDM/2012-13/15 | Tender |  | 2012-06-29 | 15 & 17 July 2012 | 2012-07-20 | 2012-08-03 | 2012-08-07 | 2012-09-19 | 2012-10-22 | 2012-11-28 | 2013-01-14 | 2013-01-14 | Yes | Consultant have been appointed.We have advertised for contractor . | 5000 | 5000 | 5000 | 105000 | 105000 | 120000 | 120000 | 800000 | 1500000 | 1800000 | 2000000 | 2000000
|  |  | 0 | 9610198 |  |  | 9610198
Municipal Support & Institutional Development
03 | IN042 | Procurement of Diesel Generator (roll over) | 494805 | 0 | CSSS |  | 494805 |  | Tender |  | 2012-06-07 | 8 & 9 July 2012 | 2012-07-18 | 2012-07-27 | 2012-08-03 | 2012-08-08 | 2012-10-22 | 2012-12-12 | 2013-01-16 | 2013-01-16 | Yes |  | 0 | 0 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805 | 494805
03 | IN017 | Procurement of movable assets (see below) | [20 empty] | PROJECTED EXPENDITURE - YEAR TO DATE June: 0
|  | - Institutional requests | 560000 | 20000 | CSSS | Maureen | 580000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | The project is implemented on a need basis. | 0 | 0 | 80000 | 80000 | 80000 | 280000 | 280000 | 280000 | 580000 | 580000 | 580000 | 580000
|  | - 23 seater minibus | 400000 | 10000 | CSSS | Phineas | 410000 |  | Tender |  | 2013-01-15 | 10&12 Feb 2013 | N/A | 2013-03-01 | 2012-08-03 | 2013-03-26 | 2013-04-10 | 2013-04-23 | 2013-04-30 | 2013-04-30 | No | The evaluation report was presented in the BAC on the 10 April 2013. | 0 | 10000 | 10000 | 380000 | 380000 | 380000 | 380000 | 380000 | 410000 | 410000 | 410000 | 410000
|  | - Procurement of municipal pool vehicles | 700000 | 10000 | CSSS | Phineas | 710000 |  | Tender |  | 2013-04-19 | 2013-04-28 | 2013-05-06 | 2013-05-13 | 2012-08-06 | 2013-05-23 | 2013-05-30 | 2013-06-06 | 2013-06-13 | 2013-06-13 | No | None | 0 | 10000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 610000 | 610000 | 610000 | 710000
03 | IN017 | Procurement of movable assets (roll over) | 381372 | 0 | CSSS | Maureen | 381372 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | The project is implemented on a need basis. | PROJECTED EXPENDITURE - YEAR TO DATE December: 81372; PROJECTED EXPENDITURE - YEAR TO DATE January: 81372; PROJECTED EXPENDITURE - YEAR TO DATE February: 81372; PROJECTED EXPENDITURE - YEAR TO DATE March: 81372; PROJECTED EXPENDITURE - YEAR TO DATE April: 81372; PROJECTED EXPENDITURE - YEAR TO DATE May: 81372; PROJECTED EXPENDITURE - YEAR TO DATE June: 381372
03 | IN021 | Procurement of IT equipment | 300000 | 0 | CSSS | Keoma | 300000 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | The project is implemented on a need basis. | 0 | 0 | 80000 | 80000 | 80000 | 160000 | 160000 | 160000 | 240000 | 240000 | 240000 | 300000
03 | IN021 | Procurement of IT equipment (roll over) | 274157 | 0 | CSSS | Keoma | 274157 |  | Quotes |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | The project is implemented on a need basis. | PROJECTED EXPENDITURE - YEAR TO DATE December: 276414; PROJECTED EXPENDITURE - YEAR TO DATE January: 276414; PROJECTED EXPENDITURE - YEAR TO DATE February: 276414; PROJECTED EXPENDITURE - YEAR TO DATE March: 276414; PROJECTED EXPENDITURE - YEAR TO DATE April: 276414; PROJECTED EXPENDITURE - YEAR TO DATE May: 276414; PROJECTED EXPENDITURE - YEAR TO DATE June: 274157
03 | IN044 | District Wide procurement of IT equipment to be VOIP compatible | 0 | 500000 | CSSS | Keoma | 500000 |  | Tender |  | 2013-01-15 | 28 & 29 JAN | N/A | 2013-03-01 | 2012-08-03 | 2013-03-26 | 2013-04-10 | 2013-04-23 | 2013-04-30 | 2013-04-30 | No | The evaluation report was presented in the BAC on the 10 April 2013. | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
02 | IN024 | PMS | 0 | 300000 | MM | Philemon | 300000 |  | Tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ? | ? | ? | Yes | None | 0 | 0 | 75000 | 75000 | 75000 | 150000 | 150000 | 150000 | 225000 | 225000 | 225000 | 300000
02 | IN024 | PMS (roll over) | 0 | 304065 | MM | Philemon | 304065 |  | Tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ? | ? | ? | Yes | None | 0 | 0 | 75000 | 75000 | 75000 | 150000 | 150000 | 150000 | 225000 | 225000 | 225000 | 304065
03 | IN027 | District Wide Integrated Financial Management Systems | 350000 | 3150000 | CSSS | Nadine | 3500000 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-09-07 | 2011-11-01 | 2011-11-01 | Yes | Further roll-out through LMs | 0 | 0 | 0 | 0 | 1850000 | 1850000 | 1850000 | 2750000 | 2750000 | 2750000 | 2750000 | 3500000
03 | IN027 | District Wide Integrated Financial Management Systems (roll over) | 50000 | 3150000 | CSSS | Nadine | 3200000 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2011-09-07 | 2011-11-01 | 2011-11-01 | Yes | Further roll-out through LMs | 0 | 0 | 0 | 0 | 1850000 | 1850000 | 1850000 | 2750000 | 2750000 | 2750000 | 2750000 | 3200000
03 | IN043 | Installation of WDM CCTV Cameras - MDC & Abattoir | 1002257 | 0 | CSSS | Phineas | 1002257 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-08-13 | 2012-09-03 | 2012-09-03 | Yes | None | 0 | 0 | 0 | 0 | 0 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 1002257
02 | IN045 | District Wide Audit System | 0 | 350000 | MM | Malose | 350000 |  | Tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-04-19 | 2013-04-26 | 2013-04-26 | No | Limited Bidding has been approved .In the process of Issuing appointment letter. | 0 | 0 | 50000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000
03 | IN046 | Installation of new lift in WDM Head Office Building | 497000 | 3000 | CSSS | Phineas | 500000 |  | Tender |  | 2013-04-23 | 2013-05-05 | 2013-05-13 | 2013-05-20 | 2012-12-18 | 2013-05-27 | 2013-06-03 | 2013-06-11 | 2013-06-18 | 2013-06-18 | No | None | 0 | 3000 | 3000 | 3000 | 3000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
02 | IN035 | Lephalale Turnaround Strategy | 0 | 526425 | MM | Philemon | 526425 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | PY | PY | PY | Yes | None | 0 | 0 | 0 | 0 | 0 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 526425
03 | IN041 | District Wide VPN Network | 0 | 1700000 | CSSS | Keoma | 1700000 |  | S32 - organ of state tender |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-10-01 | 2012-10-01 | 2012-10-31 | Yes | None | 0 | 0 | 0 | 0 | 0 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 1700000
|  |  | 5009591 | 10023490 |  |  | 15033081
Communicity Participation & Good Governance
06 | CO009 | Communication | 0 | 450000 | OEM | Pat | 450000 |  | Tender |  | 2013-04-23 | 2013-05-05 | 2013-05-13 | 2013-05-20 | 2012-12-18 | 2013-05-27 | 2013-06-03 | 2013-06-11 | 2013-06-18 | 2013-06-18 | No | None | 0 | 50000 | 100000 | 200000 | 200000 | 250000 | 250000 | 250000 | 350000 | 350000 | 500000 | 450000
06 | CO009 | Communication (roll over) | 0 | 431644 | OEM | Pat | 431644 |  | Tender |  | 2012-11-09 | 2013-04-23 | 2013-05-05 | 2013-05-13 | 2013-05-20 | 2012-12-18 | 2013-05-27 | 2013-06-03 | 2013-06-11 | 2013-06-18 | 2013-06-18 | None | 0 | 50000 | 100000 | 200000 | 200000 | 250000 | 250000 | 250000 | 350000 | 350000 | 500000 | 431644
06 | CO013 | Production of Diaries for Cllrs & Traditional Leaders | 0 | 40000 | OEM | Pat | 40000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-02-04 | N/A | N/A | Yes | None | 0 | 0 | 0 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
06 | CO011 | District IDP Public Participation Programme - EMO | 0 | 900000 | OEM | Peter | 900000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 30000 | 30000 | 280000 | 280000 | 280000 | 530000 | 530000 | 530000 | 780000 | 780000 | 900000 | 900000
02 | CO012 | District IDP Strategic Planning Programme - MMO | 0 | 402000 | OMM | Philemon | 402000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-03-07 | N/A | N/A | Yes | None |  | 0 | 0 | 30000 | 30000 | 30000 | 180000 | 180000 | 180000 | 280000 | 280000 | 402000
06 | CO014 | Learning & sharing (twinning agreement) | 0 | 200000 | OEM | Peter | 200000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 60000 | 60000 | 60000 | 60000 | 100000 | 100000 | 100000 | 100000 | 150000 | 150000 | 200000
06 | CO016 | Gender Programs | 0 | 700000 | OEM | Peter | 700000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 300000 | 300000 | 300000 | 300000 | 600000 | 600000 | 600000 | 600000 | 700000 | 700000 | 700000
06 | CO035 | Senior Citizens | 0 | 400000 | OEM | Peter | 400000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 300000 | 300000 | 300000 | 350000 | 350000 | 400000 | 400000 | 400000
06 | CO017 | HIV/AIDS Awareness Programs | 0 | 550000 | OEM | Peter | 550000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 50000 | 50000 | 250000 | 250000 | 450000 | 450000 | 450000 | 550000 | 550000 | 550000 | 550000
06 | CO018 | People with Disability Programs | 0 | 450000 | OEM | Peter | 450000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 10000 | 10000 | 10000 | 20000 | 20000 | 350000 | 350000 | 350000 | 450000 | 450000 | 450000 | 450000
06 | CO019 | Youth Programs | 0 | 650000 | OEM | Joseph | 650000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 150000 | 150000 | 150000 | 250000 | 250000 | 250000 | 250000 | 250000 | 650000 | 650000
02 | CO020 | Anti-fraud helpline | 0 | 50000 | OMM | Malose | 50000 |  | Tender | N/A | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | None | 7000 | 14000 | 21000 | 28000 | 35000 | 42000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
02 | CO020 | Anti-fraud helpline (roll over) | 0 | 179565 | OMM | Malose | 179565 |  | Tender | N/A | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | None | 7000 | 14000 | 21000 | 28000 | 35000 | 42000 | 50000 | 50000 | 50000 | 50000 | 50000 | 179565
02 | IN039 | IT Audit (roll over) | 0 | 94957 | OMM | Malose | 94957 |  | Tender | N/A | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | None | 7000 | 14000 | 21000 | 28000 | 35000 | 42000 | 50000 | 50000 | 50000 | 50000 | 50000 | 94957
06 | CO024 | Batho Pele Programme | 0 | 350000 | OEM | Peter | 350000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000
06 | CO028 | Farm Workers Empowerment | 0 | 250000 | OEM | Peter | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
06 | CO029 | Domestic Workers Empowerment | 0 | 250000 | OEM | Peter | 250000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 150000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
06 | CO030 | Back to School Campaign | 0 | 100000 | OEM | Peter | 100000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
06 | CO031 | Mandela Day Celebration | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 120000 | 120000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
06 | CO032 | Children | 0 | 260000 | OEM | Peter | 260000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-03-13 | N/A | N/A | Yes | None | 0 | 0 | 0 | 0 | 160000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000
|  |  | 0 | 6858166 |  |  | 6858166
Land
04 | LA012 | CBD Development Plan Lephalale | 0 | 500000 |  |  | 500000 |  | Tender |  | 2012-08-01 | 12 & 14 Aug 2012 | N/A | 2012-08-31 | 2012-09-20 | 2012-10-11 | 2012-10-22 | 2012-11-28 | 2013-01-25 | 2013-01-25 | Yes | SLA awaiting for signature | 10000 | 10000 | 10000 | 10000 | 130000 | 130000 | 130000 | 350000 | 350000 | 350000 | 500000 | 500000
04 | LA012 | CBD Development Plan BB, Modimolle, Mogalakwena (roll over) | 0 | 318509 |  |  | 318509 |  | Tender |  | PY | PY | N/A | PY | PY | PY | PY | PY | PY | PY | Yes | None | 10000 | 10000 | 10000 | 10000 | 130000 | 130000 | 130000 | 350000 | 350000 | 350000 | 500000 | 318509
04 | LA007 | Review of Spatial Development Framework | 0 | 550000 |  |  | 550000 |  | Tender |  | 2012-08-01 | 12 & 14 Aug 2012 | N/A | 2012-08-31 | 2012-09-20 | 2012-10-11 | 2012-10-22 | 2012-11-28 | 2013-01-25 | 2013-01-25 | Yes | None | 10000 | 10000 | 10000 | 160000 | 160000 | 160000 | 380000 | 380000 | 380000 | 550000 | 550000 | 550000
|  |  | 0 | 1368509 |  |  | 1368509
Sports, Arts & Culture
06 | SC012 | Executive Mayor's Marathon | 0 | 200000 | OEM | Peter | 200000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 200000 | 200000 | 200000
06 | CO-22 | Golf & Life Skills Development for Youth | 0 | 200000 | OEM | Peter | 200000 |  | Limited bidding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-11-01 | 2012-11-01 | 2012-12-01 | Yes | None | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
06 | SC010 | Women in Sport | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
06 | SC013 | Mayoral Golf Classic | 0 | 200000 | OEM | Peter | 200000 |  | Limited bidding | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-10-01 | 2012-10-01 | 2013-02-01 | Yes | None | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 200000 | 200000 | 200000 | 200000 | 200000
06 | SC014 | Disability Sport | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
06 | SC009 | Sport Development (Olympics) | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 50000 | 50000 | 50000 | 50000 | 100000 | 100000 | 100000 | 100000 | 150000 | 150000 | 150000
06 | CO015 | Coordination of Moral Regeneration | 0 | 199732 | OEM | Peter | 199732 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2013-04-12 | N/A | N/A | Yes | None | 0 | 0 | 50000 | 50000 | 50000 | 100000 | 100000 | 100000 | 150000 | 150000 | 150000 | 199732
06 | CO033 | Heritage Celebration | 0 | 200268 | OEM | Peter | 200268 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200268
06 | CO034 | Traditional Leadership development Programme | 0 | 150000 | OEM | Peter | 150000 |  | Quotes | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Ad hoc | None | 0 | 0 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
|  |  | 0 | 1600000 |  |  | 1600000
Water & Sanitation
05 | SA033 | Provision of household VIP sanitation at Lephalale and Mogalakwena | 0 | 1000000 | ID | Bernice | 1000000 |  | tender |  | 2013-01-24 | 3 & 4 feb | 2013-02-08 | 2013-02-22 | 2012-12-18 | 2013-02-28 | 2013-03-06 | 2013-03-13 | 2013-03-20 | 2013-03-22 | No | Awaiting Specs | 0 | 5000 | 5000 | 5000 | 305000 | 605000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
05 | SA031 | Northam Sewer Extension 5 | 0 | 168000 | ID | Bernice | 168000 |  | Tender |  | PY | PY | PY | PY | PY | PY | PY | PY | PY | PY | Yes | Project complete | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000 | 168000
05 | SA032 | Mookgophong Township Sewer Connection | 0 | 3000000 | ID | Bernice | 3000000 | WDM/2011-12/31 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | 2012-07-17 | 2012-07-27 | 1 and 2 Aug 2012 | 2012-09-19 | 2012-10-22 | 2012-12-12 | 2013-01-14 | 2013-01-14 | Yes | This information relates to the appointment of a consultants. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1500000 | 2500000 | 3000000
05 | SA032 | Mookgophong Township Sewer Connection (roll over) | 0 | 2998121 | ID | Bernice | 2998121 | WDM/2011-12/31 | Tender |  | 2012-06-07 | 8 & 9 July 2012 | 2012-07-17 | 2012-07-27 | 1 and 2 Aug 2012 | 2012-09-19 | 2012-10-22 | 2012-12-12 | 2013-01-14 | 2013-01-14 | Yes | This information relates to the appointment of a consultants. | 0 | 5000 | 5000 | 255000 | 405000 | 410000 | 410000 | 1700000 | 2998121 | 2998121 | 2998121 | 2998121
|  |  | 0 | 7166121 |  |  | 7166121
Electricity
05 | EL006 | ESCOM Electricity upgrade - co-funding in Modimolle | 0 | 1500000 | ID | Bernice | 1500000 |  | Co-funding LM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Funds were transferred to Modimolle Local Municipality on 24 Aug 2012. | 0 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
05 | EL008 | Electricity upgrade - co-funding in Lephalale | 0 | 650000 | ID | Bernice | 650000 |  | Co-funding LM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Funds were transferred to Lephalale Local Municipality on 26 Oct 2012. | 0 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000
05 | EL009 | Electricity upgrade - co-funding in Bela Bela | 0 | 850000 | ID | Bernice | 850000 |  | Co-funding LM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Yes | Funds were transferred to Bela-Bela Local Municipality on 26 Oct 2012. | 0 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000
05 | EL010 | Upgrade of Ga-Seleka drop in center | 0 | 500000 | ID | Bernice | 500000 |  | Tender |  | 2013-03-08 | 2013-03-14 | 2013-04-23 | 2013-05-07 | 2012-12-18 | 2013-05-13 | 2013-05-22 | 2013-05-31 | 2013-06-06 | 2013-06-06 | No | The project have been advertised . | 0 | 5000 | 5000 | 5000 | 155000 | 355000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
|  |  | 0 | 3500000 |  |  | 3500000
Abattoir
05 | UE029 | Upgrade of the abattoir (roll over) | 1034310 | 0 | ID | Jacky | 1034310 |  | Limited Bidding |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2012-10-08 | 2012-10-08 | 2012-11-01 | Yes | Various service providers were appointed on 8 Oct 2012 because the SLA with service provider who was appointed through open tender was terminated due to poor performance. | 0 | 0 | 40000 | 840000 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310 | 1034310
|  |  | 1034310 | 0 |  |  | 1034310
|  | Total | 19949914 | 48109544 |  |  | 68059458 | [15 empty] | 651000 | 5376250 | 8778305 | 12594305 | 20403555 | 28142043 | 31705043 | 37617043 | 42820164 | 48516414 | 51106414 | 65351599
68059458
IDP 12/13 Expenditure per Department:
| 001 | CFO | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 002 | MM | 0 | 1102000 | [18 empty] | 7000 | 14000 | 146000 | 483000 | 490000 | 572000 | 730000 | 730000 | 805000 | 905000 | 905000 | 1102000
| 003 | MCSSS | 3809257 | 3693000 | [18 empty] | 0 | 23000 | 473000 | 843000 | 2693000 | 4920000 | 4920000 | 5820000 | 6540000 | 6540000 | 6540000 | 7502257
| 004 | MPED | 0 | 2650000 | [18 empty] | 250000 | 576250 | 682500 | 832500 | 978750 | 1103750 | 1438750 | 1808750 | 2093750 | 2355000 | 2575000 | 2650000
| 005 | MID | 0 | 12238000 | [18 empty] | 178000 | 3188000 | 3758000 | 3958000 | 4408000 | 4938000 | 5478000 | 6838000 | 8738000 | 10338000 | 11738000 | 12238000
| 006 | MEMO | 0 | 7300000 | [18 empty] | 160000 | 970000 | 1600000 | 2450000 | 3160000 | 4980000 | 5230000 | 5330000 | 6080000 | 6380000 | 7050000 | 7300000
| 007 | MSDCS | 490000 | 60000 | [18 empty] | 0 | 0 | 200000 | 300000 | 450000 | 450000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000
| 008 | Disaster | #REF! | #REF! | [18 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 009 | Health | 0 | 2300000 | [18 empty] | 0 | 480000 | 1110000 | 1505000 | 2000000 | 2000000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000
| 020 | Abattoir | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total per dpt | #REF! | #REF! | [18 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Quarterly spending targets | [20 empty] | PROJECTED EXPENDITURE - YEAR TO DATE September: #REF!; PROJECTED EXPENDITURE - YEAR TO DATE December: #REF!; PROJECTED EXPENDITURE - YEAR TO DATE March: #REF!; PROJECTED EXPENDITURE - YEAR TO DATE June: #REF!
|  | 12/13 original IDP | 40350000
|  | 11/12 Roll Over | 0
40350000